## Process
Serial No | LL Number | Date | Discipline | DC | Project Name | Client | Facility category | LL category | Subject1 | Subject2 | Subject3 | Title | Background | Root cause | Corrective action | Preparer | Preparer Desn | Reviewer | Reviewer Desgn | Approver | Approver Desgn
1 | CHN-ECLL-PR-0001 |  | Process | PR | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Flare System and Optimization | Flare optimization – Qualifications in the bid not clear. |  | Optimization initiatives like Flare optimization should have suitable qualifications and basis specified in the Bid so that any changes to the optimization initiative and resultant commercial / schedule impacts can be covered during execution
2 | CHN-ECLL-PR-0002 |  | Process | PR | D6071 ¦ QP Bul Hanine | Qatar Petroleum |  | ECLL |  |  |  | Incorrection selection of software (imposed by Client) | For MOL transient analysis, Pipeline studio software had been used as specified in SOW document. Surge analysis results indicates -ve / vacuum pressure in some scenarios and requires further analysis which Pipeline studio is not capable of doing. The wrong software (pipeline studio) was imposed by QP to perform force vs. time and slack line simulations but software was not able to do. Re-work and additional costs resulted with very late delivery of the results causing significant negative variance. Additionally, the wrong FA contractor (PACE- black listed) were selected post award (different from bid basis, due to instruction from management and MOC raised). LL here is to make proper selection of subcontractor who is competent in performing the work and has full hands-on knowledge of specialist tools. | 1. Wrong software used. 2. Incorrect modelling approach (not using pump Torque / inertia curve). 3. Slack line flow phenomenon (Vapor collapse) is not available in latest version of Pipeline studio software. 4. Unbalance force data extraction is not possible in Pipeline Studio. Software only generates Pressure-time history data. | 1. Thorough review of scope of work 2. Checking of specified software capabilities. 3. Consult with software vendor, if required. 4. Discuss modelling approach with Client / SME.
3 | CHN-ECLL-PR-0003 |  | Process | PR | D6167 ¦ RasGas | Qatar Gas |  | ECLL |  |  |  | Maintaining records of critical decisions | Discussions with Company and critical decisions are to be documented. During Pre-FEED, many ad-hoc meetings are conducted to address critical aspects of engineering design. It was found during Pre-FEED that adequate records were not maintained for the critical decisions made with COMPANY | - Lack of awareness to understand the importance of keeping of records | Discussions with Company are to be recorded via mail or Record of conversations (ROC) template. Also critical decisions are to be formalized via Technical query. This will help during the later phases of the project. It is also recommended to keep the records of important decisions during bid.
4 | CHN-ECLL-PR-0004 |  | Process | PR | D6167 ¦ RasGas | Qatar Gas |  | ECLL |  |  |  | COMPANY concurrent projects and its impact on engineering design | During Pre-FEED, Information on the parallel ongoing project (which Company is performing) was provided to us in the middle of the project which leads to re-work and increases the number of deliverables and man-hrs for the Riser platform. | Some of the outcomes of the Company projects impacts the design of the Riser platform. | -
5 | CHN-ECLL-PR-0005 |  | Process | PR | D6167 ¦ RasGas | Qatar Gas |  | ECLL |  |  |  | Use of appropriate tool for Fluid Characterization | Different results were arrived due to usage of Fluid characterization tools (PVTSIM and MULTIFLASH). Transient hydraulic analysis performed by Wood Group Kenny (subcontractor) used wrong fluid characterization software PVTSIM. This resulted in less liquid holdup volumes in the pipeline. The error was identified and MULTIFLASH software has been used to re-characterize the fluid compositions which resulted in higher liquid hold-ups in the pipeline | Incorrect fluid characterization software was used | Reliable fluid characterization software MULTIFLASH to be considered for transient studies.
6 | CHN-ECLL-PR-0006 |  | Process | PR | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | Requirement of Full Bore Valves | Full Bore (FB) valves for all process lines pigging / non pigging line. The bid was carried by two different contractors. One bid contractor explicitly mentioned on the P&IDs that the drain valves as FB (Full Bore), while the other didn't mention anything. The same was followed on the P&IDs. Once the MTO was taken by the piping, wherever FB mentioned on P&ID was considered. If not mentioned, piping considered as a reduced bore. Since ADMA standards (SP-1145) calls for FB for all the drain lines, all the P&IDs were revised and also the MTO. | Lack of identification of FB Valves on P&IDs in line with Client specs / standards. | During bid stage, check the requirements of Full Bore (FB) for drain lines based on the Client relevant standards.
7 | CHN-ECLL-PR-0007 |  | Process | PR | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | Sand content in well fluid and its impact on design | Sand content As per the SOW, the topside line sizing was performed considering sand content as specified in ADMA standard SP-1060. On further Surveillance of the bid document, it was noticed in HAZOP report stating "ADMA provided composition does not contain sand". Misnomer existed regarding sand in well fluid. However, the well fluid not containing sand was captured in the process design basis. So, the valve seat was considered as soft seat. | As per the SOW, the topside line sizing was performed considering sand content as specified in ADMA standard SP-1060. On further Surveillance of the bid document, it was noticed in HAZOP report stating "ADMA provided composition does not contain sand". Misnomer existed regarding sand in well fluid. However, the well fluid not containing sand was captured in the process design basis. So, the valve seat was considered as soft seat. | During BID, ensure that all the closed FEED HAZOP actions are implemented in FEED package. If not raise necessary TQ.
8 | CHN-ECLL-PR-0008 |  | Process | PR | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | Produced water and chloride content | Specify the chloride content in produced water The H2S/CO2/chloride content in produced water analysis of the well fluid are included in both the instrument and mechanical datasheets. However, it was not included in the flame arrestor, which is considered as a special piping item. So, the chloride presence was not included in the flame arrester and rupture disc data sheet. It was later noticed that during start of depressurization the temperature was below 60°C. On prolonged depressurization it was noticed that the temperature was above 65°C. In marine environment with high chloride content and temperature above 65°C SS is not suitable metallurgy. This led to change of the metallurgy from 316L SS to cast alloy. | - Chloride content was missed to be mentioned initially in process datasheet, and this was captured subsequently. | Ensure that the H2S/CO2/chloride content in produced water analysis of the well fluid are included in the special piping item datasheets to ensure the correct metallurgy selection.
9 | CHN-ECLL-PR-0009 |  | Process | PR | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | Nitrogen blanketing requirement for Cold vent / Drain drum | ZK-300 Cold Vent/Drain Drum MOC was not found suitable at late stage of project. Nitrogen blanketing was introduced so as to ensure its suitability. | The Cold Vent/Drain Drum on ZK-300 should have been kept under nitrogen blanketing during normal operation. However, the requirement of nitrogen blanketing was discussed with the Client operations and agreed that it remove the nitrogen blanketing. However, during the last stage of engineering of the project, the metallurgist was under the impression that the vessel was still under nitrogen blanketing. Since, it was not, this issue impacted his RBI (Risk Based Inspection) study. Also, corrosion and petting would impact the vessel metallurgy (316L SS) due to the presence of chloride, which will remain on the bottom of the vessel, and oxygen ingress | Design Basis IDC to be checked thoroughly by all disciplines so that nothing is missed out. PFDs will be produced by Process to cover the fluid data as it provides the input data to the MSDs
10 | CHN-ECLL-PR-0010 |  | Process | PR | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | Type of connection from IDBB to Cold vent / Drain drum | ADMA agreed to combine the cavity bleed of IDBB valve with adjacent cavity bleed of IDBB valve with one common second isolation valve. The bid was carried by two different contractors. One bid contractor explicitly showed on the P&IDs that the bleed from IDBB (Integral Double Block & Bleed) as hard piped to the Cold Vent/Drain Drum. However, the other contractor kept the drain from bleed local. The same was followed on P&IDs during engineering stage. However, due to the presence of high H2S concentrations, the Client insisted that all the drain from drains shall be hard-piped to the Cold Vent/Drain Drum. then, the same was followed and P&IDs were revised accordingly. This impacted the layout. | - Inadequate assessment of type of Bleed connection to Cold Vent / Drain drum (considering Client standards) | Each drain source required additional valves to have individual second isolation valve. During Bid, type of bleed connection to Cold vent / Drain drum must be selected in line with client specification requirement
11 | CHN-ECLL-PR-0011 |  | Process | PR | D6803 ¦ RasGas FAXP | Qatar Gas |  | ECLL |  |  |  | Demolition scope on P&IDs | The demolition P&IDs should show the actual demolition phase of the project. If Demolition scope is to be carried out at different stages, separate P&IDs must be issued. Clarity must be brought to ensure that demolition scope is well defined per campaign considering construction / demolition aspects of project. | During FEED, the early tie-in activity demolition and main campaign demolition has been shown on same P&ID. Lack of attention paid to the construction requirements. | P&IDs should split according to the demolition phase of the project. During BID engineering phase the requirements and man-hrs will be included accordingly.
12 | CHN-ECLL-PR-0012 |  | Process | PR | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | Generation of Process Datasheets. | There are no contractual requirement to generate Process datasheet (PDS) for equipment and instruments. Hence all the process inputs are provided directly to Mechanical datasheet and Instrument datasheet. Due to design development, there are changes in the process data. Since there are no process datasheet, it was difficult to have a control on the revisions of Process data which resulted in the inconsistency between process documents and other discipline documents. | No Process datasheets were followed for project, hence change in process inputs were not controlled. Change in process data required re-issuance of equipment / valve datasheets, which were owned by other disciplines. Hence, a lot of inter-discipline issues were faced and inconsistencies among disciplines were found. | Generate and circulate process datasheet internally to have proper control on process data to other disciplines. Process data sheets can be internal document if not required contractually to be issued to Client.
13 | CHN-ECLL-PR-0013 |  | Process | PR | D7233 ¦ Umm Shaif | ADNOC |  | ECLL |  |  |  | Chloride mapping | Concentration of chlorides in streams, many times governs the metallurgy selection, and it is very important aspect for material selection purposes, particularly if the use of austenitic stainless steel category materials are being considered. Generally chloride mapping is not listed in key documents like HMBs and if the same is mentioned there, then it cannot be missed. For example, chloride concentration can lead to material selection (due to liquid carry over) for compressor casing and impeller. Hence, it will have significant cost impact as well. | - Chloride concentration may govern metallurgy many times and the same was not followed initially, which led to revision in many engineering deliverables. | Recommended to Include concentration of chlorides in stream on the H&MB for material selection purposes so that aspect of chloride concentration is not missed during material selection.
14 | CHN-ECLL-PR-0014 |  | Process | PR | D7244 ¦ Belbazem FEED | Al Yasat Petroleum |  | ECLL |  |  |  | Pre-Bid agreements with Vendors during FEED Design Competition | For design competitions, pre-bid agreements with vendors/ packagers is recommended to achieve the following: 1) Get a buy-in of the vendor / packager to provide the most optimal solution. 2) Partly unload engineering to Vendor 3) Provide an integrated and complete solution with minimal risk. 4) Shorten the schedule during EPC 5) Align scope much better to optimize the cost. Mechanism to shortlist the items where such arrangement is beneficial and the actual vendor/packager is to be developed. As presently there is no process to implement the same. | Following are the major challenges, which were faced during Belbazem FEED design competition. - Lack of vendor inputs on critical aspects such as process calculations, GAs, Dimensions, Weights etc. - Least interest in resolving technical queries by vendors. - Vendors also do not want to spend man-hours during FEED which is a natural mindset. - Lack of availability of detailed deviation list in vendor quotes. | During FEED design competitions, Pre-bid agreements will help to obtain detailed information and firm prices. Hence, it is recommended that PBAs are worked out in consultation with SCM and Project PMT team. Lack of vendor inputs / technical details from vendors must be covered with appropriate PROM during bidding.
15 | CHN-ECLL-PR-0015 |  | Process | PR | D7244 ¦ Belbazem FEED | Al Yasat Petroleum |  | ECLL |  |  |  | Injection quill design inputs | Generally, Velocity details are checked during detailed engineering to ensure that quill will be able to withstand velocity of the fluid (Wake frequency calculations from vendor). However, attention was not paid to this, and Velocity details were not specified for injection quill design. Due to this omission, quills were found to be wrongly designed. This resulted in change to model, isometrics etc. | Lack of full design inputs and on-time closure with vendor. - Wake frequency calculations and velocity aspects were ignored. | Piping engineering should liaise with Process Engineering to include gas velocity, potential for slugs and fluid properties such as density, molecular weight and operating conditions. Factors to consider include future operations (e.g. at lower pressures) and upset conditions. Process engineering should review the quill vendor data to make sure that all process conditions are adequately considered. Location of the injection quill insert is also to be appropriately considered (away from bends etc.) and calculations should be closed early prior to issue of isometrics to fabrication.
16 | CHN-ECLL-PR-0016 |  | Process | PR | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Brownfield tie-ins - Scope growth beyond physical tie-in | (1) Incompatible material at tie-ins in the flare system was noticed. (2) Concerns on inadequacy of existing Fresh water & Instrument air systems to meet new demands in project scope Root Causes: a. Interpretation of Scope b. Lack of information from Client |  | • Tie-in list shall clearly identify process parameters along with upstream MOC, fluid compatibility information • Tie-in list shall be populated during FEED or FEED endorsement period and missing information shall be clarified with client. • Inconsistencies at the tie-in location should be clarified with Company. • Inclusion of Process engineer for site survey shall be mandatory to verify / collect upstream information. Request of any missing data shall be immediately raised to PMT / Company.
17 | CHN-ECLL-PR-0017 |  | Process | PR | N0510 ¦ TYRA | Maersk |  | ECLL |  |  |  | P&ID revision for HAZOP | IFR (2nd issue) P&ID was issued to COMPANY and planned to conduct HAZOP immediately (Same philosophy in TYRA). COMPANY refused to participate in HAZOP as it is the first of P&ID to them. It delayed HAZOP, AFD P&ID and piping isometric release to site. |  | Same approach (HAZOP on IFR P&ID) followed in TYRA, however, IDC revision (1st issue) of P&IDs will be reviewed by COMPANY and DNV-GL. IFR revision of P&ID will incorporate the agreed comments. These updated P&IDs will be used for HAZOP. This approach expedites HAZOP and other safety studies and AFD issue of drawings & documents.
18 | CHN-ECLL-PR-0018 |  | Process | PR | LTA Guaranteed Scope | Saudi Aramco | Auxiliary platform | ECLL |  |  |  | Pipeline joint coating temperature and process simulation work during bid | Pipeline joint coating temperature was limited by Subsea to 80 degC. Well temperatures varied from different reservoirs and some exceeded the coating temperature. Hence Process were asked to make it fit the joint temperature if that was possible. Several pipesim simulation were performed to create a 'mix' temperature which resulted in a temperature that matched the subsea criteria. The LL is to perform simulations during bid (and hours to be provided) to ensure we don't exceed subsea criteria. This is already built into FEED Verification procedure and Process Bid checklist. Piping Design temperature and Pipeline Design temperature may not be same. Well-head platform piping design temperature is 200 °F while pipeline design temperature given is only 160 °F. Increase in pipeline design temperature will increase number of anodes and any temperature above 176 F (80 deg C) would require non standard joint coating which will increase marine time and increase in cost. | This was missed during bid and not captured even during early stage of detailed engineering. | During Bid Engineering, add sufficient hours to carryout the PIPESIM simulation to evaluate max pipeline temperature. Work with subsea to ensure design is suitable. The above analysis is required during FEED verification. It is also recommended to review the Pipeline and Topside piping spec break, and associated impact on engineering design.
19 | CHN-ECLL-PR-0019 |  | Process | PR | LTA Guaranteed Scope | Saudi Aramco | Tie-in platform | ECLL |  |  |  | Improper material selection and cost escalation during execution of project. | Material selection: Calculation of partial pressure of H2S and CO2. missed during bid and early stage of detailed engineering. If partial pressure of H2S or CO2 is greater than 50 psia, FBE lining is not suitable. Partial pressure of H2S and CO2 exceeded 50 psia for Marjan field was noticed late in the project. | No MSD was available to identify the material requirement. | Bid process engineer is required to communicate this across affected disciplines.
20 | CHN-ECLL-PR-0020 |  | Process | PR | LTA Guaranteed Scope | Saudi Aramco | Auxiliary platform | ECLL |  |  |  | Inconsistencies in P&IDs | Significant inconsistencies among SFNY / MARJAN/ZULF/ BERRI P&IDs observed. | Lack of alignment for strategy and internal P&ID design review and consistency checking at various stages of the project. Causes:1- Using different templates from FEED contractor for different fields, 2- Lack of strategy from bid stage, 3- Lack of effective leadership and coordination from the award stage. | Conduct multi-centre and multidiscipline design review and consistency checking at host location. Process to provide the leadership for this activity and costs/schedule to be covered in PEP during bid engineering. This activity is required at various stages of the project. Dubai Process. Similar exercise is recommended post HAZOP and before AFC stage.
21 | CHN-ECLL-PR-0021 |  | Process | PR | LTA Guaranteed Scope | Saudi Aramco |  | ECLL |  |  |  | Selection of appropriate material and efforts during bid. | For Neutralization tank, Material of Construction was given as SS316L same as that was given for Neutralization tank in SAF-2 project. During bid and post-award, it was always thought that battery draining liquid were same for both the projects. However, in reality, battery types had changed from alkaline type to acidic type. This was not highlighted when the project began . Later on, it was determined that MOC as SS316l is not suitable. | Differences between previous and working project were not highlighted. But execution strategy was based on experience gained from previous project. | Bid process engineer is required to undertake this task at early stage. Conduct gap analysis.
22 | CHN-ECLL-PR-0022 |  | Process | PR | LTA Guaranteed Scope | Saudi Aramco | Tie-in platform | ECLL |  |  |  | HP/LP interface and inadequate assessment during bid | This was related to lack of understanding of HP/LP interfaces during bid. Flow arm drain connection was originally plugged as per SSS, however it was changed in bid to hard pipe to slopes, creating an HP/LP interface leading to potential over pressurization of the lower rated pipe and slops tank. Due to this issue, the hard pipe line to slope was removed turning the system back to original SSS design. The HP/LP check now included in Process Bid checklist and additionally added to P&ID checklist in our Process Engineering procedures. During review of the individual flow arms depressurization and drainage for maintenance, it was identified that there was potential for over pressurization of the Closed Drains header and Slops Tank. For Marjan the operating pressure is approximately 800 psig while the Closed drains system is 150# class with a design pressure of 250 psig and the Slops Tank has a design pressure of 2.5 psig. | System design had not been previously reviewed to ensure that the HP/LP interface could not cause over pressurization. | A set of PFDs should be marked up to show all the design pressure and piping class breaks, PSVs, HIPS systems etc. to assist assessment. If possible, closed drain systems should be run to the downstream vessel (Slops Tank / Drain Drum) at the same design pressure as the production piping. The vessel inlet nozzle should match the drain line piping class. Slops Tanks / Drains drums which have closed drain systems discharging to it should be designed for a minimum upper design pressure of 50 psig (This actually matches the Saudi Aramco requirement for Closed Drains Drums in Section 6.2.5 of SAES-A-401).
23 | CHN-ECLL-PR-0023 |  | Process | PR | D6875 ¦ Header 9 & 3CRPO | Saudi Aramco |  | ECLL |  |  |  | HIPPS set-point requirement & Flow assurance study work | It was found that requirement of arriving HIPS set point was not identified and led to additional work with vendor and additional cost as well. This requirement shall be identified based on the output of the Flow Assurance Study | During design review, the basis of the HIPS set point was raised by client, and it was not considered during Flow assurance work. | Check BID documents and see if HIPs study is by MDR or provided by client. Establish that the HIPS set points are provided by study provided by the Client, otherwise include in the Flow Assurance SOW.
24 | CHN-ECLL-PR-0024 |  | Process | PR | D6875 ¦ Header 9 & 3CRPO | Saudi Aramco |  | ECLL |  |  |  | Mismatch of Nozzles between P&IDs and GADs | This was about misalignment between Process/Mechanical/Layout. During the copy strategy between LTA II GS & Header #9 projects, the nozzles arrangement of the Slops Tank were copied from LTAII GS without checking the arrangement as per Header #9 P&IDs. P&ID rework resulted as there were inconsistencies between nozzle designations on P&IDs and GA drawings. LL here was that a standardized nozzle designation will help avoid rework, and maintain consistency. | Mismatching between the GAD and P&IDs for the Slops Tank nozzle arrangement | Lead Engineer shall emphasize on both mechanical and layout to follow the P&IDs and review the nozzle arrangement as the P&IDs. Also cerate a standard Nozzle designation to minimize errors.
25 | CHN-ECLL-PR-0025 |  | Process | PR | D7072 ¦ MRJN PKG-4 | Saudi Aramco | Tie-in platform | ECLL |  |  |  | Timely PO Placement for FLOW ASSURANCE subcontract work. | The Work order for Flow assurance study was placed very late in the project. The delay was due to Selection of FA study sub-contractor (SCHLUMBERGER vs. WOOD). After placement of work order the actual runs and results were further delayed due to the following; 1. Considerable amount of were COMPANY comments on Basis of Study 2. Requirement of additional sensitivity cases, which were not identified or studied during FEED stage. 3. A workshop was carried out with COMPANY to freeze the Case matrix for the study. This resulted in the delayed availability of the FA results; impacting the procurement of Choke valves etc. | This a recurring problem. The problem is FA work is subcontracted and the PO placement is always late due to vendor selection/SCM and this means late delivery of results form such studies and knock-on effect on P&IDs and other process and piping stress deliverables. Way forward on this requires management input to change the approach to ensure timely PO placement as per the schedule or even if done internally (e.g. by Houston) there should be a clear plan to work to and resource (people and tools) availability confirmation in advance of assigning work to them. | Flow Assurance subcontract placement shall be done on High priority and no. of cases discussed with COMPANY at the very early stage
26 | CHN-ECLL-PR-0026 |  | Process | PR | D7072 ¦ MRJN PKG-4 | Saudi Aramco |  | ECLL |  |  |  | Proper communication & follow-up | Marjan Package-4 execution is being performed from Chennai, KSA and Dubai. As per scope split common activities and deliverables e.g. Design Basis, Philosophies, HYSYS simulation are Chennai Centre's responsibility. As the COMPANY SAPMT is stationed in Dubai Office and overall responsibility is from Dubai Office, a level of control / involvement of Dubai Office is necessary for the common deliverables and activities | Issuance of deliverables without involvement / signature of Super Lead caused rework and subsequent delays. Split of scope and responsibility for MOPEX projects need to defined based on the centre which will Liaise with the COMPANY | Common Deliverables such as Design Basis, Philosophies, HYSYS simulation /report shall be performed by the same centre where COMPANY representative are stationed.
27 | CHN-ECLL-PR-0027 |  | Process | PR | D6847 ¦ Hasbah | Saudi Aramco |  | ECLL |  |  |  | Non-receipt of P&ID's Native File ( MicroStation & SPPID) from Company | During execution, SPPIDs were not received at the outset of the Project. In order to proceed with engineering, it was decided to develop the P&IDs’ in MicroStation, and later need to be converted into SPPID. However, Bid strategy was in contrast to it. Bid strategy was based on preparation of P&IDs in SPPID. | Estimated hours during bid did not cover for work to be carried out twice – one time in MicroStation and the another time in SPPID. | - Prior to execution of project, resource requirements & project execution risks must be communicated to Engineering management so that adequate resources or pre-award work strategy can be adopted. - Bid strategy to be revised to adopt practicable approach for engineering execution. Add suitable PROM mitigations with suitable cost allocation against it to ensure that risk is covered and appropriate cost has been allocated against it.
28 | CHN-ECLL-PR-0028 |  | Process | PR | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | No Material Selection Study during BID | Not engaging Material Specialist during bid engineering and also during early engineering stages created lot of changes and confusion. |  | Material Selection study and engaging Material Specialist should be done during Bid stage and continue during early stages of project execution
29 | CHN-ECLL-PR-0029 |  | Process | PR | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Material Selection and Process Design / Scheme Selection for DHDS | DHDS Metallurgy and Scheme Selection : discussions took place after the design was mature |  | Major design changes / Material selection should be done early during Engineering. Any change at a later stage should only be based on specific change order request from client
30 | CHN-ECLL-PR-0030 |  | Process | PR | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Vessels and Packages optimization | Optimization like vessel sizes, splitting packages in to multiple skids - not pursued during bid |  | Philosophy for each package - splitting into multiple skids, optimization initiatives to be done during Bid Stage Bid execution strategy should be made mandatory for all bids and this needs to be defined in that strategy document. In addition, the basis of bid given to client should also document the optimizations done.
31 | CHN-ECLL-PR-0031 |  | Process | PR | D7202 ¦ NFE FEED | Qatar Gas |  | ECLL |  |  |  | P&ID Review workshop | P&ID review workshop is very important workshop to be conducted prior to HAZOP. However, a P&ID Review workshop was not conducted during FEED. This led to numerous comments during HAZOP and it was a painful task to close all HAZOP recommendations. | Formal P&ID Review was not conducted prior to HAZOP. | It is highly recommended to conduct a P&ID Review prior to HAZOP during FEED.
32 | CHN-ECLL-PR-0032 |  | Process | PR | D7244 ¦ Belbazem FEED | Al Yasat Petroleum |  | ECLL |  |  |  | Number of HE shells, calculations and its impact on engineering design / 3D model | Thermal design of Heat Exchangers was expected to be carried out by FEED CONTRACTOR. The information (number of shells, dia) was provided in Equipment list. However, the information was not marked up in the related P&IDs. Since details were not available in P&IDs, Piping discipline did not capture the change in its design and model. Hence, correct numbers of shells required for heat exchangers were not modelled, and was considered as a major miss-out as far as equipment are concerned. (For examples, there were 4-6 numbers of shells were required, where as only 2 shells were considered in to 3D model) It was noticed during the model review and this led to rework for piping. This also affected BOQs and MTOs of all disciplines including piping, I&C, Civil etc.. | Correct numbers of shells were not shown on P&IDs and layouts did not capture correct numbers of shells in 3D model. | Inter discipline flow of information particularly from upstream disciplines to downstream discipline need to be clearly planned, documented and tracked. Numbers of exchanger shells and diameter should be either clearly marked up in P&IDs or kept on HOLD on P&ID thru a note until confirmation is received from Mechanical/Vendor. HTRI calculations to be performed and correct numbers of heat exchangers to be considered in the process drawings to avoid such issues in future.

## Loss Prevention
Serial No | LL Number | Date | Discipline | DC | Project Name | Client | Facility category | LL category | Subject1 | Subject2 | Subject3 | Title | Background | Root cause | Corrective action | Preparer | Preparer Desn | Reviewer | Reviewer Desgn | Approver | Approver Desgn
1 | CHN-ECLL-LP-0001 |  | Loss Prevention | LP | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Safety studies for the project | The Risk Assessment report has been revised more than ten times due to various reasons such as poor quality, incompleteness & projection of incorrect references. |  | Contract safety studies to proven safety study contractors with past working experience with MDR. Atleast three vendors to be considered for TBE.
2 | CHN-ECLL-LP-0002 |  | Loss Prevention | LP | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Fire Water Demand and Pump Sizing | Confirmation regarding fire water pumps sizing due to lack of understanding on FW demand calculation requirements. |  | The firewater pump selection during the bid stage was based on the pumps offered in a simultaneous bid and no basis was developed during bid stage. Trying to meet the firewater demand to the pump selected during bid led to considerable delay in finalizing the firewater demand calculations and pumps. Firewater demand calculations to be done during bid stage based on which the pumps should be selected.
3 | CHN-ECLL-LP-0003 |  | Loss Prevention | LP | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Automatic Gas flooding system for the buildings | Initially, a common gas flooding system has been considered for all the buildings to optimize the design. However, Pemex insists for individual cylinder bank for each building which needs more space. TQ's raised by discipline was never sent to Client for acceptance. |  | Any design optimization beyond the contractual requirements needs to have client buy-in.
4 | CHN-ECLL-LP-0004 |  | Loss Prevention | LP | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Procurement of Safety Eqpt | Involvement of many coordinators result in delay in decision making, communication failure & improper vendor offer & more set of TQ's. |  | For all technical queries, Safety dept alone to communicate with vendor. Necessary discussions to be initiated amongst Engineering functions to update the global norms.
5 | CHN-ECLL-LP-0005 |  | Loss Prevention | LP | D6071 ¦ QP Bul Hanine | Qatar Petroleum |  | ECLL |  |  |  | Safety related deliverables linked with other disciplines. | In BH EPIC project, considerable amount of time and efforts were spent to define the responsibilities between disciplines especially on drafting, CRS and issue to DC for safety deliverables linked with other disciplines - viz., Safety layouts (Escape route, Safety equipment, Safety Sign & PFP Zone layout, Fire & Gas Layout and F&G C&E) | No design cost centre for Safety, lack of consistency followed in previous projects and difference in COMPANY cost centre & MDR cost centre | Safety related drawings under other discipline cost centre - viz., Safety layouts (Escape route, Safety equipment, Safety Sign & PFP Zone layout, Fire & Gas Layout and F&G C&E) ownership to be determined and agreed between respective discipline, safety and PMT at start of EPIC projects/MDR finalization. It includes, drafting, inputs, review and issue to CPY. This is regardless of any agreement reached during bid stage.
6 | CHN-ECLL-LP-0006 |  | Loss Prevention | LP | D6071 ¦ QP Bul Hanine | Qatar Petroleum |  | ECLL |  |  |  | Safety equipment/ F&G modelling | In BH EPIC project, Safety discipline review of individual WHT 3D model for all safety equipment, safety signs and F&G devices was not accounted. One WHT review was only done, considering similar WHT design. Later on incomplete and incorrect modelling resulted in non-reviewed WHTs, which caused additional time and efforts for Safety to review all other WHTs, which was not accounted for. Disciplines, who owns the 3D model, don’t take responsibility and largely depend on safety discipline for modelling safety & F&G equipment. | Similar WHT/platform approach (Synergy), | During EPIC bid stage, Safety discipline should consider 3D model review of all safety equipment and safety signs modelled by piping and I&C. E.g. Safety, lifesaving and firefighting equipment modelling by Piping and F&G devices by I&C. Other disciplines don’t take responsibility and largely depend on safety discipline for correct modelling.
7 | CHN-ECLL-LP-0007 |  | Loss Prevention | LP | D6071 ¦ QP Bul Hanine | Qatar Petroleum |  | ECLL |  |  |  | Safety Sign Vendor | In BH EPIC, Safety Sign Vendor selection was primarily based on budget and the selected Vendor sublets the activity to a Sub vendor, who was not a professional safety sign vendor. This results a lot more of additional efforts in Vendor coordination, Vendor documentation review and approval. Even materials submitted to site prior to final approval of drawings and the materials were not correct as per the drawings. | Least importance to Safety Signs in most of EPIC projects | Proper technical review to be performed in Vendor selection process and Safety should be involved in Vendor selection process. Both, Vendor and Sub Vendor (if any) shall be technically professional.
8 | CHN-ECLL-LP-0008 |  | Loss Prevention | LP | D6071 ¦ QP Bul Hanine | Qatar Petroleum |  | ECLL |  |  |  | Process Inputs to Flare/Vent Dispersion | In BH PhIB EPIC, due to process inputs on Vent Dispersion received multiple times, resulted in additional efforts in Vendor Coordination and resulted in Variation Order (VO) to Third party Consultant for Vent Dispersion study update. | Process inputs changed due to COMPANY comments | In all PreFEED/FEED and EPC projects, 1. Process should provide a firm inputs on preagreed timeline along with COMPANY (Process) concurrence. 2. PHAST based Flare and Vent study shall be performed in house, to avoid any potential Variation Order to third party consultants.
9 | CHN-ECLL-LP-0009 |  | Loss Prevention | LP | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | Incorporation of Human factors Engineering requirements into 3D model | COMPANY (QG) has stringent Human Factors Engineering requirements that will not be easy to take exceptions. The requirements were not considered right from the start of the project and had to be addressed mid-way in to engineering design. This resulted in adjusting the valve and handle elevations, provision of temporary access platforms, reviewing the access paths to handle the access platforms movement, relocation of handrails, some local re-routing of lines etc. | Lack of awareness by all disciplines of the specification requirements during model development | 1. At the start of the project, technical safety engineer to take ownership of disseminating the HFE requirements 2. Process to mark-up valve categories in consultation with COMPANY Operations as a red-line on the IFA P&IDs. 3. PEM and PE to ensure that an internal meeting is held in order that requirements are correctly disseminated and agreements with COMPANY are documented. 4. Layout/Model Coordinator to capture HFE requirements as part of the 30% model review pre-requisite. 3D model procedure to be reviewed and updated by the function. 5. Mechanical, E&I to include the specification for packages (as applicable) in the MR and vendor acceptance as part of TBE. 6. 60% model review to be utilized as a final check against the requirements.
10 | CHN-ECLL-LP-0010 |  | Loss Prevention | LP | D7202 ¦ NFE FEED | Qatar Gas |  | ECLL |  |  |  | Design of DIFFS by the Helideck design vendor | At the early stage of the project, McDermott Loss Prevention discipline, Structural discipline and PMT team (in consultation with procurement team) decided to include DIFFS package in the scope of Helideck vendor package due to following reasons. - There are common suppliers, who can supply DIFFS and Helideck - Less interfaces - Optimized packaging can lead to cost reduction | - Not applicable. | For future projects, Helideck and DIFFS package may be clubbed as a single package (depending upon commercial considerations) as there are common suppliers and interface can be reduced significantly.
11 | CHN-ECLL-LP-0011 |  | Loss Prevention | LP | D7202 ¦ NFE FEED | Qatar Gas |  | ECLL |  |  |  | Use of Safe / Passive Helidecks in place of standard (non-porous decks) | Safe / Passive Helidecks are considered to provide higher level of fire protection against Heli fuel fires due fuel spills on the Helideck compared with standard steel & non- porous decks. Typically this is achieved by draining fuel through holes in the deck surface, into cavities filled with aluminium mesh in the design of passive helidecks. This starves the fire of oxygen and dissipates heat, extinguishing the flames and draining away unburnt fuel for collection. Safe / Passive helidecks are cheaper than standard helidecks and they will eliminate the requirement of foam tank in Helideck DIFFS as they use water in place of foam. Combination of Safe / Passive Helideck and water DIFFS has following advantages: Higher fire protection, Less capital cost, Less helideck weight due to elimination of foam tank, Less OPEX cost as no regular foam replacement is required and less operator checks & maintenance activities as there is foam tank. | It was decided to use Safe / Passive helideck for NFQ WHP based on technical assessment performed on helideck design. | It is recommended to use Safe / Passive Helidecks in future offshore projects as well as they are inherently safe with respect to design and helps in reducing CAPEX and OPEX as well.
12 | CHN-ECLL-LP-0012 |  | Loss Prevention | LP | D7369 ¦ NASR 100 MBD | ADNOC |  | ECLL |  |  |  | PHA Pro License (Software) | In NASR 100 MBD PreFEED, PHA workshop was awarded to freelancer Individual chairman and PHSER workshop was chaired by MDR safety HOD. Both cases PHA Pro license was not available, neither with freelancer nor with MDR. Additional efforts took to get waiver from COMPANY to perform PHA using Excel. | No PHA Pro License with MDR Dubai | MDR Safety or Process Discipline could explore feasibility of possessing PHA Pro license in-house. This is in contest of awarding Safety workshops to individual freelancer chairmen and performing safety workshops using in-house resources.
13 | CHN-ECLL-LP-0013 |  | Loss Prevention | LP | D7369 ¦ NASR 100 MBD | ADNOC |  | ECLL |  |  |  | PHAST based Dispersion Study | In NASR 100 MBD project, during an update of an existing flare study software file, which was done in older PHAST v7.2 with some PHAST defaults changed. Update was performed using latest PHAST v8.1 using PHAST defaults, unpredictable and unexpected results were generated. Hence as per DNV support advise, certain PHAST defaults were changed to non defaults to match with existing v7.2 inputs and to make the results reasonably similar to existing dispersion results. | Update of existing PHAST native file received 'as is' from COMPANY, in which PHAST default parameters were changed. Lack of understanding on software version modelling updates/ bugs and results behaviour. | PHAST based Flare Dispersion Study on a typical Brownfield projects – only use PHAST software defaults in all parameters used when the scope is to update the study made in older version of PHAST (For e.g. V.7.2) with a latest version of PHAST file (For e.g. V.8.1), regardless to any non-default parameters already in place on existing PHAST model.
14 | CHN-ECLL-LP-0014 |  | Loss Prevention | LP | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | F&G system FAT | Many site issues faced during yard pre-com of F&G system as the devices did not work properly; site changes done in trial and error to address the issues. This happened as the team did not take sample F&G devices during System FAT, which is a requirement |  | Include this as a procedure so that no F&G system FAT ever happens without taking sample devices of each type
15 | CHN-ECLL-LP-0015 |  | Loss Prevention | LP | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Growth in Brownfield F&G detectors | During our FEED study for the new platform, we had considered the existing F&G system in KJO platforms as in working condition and hence we did not augment the same. During post-CO execution at 60% DR stage, Client commented that the existing are not working well and we need to provide extra devices to ensure coverage. |  | In case of brownfield scope, it is recommended to raise clarification to Company upfront regarding functionality of the existing F&G systems. Should not bank on existing F&G systems without concurrence from Company.
16 | CHN-ECLL-LP-0016 |  | Loss Prevention | LP | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | NOVEC 1230 over FM-200 for building fire suppression system | Since building fire suppression made applicable to this projects, MACL proposed initially FM 200 as fixed fire suppression system within the building. KJO has requested for NOVEC 1230 and hence, NOVEC system has been studied in detail. considering following advantages of NOVEC 1230 system the same has been finalized over FM-200. 1. Due to the low concentration levels of Novec1230 fire suppression, means that less Novec cylinders and less space is required, making the storage footprint for the fire suppression agent very small. 2. Novec 1230 offers significant atmospheric advantages over it synthetic rivals. 3. Novec1230 is considered as a green gas and posses no threat to both the Ozone Layer and offers Novec does not fall into global warming gases. 4. Novec 1230 fluid has zero ozone depletion potential and the lowest atmospheric lifetime for halocarbon alternatives: 5. Novec 1230 has an atmospheric lifetime of only 5 days 6.Novec 1230 fluid has the greatest margin of safety for use in occupied spaces Consequences: FM 200 Fixed fire suppression system has main disadvantage over NOVEC system- 1. Though its clean agent the atmospheric lifetime is longer (in years), 2. The system works on higher pressures than NOVEC and has complex high pressure maintenance methods |  | Novec and FM-200 are equally effective when it comes to extinguishing fires, but considering mentioned advantages, NOVEC 1230 systems to be advised for all future projects where fixed fire suppression system is applicable.
17 | CHN-ECLL-LP-0017 |  | Loss Prevention | LP | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | SA 'UL1709" fire rating test issue and Alternative IMO-EN tests for fire rating of Material | As per SAES-B-009 section 4.6.1 “On platforms handling hydrocarbons, buildings shall be of noncombustible material and shall have two-hour fire-rated walls, per UL 1709 or ASTM E119, with steel exterior.” two hours fire rating complying with UL1709 is not available in the industry with the insulation manufacturers. Hence, the external walls, floor and roof of KRG building on main deck, the H120 two-hour hydrocarbon fire-rated insulation tested as per IMO 754 (18) hydrocarbon curve equivalent to EN 1363-2 guidelines have been used. Considering this UL rating related limitation, MACL compared the fire test temperature v/s time curve for UL1709 and IMO 754 (18)_ EN 1363-2 hydrocarbon curve. As per UL1709, the temperature of 1093 deg C is achieved within first 5 minutes, where, EN1363-2 achieved the 1000 deg C temperature after 7.5 minutes and after first 15 minutes temperature is constant at 1093 deg C up to 60,120 minutes. Consequence: 1. Insulation Material Approval issues may be raised from KJO. |  | Since EN1363-2 HC curve is close to UL-1709 test time-temperature curve, it is recommended to follow EN1363-2 HC curve for projects where UL-1709 fire insulation rating test requirement is applicable in future. 2. Management of Change should be raised to get projects approval on this alternate way.
18 | CHN-ECLL-LP-0018 |  | Loss Prevention | LP | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Credit criteria for Existing F&G instrument for brownfield scope | As per Safety studies recommendations, new F&G detection system had to be added only if existing F&G coverage is unavailable. KJO were completely reluctant to provide any information on existing F&G status. When MDR came up with the coverage of existing F&G system, KJO asked MDR for taking guarantee of existing F&G with respect to lifespan and other existing technical issues. Hence, finally it has been decided to go ahead with new F&G system for brownfield. Consequence: 1. F&G detection and Alarm devices count increased. 2. follwed by Instrument configuration system adequacy checks. 3. Increased instrument hardware such as cabling, panels, Cable trays, power cables etc. 4.Spending of more engineering manhours on F&G systems 5. Increased overall F&G instrument cost towards project |  | For brownfied activities involvement, credit note and usage strategy for existing F&G instrument has to be clarified at the start of the project via formal letter to Company.
19 | CHN-ECLL-LP-0019 |  | Loss Prevention | LP | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Understanding on Third Party Safety Study Conssultant Capabilities | 1. Some times, understanding on technical issues by third party safety consultant is not in line with the requirement 2. Improper recommendations on reports without understanding on implications 3. Third party safety consultant is not keen to the project requirements and scope change. 4. Chairman candidates from Third party safety consultant were not having grip over the workshop sessions Consequence: 1.Extended technical review cycle (third party issues several revisions) which is ultimately delaying schedule and investing more engineering man-hours 2. Reports with scope understanding related issues |  | Third party safety consultants and their sub-contractors performance capabilities to be checked with the help of technical interview session with key personnel at the start of the project
20 | CHN-ECLL-LP-0020 |  | Loss Prevention | LP | D7068 ¦ MRJN PKG 1 | Saudi Aramco |  | ECLL |  |  |  | Document Submittal to COMPANY for review and its Comments resolution | At the moment in PK1 several documents been submitted to SAPMC by email and this created many un-official comments which cannot be traced and closed properly since there is no formal CRS and records. | Company Instruction/ Projects - Company - discipline communication | Submitting documents for review to SAPMC should be done only through formal project transmittals ( i.e. IDocs) and not by email.
21 | CHN-ECLL-LP-0021 |  | Loss Prevention | LP | D7369 ¦ NASR 100 MBD | ADNOC |  | ECLL |  |  |  | In-house studies in place of third party studies | Many third party studies, which are performed conventionally by third parties due to ADNOC requirements, were performed in-house due to schedule criticality CV of in-house resources were found acceptable to ADNOC for NASR 100 MBD FEED. This approach helped in adhering to schedule and helped in reducing project cost. Few examples are below. Should be mentioned in the basis of BID so that it can get approved by COMPANY prior to award. - PHSER workshop - Flare dispersion analysis - Sector Analysis workshop | - Schedule criticality - Availability of in-house skilled man-power - Acceptance from ADNOC | - During Bid, propose maximum numbers of in-house studies by giving reference of project like NASR 100 MBD Pre-FEED and other projects where work has been performed in-house. This can help in reducing cost, and in turn will help to pose a competitive bid. - This helps to see McDermott as an established CONTRACTOR for Pre-FEED / Conceptual studies. It is highly recommended to follow this approach for future projects.
22 | CHN-ECLL-LP-0022 |  | Loss Prevention | LP | A6224 ¦ KJO Hout | Al Khafji Joint Operations | [5 empty] | Inadequate understanding of Building underdeck insulation / Material handling | In the building underdeck location, beam clamps were considered in design for material handling and there was a lack of communication within engineering (Safety and Mechanical) as this location was supposed to be fully insulated by Building subcon for fire protection. This led to late stage surprise as there is no means of handling major valves located beneath this location. Also, what led to this was that the insulation was not modeled in the PDMS and hence it was not clear to all discipline members. |  | Improve awareness in this aspect for multidiscipline team; Cover this in checklist, Include 3d modeling of the insulation as a must in future projects

## Mechanical
Serial No | LL Number | Date | Discipline | DC | Project Name | Client | Facility category | LL category | Subject1 | Subject2 | Subject3 | Title | Background | Root cause | Corrective action | Preparer | Preparer Desn | Reviewer | Reviewer Desgn | Approver | Approver Desgn
1 | CHN-ECLL-ME-0001 |  | Mechanical | ME | D5773 ¦ ONGC | ONGC |  | ECLL |  |  |  | Damange Component and painting | Jib crane received with poor paint quality. Lot of manhours / paint spent on touch-ups Pedestal cranes received with mechanical damages (2 out of 4 cranes) and with missing components and defective beacon lights, etc. |  | More thorough checks recommended at FAT for specialized items and proper packaging for transportation.
2 | CHN-ECLL-ME-0002 |  | Mechanical | ME | D5773 ¦ ONGC | ONGC |  | ECLL |  |  |  | Certifying Agency Approval | The role of certifying agency and the extent of its review on engineering documents was confirmed after 3-4 months after commencement of engineering. This led to delays in final approval of engineering deliverables and also difficulty in tracking / managing the approval of these documents in the document management system |  | Insist upon ONGC to appoint the TPI and CA as early in the project as possible, and define it as a project milestone. Based on the D5773 experience, a set of guidelines to be framed for use in future ONGC projects.
3 | CHN-ECLL-ME-0003 |  | Mechanical | ME | D5773 ¦ ONGC | ONGC |  | ECLL |  |  |  | Pad for consumables | Vendor supplied bulk consumables like bolt , gasket should also have construction pad. |  | This needs to be considered at the time of placement of the order.
4 | CHN-ECLL-ME-0004 |  | Mechanical | ME | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | No mechanism to address Vendor deviations | Qualification of vendor deviation points with PEMEX prior to the purchase order. No opportunity was given to the engineering team to discuss with client engineers on these open points and come to an agreeable path forward. |  | Communication should be established between Engineers and Clients to discuss and agree upon these deviation points. Barricading engineers from communicating with clients directly doesn't help in resolving technical issues. Client specifications always mandate the best of the features which are available from different vendors and it is not practical always to meet all the requirements mandated in the specifications.
5 | CHN-ECLL-ME-0005 |  | Mechanical | ME | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Offshore installed items | Installation philosphy for the offshore installed items to be finalized with commissioning team. In the absence of commissioning team well until 80% engineering completion, many of the decisions had to be taken by engineering in the absence of commissioning team. |  | All critical functional leads for the project to be identified early on in the job and continuity to be ensured in case leads quit the job.
6 | CHN-ECLL-ME-0006 |  | Mechanical | ME | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Quality of PR attachments | Engineering docs attached with PR shall be of AFD quality without any hold points. |  | The risks of placing PR's when the design is not complete needs to be informed to management and appropriate mitigations to be identified updated in monthly PROM updates.
7 | CHN-ECLL-ME-0007 |  | Mechanical | ME | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Potable water package - delays from vendor | Potable water package should have been split & ordered with multiple vendors. As inter skid details was not mentioned in the PDS. |  | The skidding philosophies for such complex packages need to be discussed and agreed keeping in mind a. Constructability issues, Schedule Constraints b. Vendor availability and reliability c. Cost benefits Involve SME's during bid stage/ Basic Engineering stage to arrive at an informed decision.
8 | CHN-ECLL-ME-0008 |  | Mechanical | ME | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Review of painting specifications. | QC team in AFY did not have resources to review paint specifications from vendor packages and provide path forward on paint related issues, which led to delay in finalization of painting system & RAL color code. |  | QC team in AFY to be strengthened with resources having knowledge of paint systems.
9 | CHN-ECLL-ME-0009 |  | Mechanical | ME | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Allowable nozzle loads | Nozzle loads relaxation for utilities packages up to 6" of pipe size |  | Separate criteria for process based packages and utility packages for determining allowable loads to be developed.
10 | CHN-ECLL-ME-0010 |  | Mechanical | ME | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | PSV stamping requirements for Pemex | UV stamping requirements for the PSV to be finalized before PO. |  | For all Pemex projects consider this as a default requirement for PSV's and price accordingly.
11 | CHN-ECLL-ME-0011 |  | Mechanical | ME | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | SCOPE Clarity in Packages for Engineering, Procurement, Fabrication Installation | System approach for various packages – Lack of clarity on scope for engineering, procurement, fabrication, lifting and installation |  | In the absence of a global procedure for package management, R.A.C.I chart for Packages to be finalized early in the Project.
12 | CHN-ECLL-ME-0012 |  | Mechanical | ME | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Vendor document- SDRL | Mexican Vendors don't have understanding of SDRL requirements and Vendor document approval cycle requirements. |  | More clarity to be given to Vendors during Kick - off Meeting (KOM) and SDRL shall have minimum document requirement.
13 | CHN-ECLL-ME-0013 |  | Mechanical | ME | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | Warehouse spare pump Bid miss | There was a requirement of a common Warehouse spare pump for Drain sump pumps in ADMA 6221 project. During the bidding, this spare pump was not considered for pricing and later the requirement was identified during detailed engineering. | Warehouse spare pump was not identified in the MTO list as a separate line item | a. The requirement of warehouse spares/ Capital Spares shall be identified during bidding stage and shall be listed in the MTO for pricing purpose as a base scope. b. Notes on Process datasheet, P&ID and Equipment sparing philosophy shall be reviewed by Mechanical Engineer during bidding stage to avoid such bid misses.
14 | CHN-ECLL-ME-0014 |  | Mechanical | ME | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | Incorrect pricing reference for Category C and Category D items. | During the bidding stage, incorrect reference of other project was provided for Nitrogen bottle racks where the storage pressure and number of cylinders were not matching with the requirement of the Project. | Incorrect reference and Incorrect TAF was provided | If the proper reference is not available for a given equipment, Inquiry shall be floated rather than applying TAF on incorrect references.
15 | CHN-ECLL-ME-0015 |  | Mechanical | ME | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | Jib crane accident | Accidental failure of Jib Crane at ZK-158 during SAT at McDermott yard. The brakes of the crane failed with and 5.5 tonnes load on crane dropped on the laydown area of the platform. This resulted in: a) Failure of SAT b) Dropped object risk during testing c) Possibility of fatal accident | This was due to incorrect machining of the motor shaft for retention of the circlip which resulted in disengagement of the motor shaft pinion from the drum gear and in turn allowing the drum to rotate freely (i.e., free fall of the load). It was found later that Stahl had made a new development in the shaft design which led to this failure and all the cranes that were supplied were called back. | a) Complete FAT of Cranes shall be carried out at vendor works prior to shipment. b) Prototype design shall not be offered for cranes. Only proven designs shall be accepted.
16 | CHN-ECLL-ME-0016 |  | Mechanical | ME | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | String test requirement for GTG | During bidding, engineering team issued technical clarification regarding to include string test in to GTG's vendor offer. Vendor confirmed to meet this requirement. String test was specifically mentioned in the specification, and vendor confirmation was obtained during bid. TBE issued to SCM also included the requirement of string test. However, SCM did not include String test for GTG in to pricing. This was considered as bid miss during execution. | - SCM missed pricing of String test. - Engineering TBE highlighted the string test requirement. However, big cost items like string test must be discussed during cost review. - Insufficient cost reviews among functions. - GTG package was a Single source vendor, and no strategy was in place during bid to keep price escalation from vendor in check. - No specific PROM Inputs from SCM or Engineering on price escalation from single source vendor. | -For future bids, Engineering must arrange TOP 20 Package wise discussion with SCM and Estimation to review pricing basis for each package. BEM should take lead and arrange such sessions with Lead engineer, Estimation, Proposal, Bid manager and SCM team. - Engineering must not provide technical adjustment factors for big ticket cost items like string test. Care must be taken while dealing with such packages as engineering may not be qualified to suggest commercial implications for big ticket items. - Recommended that proper strategy must be in place to deal with possible price escalation GTG package during execution. - Specific PROM Inputs from SCM or Engineering on price escalation from single source vendor must be provided and discussed.
17 | CHN-ECLL-ME-0017 |  | Mechanical | ME | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | Costing of HVAC and Building scope | During bidding, there were 3 vendor offers were received by engineering. Technical clarifications were issued to vendors, however, final vendor response were not received from vendors. Engineering issued recommendation through email that pricing of SIEMENS to be considered based on status of vendor offers received during bid. However, SCM did pricing based on other vendors, and this led to price increase around 2.5 M - 3 M US$ during execution. | - Engineering recommendation was ignored by SCM. - During cost review, this package was not discussed in detail. - No PROM Inputs were considered to address the risk associated with this package by SCM. | -For future bids, Engineering must arrange TOP 20 Package wise discussion with SCM and Estimation to review pricing basis for each package. BEM should take lead and arrange such sessions with Lead engineer, Estimation, Proposal, Bid manager and SCM team. - Engineering must highlight the deviation from practice during cost reviews that TBE could not be issued due to non-availability of compliant vendor offers so that P&E and Bid manager can apply suitable risk mitigation strategy. - Specific PROM Inputs from SCM or Engineering on price escalation from single source vendor must be provided and discussed.
18 | CHN-ECLL-ME-0018 |  | Mechanical | ME | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | Costing of Fuel Gas Treatment package | During bidding, vendor offers were received, and TBE was issued to SCM. However, at last offer from another vendor BESTWIDE was received. Engineering did not include this vendor in bidding, however, it was stated to BESTWIDE needs to be further investigated in case to be included in technical evaluation. However, SCM did pricing based on BESTWIDE vendor offer, without performing proper technical evaluation. BESTWIDE was also not available in AVL as well. This was the major reason for cost escalation during bid. Moreover, one of the vessel metallurgy was changed to alloy 625 clad, which also led to price escalation. | - Pricing based on non-AVL vendor by SCM. - Pricing without TBE from engineering by SCM. - No specific PROM strategy to deal with this risk. - Change in metallurgy in one of the vessel internals. | -For future bids, Pricing must be considered based on AVL vendor and must be in compliance to Engineering TBEs. BEM to discuss this aspect with SCM during cost reviews. - Specific PROM inputs must be discussed in case pricing is considered based on non-AVL vendors. - Maintain the records of engineering recommendations for future references. - Review of vendor offers by Material's team as required during Bid.
19 | CHN-ECLL-ME-0019 |  | Mechanical | ME | D7233 ¦ Umm Shaif | ADNOC |  | ECLL |  |  |  | Thrust Bearing RTD - Client LL for failure in USGIF | Lack of thrust bearings' RTDs caused thrust bearing assembly failure and pump were to be sent for refurbishment. | Client lesson learnt | Thrust bearing's RTDs and Vibration accelerometer to be provided for vertical turbine pumps rated for more than 160 kw for all ADNOC-Offshore projects.
20 | CHN-ECLL-ME-0020 |  | Mechanical | ME | D7233 ¦ Umm Shaif | ADNOC |  | ECLL |  |  |  | Vessel internals vendor engagement | Vessel MRs were only sent to vessel fabricators and resulted in partial bids with respect to internals. Following clarifications, the vessel fabricators were required to update their offer based on their chosen internals supplier which resulted in the overall bids being difficult to evaluate "like-for-like" as the impacts on the plant layout would need to be evaluated. Further, certain internals suppliers stated that the specified process guarantee could not be offered with the specified internals. | Lack of strategy for sizing of pressure vessels | During FEED or EPC Bid, the Vessel MRs should be sent to internals suppliers also in order to guarantee that we receive confirmation of vessels sizes and prices for internals. This will also allow for optimisation of the vessel dimensions and better preparation for EPC phase. Engage with internals vendors early in the design phase (i.e. first rev of the datasheets) in order to: - validate the process design - normalise the vessel dimensions - select vessel dimensions that will benefit our layout and be cost effective.
21 | CHN-ECLL-ME-0021 |  | Mechanical | ME | D7244 ¦ Belbazem FEED | Al Yasat Petroleum |  | ECLL |  |  |  | Incomplete Process Parameters | In various packages for this FEED, there has been changes in the Equipment model selection / Material of Construction due to incomplete Process inputs / late changes in the Process inputs. | Multiple reasons like miss outs as well as late client inputs | Timely and correct Process inputs are very critical for successful evaluation of vendor offers.
22 | CHN-ECLL-ME-0022 |  | Mechanical | ME | A7697 ¦ Angelin | British Petroleum |  | ECLL |  |  |  | Incorrect information in MR | In few cases, noted that incorrect specifications were attached, few documents attached correctly however revision number mentioned was incorrect. | Proper checking not implemented. | Project specific checklist needs to be prepared and included the required information to be verified prior to issue of MR In case any key documents attachments/ new revisions missing, shall be informed bidder at TBC stage itself and confirm with Bidder/vendor. MR/PR checklist shall be used for all revisions
23 | CHN-ECLL-ME-0023 |  | Mechanical | ME | D5763 ¦ Karan offshore | Saudi Aramco |  | ECLL |  |  |  | Vendor scope split for Packaged items | a. KARAN: Other packages: Vendor scope splits were clearly defined for the components to be procured by MDR within the skid (e.g. free issue of cladded flanges, valves, H2S/LEL Detectors, Telecom items, etc. that vendor could not procure from the approved vendors) and the items to be loose supplied by vendor outside the skid limit (e.g. PZV outside the skid limit). b. General: Interconnecting piping between multiple Vendor supplied package skids (e.g., Compressor skid and Lube oil skid for Centrifugal compressors) were kept in MDR scope of supply. | These are positive lessons learnt as it was followed for Marjan Increment Package 1 | Scope shall be clearly defined in the RFQ, specification and P&IDs. Separate line items in the MR shall be there for loose supplied items and skids so that there are no miss outs. The scope of interconnecting piping and associated instruments shall be clearly defined for major packages. It is recommended that interconnecting piping are excluded from Vendor scope to have more flexibility for Layout finalization. Both recommendations shall be implemented at bidding stage RFQ as well.
24 | CHN-ECLL-ME-0024 |  | Mechanical | ME | D6255 ¦ LTA II | Saudi Aramco |  | ECLL |  |  |  | Saddle design & fabrication for pressure vessels. | Saddles of the various tanks in LTA II project faced buckling. | Saddles of the tank were directly welded to structural support. So due to welding heat affected zone was created, combined with thermal expansion which led to buckling of the saddles. | a. PIP standards / COMPANY standards shall be followed for saddle design. Minimum saddle thickness shall be specified in datasheet. This point shall be added in vessel checklist. b. Alternatively, saddles shall be anchor bolted with the structural support of the platform. Sizing and selection of anchor bolts shall be reviewed by Structural team as a part of VDR.
25 | CHN-ECLL-ME-0025 |  | Mechanical | ME | D7068 ¦ MRJN PKG 1 | Saudi Aramco |  | ECLL |  |  |  | Location of Panels / loose supplied E&I auxiliaries | In this FEED, there are various major packages with complex control systems required. Location of these panels (example Machine Monitoring system, Performance controllers, Turbine control panel, etc. ) are very critical for hazardous area certification and eventually has an impact on the pricing. Location of all the panels for all the packages were clearly discussed with Electrical and Instrumentation teams and defined at an early stage including supply scope and spec. | This is a positive Lessons learnt. | Scope of supply and Location of E&I panels shall be specified part of RFQ at bidding stage. This will facilitate proper pricing.
26 | CHN-ECLL-ME-0026 |  | Mechanical | ME | D6255 ¦ LTA II | Saudi Aramco |  | ECLL |  |  |  | Non-sparking wheels and Hooks | Material of construction for wheels and hook for Electrical monorail hoist was not Non-sparking. This was identified during an inspection. | It was not communicated to Vendor in TQ stage / RFQ. | Material of construction of wheels & hook shall be non sparking type. Base material shall be specified in the specification and approved by COMPANY during the bidding stage. This requirement shall be captured suitably in the specification / RFQ / TQs to Vendor.
27 | CHN-ECLL-ME-0027 |  | Mechanical | ME | D6255 ¦ LTA II | Saudi Aramco |  | ECLL |  |  |  | Fusible plugs / H2S detectors | a. Fusible plugs located around the pump skid obstructed the access to the skid components. B. H2S / LEL detectors were not placed with the required work-around space at scraper door location. | Fusible plugs and H2S detectors were not modelled at early stage and access to the skid was not checked while modelling the same. | Fusible plugs / detectors are normally installed in front of pump / scraper door & routing of these items may obstruct the access. Hence they shall be modelled at initial stage. Fusible plugs outside the skid limit shall be located such that they wont obstruct access to skid components. To be addressed during internal model reviews.
28 | CHN-ECLL-ME-0028 |  | Mechanical | ME | D6255 ¦ LTA II | Saudi Aramco |  | ECLL |  |  |  | Slop tank nozzle - Level switch/overflow settings | Nozzle locations for Level gauges on Slops nozzles were not matching level settings of the Transmitters / Level gauges. | Nozzle locations for Slops Tank was firmed up with vendors without confirming the level settings - merely following the go-by of SAF-2. Process had not generated level sketches to finalize the locations of nozzles | Process needs to internally generate a document to record the calculations required for level settings and provide the nozzle location / elevation confirmation only upon producing that document and not rely on go-by information.
29 | CHN-ECLL-ME-0029 |  | Mechanical | ME | D6255 ¦ LTA II | Saudi Aramco |  | ECLL |  |  |  | Design Pressure/ MOC for instrument as per piping class | In the CI package, the Instrumentation was selected for the PSV set pressure instead of Piping class design pressure. | It was with the incorrect assumption that the line pressure will never exceed PSV set pressure as the PSV will pop up above that pressure | a. All instruments and pulsation dampener shall be selected at least for the piping class rating and benefit of PSV set pressure shall not be taken. TQs shall be raised to Vendors to get confirmation on this. b. MOC of instruments shall be minimum matching the MOC of valve trim of the root valve.
30 | CHN-ECLL-ME-0030 |  | Mechanical | ME | D6463 ¦ SAF 5 | Saudi Aramco |  | ECLL |  |  |  | Scraper Tool Handling Frame / Cradle | During Offshore Walkthroughs and SAT completions, COMPANY representative kept asking questions as to how the tool will be inserted inside the QOC / scrapper door and that the provided Monorail or Davit will not serve this purpose. COMPANY representative asked for a cradle for safe operation instead of referring to the Scope of Work or Bid Q/As. | Based on Bid Q/As, Scraper Tool Handling Frames or Cradles for the Scraper Launchers were not required to be provided in SAF 5 / SAF 6 Projects. | Cradle shall be considered for each size of scraper launcher / receiver on the platform and shall be provided with in-built winch mechanism, it is required for inserting the tool inside the QOC (in case of Launcher) and retrieving the tool out of the QOC (in case of Receiver).
31 | CHN-ECLL-ME-0031 |  | Mechanical | ME | D6847 ¦ Hasbah | Saudi Aramco |  | ECLL |  |  |  | Scraper Traps design code for #10000 rating | During FEED / bidding stage, Scraper Trap #10000 rated has been specified to be designed as per API 31.8 Code and ASME Section VIII Div. 1 was specified for Quick Opening Closure. It is to be noted here that no pipe class is available for this high pressure rating and Scraper Traps for 10000 # rating are made from Forging. For Quick Opening Closure also, ASME Sec. VIII Div. 1 cannot be used as it has a limitation upto 3000# rating. Hence ASME Sec. VIII Div. 2 shall be suitable for such high pressure rated scraper traps. This change in the design code was observed only during detailed engineering and pricing during the bidding stage was not done taking this into account. | a) During the bidding stage, MTO reference was provided and no MR was raised for scraper trap. b) Datasheet was not revised during the FEED stage to capture this change. c) It was observed that COMPANY standards are also suitable only upto 3000# rating. This issue should have been highlighted to COMPANY during the FEED / Bidding stage. However, the same was not highlighted. | a) Applicable codes shall be correctly decided during the Bidding / FEED stage. If the project requirement falls outside the range / scope of COMPANY standards, clarity shall be sought from COMPANY. b) For any non-standard item, pricing shall be based on Vendor offers and not on the references with TAFs.
32 | CHN-ECLL-ME-0032 |  | Mechanical | ME | D7072 ¦ MRJN PKG-4 | Saudi Aramco |  | ECLL |  |  |  | Pulsation Dampener for Flare KO drum & Ware house pump for Washdown pump | a) During the bidding stage MR for Flare KO pumps, type of Pulsation dampener required was not explicitly mentioned to Vendors. Only a P&ID note mentioned that Bladderless pulsation resonator was required.. Three offers were reviewed; viz. Peroni Pompe, RAM pumps and Technip FMC during the bidding stage. Both Peroni Pompe (who had considered Bladderless pulsation resonator) and RAM pumps (who had considered bladder type pulsation dampener) were considered Technically acceptable but there was a huge price difference between the two. Eventually the L1 offer (RAM pumps) price was considered for bidding. b) For Washdown Pump P&ID (NAG TP, CGP TP and CGI TP) - One Spare Pump shall be kept in onshore store. However, the same was missed during the bidding stage | - a and b: P&ID notes were confirmed by bidder but detailed TQ was not asked bidding stage. - a: Huge price difference between the two vendors was not investigated as a potential miss out in the scope by one of the bidders. | - P&IDs notes shall be reviewed in detail during the bidding stage. - If there is additional requirement in the P&IDs, the same shall be carried to the Equipment list and MTO as a note, so that it doesn't get missed out. - If there is a huge cost difference between pricing of two vendors, Procurement shall raise this to concerned engineer to check if L1 vendor has missed out something. Bidders shall provide cost breakdown for sub-vendor items.
33 | CHN-ECLL-ME-0033 |  | Mechanical | ME | D6875 ¦ Header 9 & 3CRPO | Saudi Aramco |  | ECLL |  |  |  | Insufficient head room for OFFSHORE assembly and installation of the Seawater submersible pumps for both BRRI 432 and BRRI 700 Facilities | This was a print to build job and the headroom for seawater pumps was as per the 3D-model / Layout drawings provided by FEED contractor. There was insufficient headroom for assembling the submersible seawater pump. | Installation / removal strategy of the pumps was not carried out for these platforms. | Platform design and installation requirements must be checked during Vendor document review. Solitary review of vendor documents shall not be performed.
34 | CHN-ECLL-ME-0034 |  | Mechanical | ME | D6255 ¦ LTA II | Saudi Aramco |  | ECLL |  |  |  | Slops pump Package and CI package Panel and preservation | A. During the Platform Walkthrough by COMPANY representative, following were observations for Slop pumps: 1. Cable ferruling did not have source and destination terminal number on each end of the cable as per Aramco standard. 2. Proper space for maintenance inside the panel was not there. 3. There was insufficient space below the motor terminal box for terminating power cable. B. Pumps were shipped for Long term preservation without plunger packing installed. | A.1. Wiring drawing was not reviewed properly A.2. Panel GAD was not reviewed in terms of space availability. The size of the panels were selected based on the following design requirements: a) Available accessible space for keeping panel within the skid limits, b) Minimum panel height c) Maximum panel height to keep the panel accessible by standing on the floor requirement to ensure bending radius of connected cables, d) Visibility to the field instrument displays behind the panel. A.3. Motor cable entry was not reviewed with Electrical team. B. Vendor recommendations were avoided for packing damage during shipping. | A.1. Cross ferruling of the cables shall be done inside the panel. To be checked in the Wiring diagram A.2. Even when there are overall space constraints for package installation, operational access shall not be compromised. Investigate the possibility of a bigger panel without impact on the skid size (& costs) during review of Panel GAD. A.3. Sufficient space shall be ensured below motor terminal box for cable termination in the GAD C. If the pump is to be shipped without Hydraulic packing, the same shall be informed to Production team for manhours estimation.
35 | CHN-ECLL-ME-0035 |  | Mechanical | ME | D6255 ¦ LTA II | Saudi Aramco |  | ECLL |  |  |  | ATEX certification | Our findings on Phase 2 due to the latest Saudi Aramco Desktop Standards is that ATEX certification is not acceptable. This will directly impact pricing of equipment, available vendors and their qualifications/certifications for this project as well as those in future. We have had this issue on Overhead Crane and JIB Crane packages especially and we have managed to mitigate this to the best extent and ensure that items supplied are not ATEX certified, during TQ/TBE stage. | This is a positive Lessons learnt. | The requirement of certification by IECEx CB as per the SAES-P-100 for Electrical equipment located in Hazardous area shall be communicated to VENDOR for Saudi Aramco Projects as ATEX certification is not acceptable. For other clients too, this requirement shall be assessed at early stage and confirmation shall be sought from vendors during TQ/ TBE stage.
36 | CHN-ECLL-ME-0036 |  | Mechanical | ME | D6376 ¦ SAF II | Saudi Aramco |  | ECLL |  |  |  | 3D model of the package | In LTA II project, 3D model was included as a part of Vendor deliverable | This is a positive Lessons learnt. | It is highly recommended that for all packaged items, models are a part of Vendor deliverables. Further, Package model to be compatible with the main model software used by layout team so that integration of package model with the overall plant model is feasible.
37 | CHN-ECLL-ME-0037 |  | Mechanical | ME | D6376 ¦ SAF II | Saudi Aramco |  | ECLL |  |  |  | Jib Crane column construction | MDR QA/QC insist that Jib Crane not be spiral welded by making reference to 12-SAMSS-018. Jib Crane (Colum Mounted), is usually a vendor standard item. In most cases vendors perform spiral welding to construct the column. This is fine as long as it is clearly stated by vendor before order placement and clarified during TQ/TBE stages. As per experience in SFNY P2, one of the specifications for fixed offshore platform columns (12-SAMSS-018) mention that spiral welding is not allowed only longitudinal seam welding or seamless is allowed. However these spec does not pertain to package equipment and is also then based on client interpretations which can be difficult to convince. It is best defined clearly in the beginning and agreed by all parties for the type selected. Any deviations should be made in writing and approved formally. | 12-SAMSS-018 was included as a part of RFQ. Deviation to the requirement of Long seam welding was not taken by Vendor. | Only the applicable COMPANY standards / specs shall be listed and included in RFQ. 12-SAMSS-018 and its corresponding IR forms shall not be listed in crane package specification as it is not applicable. Consider 12-SAMSS-007 and IR forms for crane structure
38 | CHN-ECLL-ME-0038 |  | Mechanical | ME | D7072 ¦ MRJN PKG-4 | Saudi Aramco |  | ECLL |  |  |  | Scraper Traps Lengths | Scraper Trap lengths mentioned in the FEED datasheet were not matching with that in the Saudi Aramco Library Drawing for same sizes. During the Bidding however, the scraper lengths as per FEED datasheet were considered. It should have been clarified with Saudi Aramco during bid stage to avoid issues during EPCI. | Scraper lengths were not checked with respect to Saudi Aramco Library drawings | Type of Scraper tools to be used and scraper trap lengths (if non-standard) shall be checked with COMPANY during bidding.
39 | CHN-ECLL-ME-0039 |  | Mechanical | ME | D6875 ¦ Header 9 & 3CRPO | Saudi Aramco |  | ECLL |  |  |  | Crane accident | McDermott chartered Jack-up Barge QMS Achiever from Zakher Marine International was jacked up in position at the Berri 76/81 WHP located in the Berri Oil Field, Offshore King Fahd Industrial Port, Jubail, Kingdom of Saudi Arabia. On Oct 20, 2019 morning, crane operations were being conducted using the starboard crane across the WHP upper deck. After successful completion of five lifts the crane operator halted lifting to check an alarm in the cabin. The crane operator left the cabin to investigate the cause of this particular alarm. Upon his return to the cabin he attempted to hoist up the boom, at which time the boom descended to the platform deck. | The immediate cause was identified as an insufficient quantity of rope on the right-hand luffing winch which, led to the rope being pulled from its termination clamps and allowing uncontrolled descent of the boom. Later however, the following was the conclusion: - Alarms and inhibits from the crane’s HMI were not adequately understood by operators, leading to habitual misuse of the “Stow Mode” by the crane operators. Base on investigation findings its evident that use of “Stow Mode” had become a routine practice during lifting operations. - This particular manufacturer’s logic controls of “Stow Mode” did not make the crane “Fail Safe”. It was possible to generate conditions from the operator’s cabin, without second party involvement, which would inhibit the “stow mode” safety limits. - The “Stow Mode” is supposed to be used only when the crane is to be parked on the Boom Rest after operations are complete. The habitual mis-use of the “stow- mode” described above caused the boom hoist rope to migrate between the winch drums, eventually resulting in a condition where the right-hand luffing winch had no rope left on it, which ultimately led to the incident. | Although the crane accident was related to Jack-up barge and not related to the project cranes, following is the take-away point from the incident. To avoid such kind of incidents, following specific paragraph shall be added in the crane specifications for ongoing (where possible) / future project. This would help ensure the requirement is not missed while performing offer evaluation: "The Pedestal Crane shall be provided with the following safety mechanisms as a minimum, in addition to the safety mechanisms as per API 2C latest Edition: Stow Mode Angle Limiters or similar : Vendor to provide stow mode angle limiters to ensure that the activation of the crane “Stow Mode” is possible only at the pre-determined boom-rest/s position angle. Activation of the crane “Stow Mode” shall not be possible in the normal operating slew zones of the crane & shall only be possible when it is on the boom-rest/s position. Boom angle sensor and luffing winch encoder or similar to be supplied along with HMI panel (located in crane cabin) which shows the quantity of wire rope available on the winches. Vendor to ensure that at least 5 turns of wire rope shall always be available on the winch drums and under no condition should the pay-out of these safety layers should happen during normal crane operation. Wire-spooling mode or similar shall be the only dedicated mode which allows bypass of the absolute wire rope low limit (5 turns on winch drum). To prevent un-intentional use of this mode, it shall be “password-protected” or similar. The use of this mode shall only be possible when the crane is in its final parked position on the boom rest. "

## Piping layout
Serial No | LL Number | Date | Discipline | DC | Project Name | Client | Facility category | LL category | Subject1 | Subject2 | Subject3 | Title | Background | Root cause | Corrective action | Preparer | Preparer Desn | Reviewer | Reviewer Desgn | Approver | Approver Desgn
1 | CHN-ECLL-PL-0001 |  | Piping & Layout | PL | D5773 ¦ ONGC | ONGC |  | ECLL |  |  | Fabrication requirements | Discripency between structural and piping isometrics | Mis-match of dimensions between riser isometric drawings (issued by SURF) & structural drawings Riser clamps bolts floro-ploymer coated as per drawing but galvanized (above splash zone) as per MTO. |  | Better interaction between engineering disciplines (pipeline, piping and structural) to avoid conflicting dimensions / details.
2 | CHN-ECLL-PL-0002 |  | Piping & Layout | PL | D5773 ¦ ONGC | ONGC |  | ECLL |  |  |  | Hydrotesting for small bore lines | 1/2 “ piping connected to F.E could not be hydro-tested. |  | Tubing to be considered for sizes less than ¾“. If above option is not possible, then the design should be in such a way that carrying out hydrotest should be possible.
3 | CHN-ECLL-PL-0003 |  | Piping & Layout | PL | D5773 ¦ ONGC | ONGC |  | ECLL |  |  | Piping Stress Analysis | Pipe Stress man hours | It has been noticed that in quite a few jobs done recently, the consumption of man hours for pipe stress has been more than estimated during the bid. In D5773, 790 man hours were estimated during the bid stage, we have spent 1685 hours actual on this CTR (PIP-283). We have raised a DTCMS to record this fact in this project. |  | The norms for estimation of pipe stress manhours need to be looked during bid stage.
4 | CHN-ECLL-PL-0004 |  | Piping & Layout | PL | D5773 ¦ ONGC | ONGC |  | ECLL |  |  | Fabrication requirements | Weldolet selection and design - to minimize welding effort in fabrication | Weldolets normally considered as bulk items, were procured by specifying the wall thickness at the down size only. The wall thickness of the header side was not specified as the plan (as is normally done) was to use the Olets across a wide section of header sizes. The weldolets on launchers were also procured in a similar fashion. As the wall thicknesses on the header portion were different, the fabrication hours required to weld the olets were considerable and this affected the fabrication productivity, especially on the launchers. |  | When the weldolets are spaced very closely, as in the case of launchers, either Flangeolets (or) weldolets specially designed for the header pipe thickness need to be procured. This needs to be captured during technical evaluation. The costs for the same need to be considered in the bid.
5 | CHN-ECLL-PL-0005 |  | Piping & Layout | PL | D5773 ¦ ONGC | ONGC |  | ECLL |  |  |  | Clashes or close promiity on site | Insulation thickness / flanges not accounted for in some case, leading to proximity issues (very few though) Insulation kit missed out between dissimilar flanges in a few areas. Also, bolts were short in these areas. Space for thermowell element installation not considered at a few locations on B192-1 deck |  | Insulation thickness space and Thermowell installation needs to be considered and checked during Engineering development.
6 | CHN-ECLL-PL-0006 |  | Piping & Layout | PL | D5773 ¦ ONGC | ONGC |  | ECLL |  |  |  | Support Guide gap | Shoe support guides gap of 0-3mm was specified in the drawings. In some of the previous projects, specific gap values were mentioned, which were difficult to maintain. |  | Include range wherever possible instead of specific values.
7 | CHN-ECLL-PL-0007 |  | Piping & Layout | PL | D5773 ¦ ONGC | ONGC |  | ECLL |  |  |  | Change in execution philosophy done for layouts -- not clearly communicated to PMT / management | As per the engineering execution strategy finalized during bid, only 2 PDMS models (BHE and B192-5) were supposed to be made as the base models and the remaining 3 (WO-24, B192-1 and B192-8) were supposed to be extracted out of the B192-5 model only after 60% model reviews. This strategy was not in line with the schedule requirements. Moreover, this conclusion was taken without completely studying the differences between the layouts. However, during detail engineering these differences were noticed and work had to proceed in parallel on all the 5 models. This affected the productivity of the layout discipline and an additional 5000 manhours had to be spent. |  | The bid strategy for 3D modelling needs to be finalized after throroughly studying and identifying the similarities / differences between platforms and the project schedule. Any change to the execution strategy agreed upon during bid stage needs to be informed to the engineering & project management as soon as possible, and not wait till the deterioration in productivity is noticed.
8 | CHN-ECLL-PL-0008 |  | Piping & Layout | PL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Too many MTO topups for Valves. | Non-availability of experienced "Valve buyers" to source valve vendor offers and close the open points on TBE's was a major issue on this project. In spite of daily monitoring of the procurement status and PO updates, not enough progress was being made and eventually, we had to prioritize the placement of valve PO's. Engineering started giving MTO updates in stages after the PO's were released, as providing any additional information to inexperienced buyers was further delaying the procurement process. Eventually, we landed up in too many MTO topups for Valves in some cases. |  | Buyers experienced in sourcing valves need to be part of procurement team. For enquiry purpose Engineering need to list all possible valve sizes in the MTO for getting upfront pricing from the vendors. Lead Engineer to use judgement and discuss with process about potential changes (without waiting for formal revisions of P&ID's) and obtain optional quotes for them in the initial RFQ's to help procurement.
9 | CHN-ECLL-PL-0009 |  | Piping & Layout | PL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Frequent changes to layout and bad productivity. | Too many chages to the piping layouts because of 1. Not enough clarity on Skid / Package design concept during the initial stages. 2. Late identification about the requirement of pipe rack arrangement for pipe supports 3. Pipe routing in the 3D model just for the sake of issuing MTO's |  | 1. Clarity to be provided to layout teams about the skids/ package design concept and the scope of vendor packages to the designers by package engineers and PEM. 2. Early initiation of discussions with structural / piping / E&I teams to identify any pipe rack requirements on such large scale decks and involvement of 3D model coordinators for this task. 3. Insist that pipe routing studies to be done for developing the design, not just for the sake of issuing MTO's.
10 | CHN-ECLL-PL-0010 |  | Piping & Layout | PL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Scope clarity on vendor packages to design team | Effective Vendor Data Review on Packaged equipments including layout arrangment, Safety and access space, material handling and Constructability requirements |  | Briefing on package to be given to the review team prior to the initiation of reviews. Coreworx should be used for IDC reviews. All comments on the vendor drawings to be vetted by the respective lead prior to passing it to package manager. If issues are not getting resolved, elevate the issues to respective discipline managers for their involvement and resolution.
11 | CHN-ECLL-PL-0011 |  | Piping & Layout | PL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Space reservation in 3D model for piping/E&I | Piping and Trays corridors and space reservation to be done at early stage. This shall cover N-S & E-W common elevations, common corridors with integrated supports etc. Even though the corridors were identified and space reservations done, too much of change on the relief system/drain system routing and size changes during the course of the project (because of Pemex not accepting to the HIPPS system and drain tie-in location changes on packages) made the space reservations defunct. |  | Rigorous checks to ensure the reserved corridors are followed and updates of corridors if changes prohibit usage of corridors. Model coordinator shall be made effective and empowered to enforce the utilization of corridors.
12 | CHN-ECLL-PL-0012 |  | Piping & Layout | PL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | 100% RT requirement | The requirement of 100% radiography for certain specifications was identified very late after the isometrics have been issued AFC, based on client comments. |  | QA / QC engineer need to be involved from the beginning to get the project NDT requirement on time while floating the enquiries.
13 | CHN-ECLL-PL-0013 |  | Piping & Layout | PL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Weld Proximity, radiography requirements. | Deviations to NRFs - weld proximity, NDT / radiography requirements were raised by QC after the design freeze. |  | Such issues to be regularized by raising a TQ and getting client concurrence during early stages.
14 | CHN-ECLL-PL-0014 |  | Piping & Layout | PL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Delays in valve procurement and knock on effects on engineering/ PDMS modelling. | Because of delays in valve procurement efforts and multiple top-ups, Valves having same description/size/ datasheet references were placed with different vendors to obtain better delivery times. This created problems for layout designers/PDMS administrators as any change in valve dimensions between different vendors were not able to be captured in the 3D model. |  | Mutliple vendors for a same type of valve having same size and datasheet references should be avoided, instead valve PO's to be split based on description/type/size and datasheet combinations.
15 | CHN-ECLL-PL-0015 |  | Piping & Layout | PL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Optimization of Special Supports | Budget, manpower and workflow planning for Special pipe support validation by Support designers, Stress engineers and Structural designers |  | Pipe support standard to be tailor made for project requirements and validated once by structural. Work instruction on handling multi-discipline supports and minimizing the review times to be issued by Layout/Structural/E&I/Mechanical DM's
16 | CHN-ECLL-PL-0016 |  | Piping & Layout | PL | D6071 ¦ QP Bul Hanine | Qatar Petroleum |  | ECLL |  |  |  | 3D modelling - Design replicate strategy during bid. | During the bid phase, a design optimization on modelling was identified with the copy and paste design strategy of similar platforms to deliver cost effective and reduced duration during engineering execution. Bid strategy adopted : Review, validate and update the 3D model for one typical platform (Master), develop up to 60% and replicate it for second platform to develop from 60% to 90% and further 3D model replicate/copy to the remaining 2 WHJs. Because of proposed design optimization, the engineering schedule and engineering man-hours were found to be reduced. All information regarding this optimization were collated by bid PMT and savings estimate with respect to time and cost was prepared by the estimating team. No man-hours were considered in the base estimate for preparing separate models ‎for 60% Client review. | ‒ Risk of COMPANY requesting separate 3D model for each platform during engineering execution was not identified in PROM. ‒ Optimization along with appropriate risk mitigation measures to respond along with impact on schedule and/or cost were not presented to the area management during the bid phase. -No evidence of Risk mitigation measures (Risk and Opportunity Action Plan- ROMAPs) prepared for the modelling optimization to reduce the risk even after project award. | Optimization risks identified during bid phase needs to be recorded in PROM along with following mitigation measures particularly for the model optimizations (design duplication strategy) considering the probability of predicting the nonacceptance of design optimization by company upon award.
17 | CHN-ECLL-PL-0017 |  | Piping & Layout | PL | D6071 ¦ QP Bul Hanine | Qatar Petroleum |  | ECLL |  |  |  | Extent of weld overlay on valves | During the bid, weld overlay requirement was mentioned only for valves under two piping classes and the requirement was not specific about the extent of the weld overlay. Part of technical clarification, COMPANY clarified that the weld overlay(minimum to seat pocket and body cavity)is applicable for the all the valves under sour service application even though not specifically mentioned in valve data sheets. | Engineering did not reviewed the technical clarification properly to account for the appropriate cost impact due to the clarification received from COMPANY during the bid time. Engineering did not raised a clarification to clarify the "extent of weld overlay" statement mentioned in the clarification. | Bid clarifications shall be properly reviewed and any impact shall be appropriately accounted in the cost estimate. BEM must ensure that all bid clarifications are closed appropriately. The new bid clarification template which is updated "with actioner/discipline/impacted document/Impact on schedule or cost and the status as closed or Open" has to be strictly followed to avoid such bid misses for any requirements that is added thru clarification and not reflected part of the FEED specification / Datasheets . During the bid, extent of weld overlay has to be clarified if not clear. In general there are three “levels” that are usually covered: - Dynamic seals: seat pockets and stem seals area - Static seals: body-closure or bonnet seals, trunnion to body seals, etc. - And finally the full wetted areas WOL: this needs to be extended all the way thru valve bore up to end-flange gaskets, and including the entire valve cavity.
18 | CHN-ECLL-PL-0018 |  | Piping & Layout | PL | D6167 ¦ RasGas | Qatar Gas |  | ECLL |  |  |  | Brownfield Piping Tie-in’s philosophy | Brownfields piping Tie-in’s philosophy was reviewed from the basic issue of no production shutdowns and maximum availability of the existing system up to the point where the new system is available and tested. Further assessments could have led to more value addition by potentially eliminating another offshore campaign, with the addition of a few valves. | Lack of Brownfield experience in project personnel and deficiency in communication between functions. | Conduct an internal "Tie-in" brainstorming meeting, with representatives from Project, Piping & Layout, Brownfield specialists, Process, Hook-up and Pre-Commissioning. Endeavor should be to develop a best value tie-in philosophy from contractor and client perspective. This should be documented in a philosophy type document during early stage of the project and communicated to all the stakeholders for a mutual agreement.
19 | CHN-ECLL-PL-0019 |  | Piping & Layout | PL | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | Christmas tree growth | Delay & re-work of stress analysis to satisfy client requirement of well head growth study. Eventually considered 50mm only(with some space margin on the top of well head) | There were no information for Christmas tree growth at bid stage/early stage of design and later on, Company advised to consider 50 MM growth. | Basis for Christmas tree growth should be finalized at bid stage/early stage of the project and accordingly design shall proceed.
20 | CHN-ECLL-PL-0020 |  | Piping & Layout | PL | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | Extent of stress analysis | Per ADMA SP-1051, Stress analysis was required to be performed for almost all line including 1" size as well. No much attention was paid during bid to review stress design basis. During execution, COMPANY requested CONTRACTOR to perform stress analysis for almost all lines (including 1" lines as well). These efforts were not estimated during bid. | During the bid, estimation was not done inline with the Stress design basis received part of FEED specification. This aspect was missed during bid. | Review of Client specifications and raise clarifications to Client for confirmation at bid stage and accordingly manhour shall be estimated.
21 | CHN-ECLL-PL-0021 |  | Piping & Layout | PL | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | In accurate Pipe supports quantities estimation | Pipe supports were estimated for project based on line numbers and pipe sizes using high level support span calculations. But during project execution phase, significant increase in pipe support quantities from bid estimate to actual for base scope lines to comply with design growth, installation sequence and brownfields scope requirements. | Due to design growth and brownfield/installation philosophy requirements pipe supports quantities were increased quite significantly. Supporting spans/types of secondary supports were not optimized to meet constructability, early enough in project. | Proper evaluation and finalization of installation sequence of pipe/pipe supports to be finalized in early stages of the project to conclude/efficiently estimate pipe supports. Knowledge share of installation/construction sequence for brownfield scope needs to be finalized in early stage of the project. Accordingly dedicated Pipe Supports design team to be set up early in project to minimize impacts at deliverable extraction stage.
22 | CHN-ECLL-PL-0022 |  | Piping & Layout | PL | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | Weldolets and Nippoflanges dimensions mismatch in 3D model catalogues | Standard/default welded branch details for weldolets and nippoflanges were used in 3Dmodel as go by. The same details were used to produce piping design isometrics and subsequently same has been used in spool isometrics and later on production team identified mismatches in yard while installing pipe spools. | Vendors provided drawings for weldoelts and nippoflanges were not passed on to 3D systems admin to correct the default catalogue items | Standard Catalogue items shall be verified with the project specific vendor drawings and feedback to be given to 3D systems group to correct the standard default dimensions available in catalogue.
23 | CHN-ECLL-PL-0023 |  | Piping & Layout | PL | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | Multiple vendor for the same Valve category | Different Valve Vendors per Valve package | Multiple valve vendors result in multiple dimensions ( of valve accessories), because of top-up, for same type, size, rating, etc. valves placed on different vendors. | Multiple vendor per package shall be avoided. I n the event unavoidable, separate catalogue in 3D had to be created and reselected. Identification of valves from separate vendor shall be addressed. Separate Catalogue specific to vendor shall be created in model and accordingly selected, provide identification in isometrics as required
24 | CHN-ECLL-PL-0024 |  | Piping & Layout | PL | D7244 ¦ Belbazem FEED | Al Yasat Petroleum |  | ECLL |  |  |  | Use of MCML template in place of Valve data sheets. | During a standard FEED project, the production of individual valve datasheets is required for inclusion within the EPC ITT Package. This is man-hour intensive activity with many hundreds of datasheets to be prepared in medium to large projects. Hence, it was proposed to prepare MCML (in excel file) in place of datasheet , still meeting the technical requirements (MCML includes all datasheet fields but in excel template, which can be easily followed by vendors), with SCM and COMPANY representatives. COMPANY representatives agreed for MCML template in place of Datasheet, Which not only reduced a lot of man-hour spending at CONTRACTOR's end but also resulted in vendor friendly database, which can be easily followed by all vendors. If accepted by SCM and COMPANY, MCML approach can be proven as cost efficient, schedule efficient and vendor friendly approach. | EPC Bidders require specific details to provide accurate cost estimates for valves from vendors. Handling of multiple datasheets and multiple files is a tedious work for vendors. This requires more time by vendors to prepare bids. MCML approach can help in quick preparation of vendor offers and reduction in overall Technical clarification cycles with vendors. | Consider the preparation of an overall MCML (Main Component Material List) in a spreadsheet format. Key details to be provided will include design, construction, materials, inspection/testing and painting/coating. This is adequate information to be sent to vendors for inquiry and costing. Before following MCML approach, COMPANY approval is required to be sought to avoid any re-work.
25 | CHN-ECLL-PL-0025 |  | Piping & Layout | PL | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | X-Mas tree details required for detailed design | Issue: Proceeding with the design without the availability of X-Mas tree design, will result in incomplete design or re-work at offshore. As examples, the connection points to the X-Mas tree and the stabbing guide height (if topsides are installed post tree installation) will be affected if the details are unknown. If this occurs at an advanced stage, late fabrication changes and offshore re-work will occur. In addition, orientation of the X-Mas tree connections can only be ascertained once they are installed. In the case of D7333, the X-Mas tree design provided by COMPANY changed from Y type to T-type. This occurred due to miscommunication within the client. In I1P1, the jacket stabbing guide elevation had to be adjusted to be above the X-Mas tree with a clearance of 500mm, this was caught at the right time in a constructability review. | Client inputs not available or incomplete at the time of execution. | 1. As a first step, at the start of the project, pursue with the client to obtain detailed dimensional information of the X-Mas tree via a TQ. 2. If the above information is not available, allow for the design of the three-dimensional closing spool. 3. Make allowances in fixing the height of the stabbing guide, with some allowance to accommodate change to tree height. Alternately, liaise with COMPANY to strip down appropriate parts to facilitate safe topsides installation. 4. Review the need for a local laser survey prior to actual work at offshore to pre-fabricate the spool.
26 | CHN-ECLL-PL-0026 |  | Piping & Layout | PL | P6068 ¦ NFPS I1P2 Bid | Qatar Gas |  | ECLL |  |  |  | Estimation was not able to price the valve MTO due to mismatch in the description between MR and MTOs issued by engineering | During Bid, as a standard practice, Piping team prepares Valve MTOs in the line wise valve MTO template developed with standardized parameters required for the valve detailed description and then the compiled MTO’s will be used in MR’s to have consistent description, so that SCM and Estimation team can co-relate prices received for the MR’s issued to vendors with final valve MTO. For NFPS I1P2 bid, Valve MTO was prepared using conventional McDermott procedure using the valve MTO template, However, during MR preparation different valve description were followed instead of using the consolidated MTO from line wise valve MTO. This led to mismatch in valve description between valve MTO and MR. | Lack of awareness while preparing of valve MRs & McDermott procedure was not followed. - Lack of oversight / review from Piping team | - Piping Lead engineer shall review the MTO and MR’s to ensure compliance to standard work practices / procedure prior issuance to SCM/Estimation that the standard practice is followed.
27 | CHN-ECLL-PL-0027 |  | Piping & Layout | PL | A7697 ¦ Angelin | British Petroleum |  | ECLL |  |  |  | Layout requirement | Failure to pass layout requirement and changes by vendor post approval. Though on many occasion Layout requirement was passed to vendor as part bid evaluation , there were misses. We experienced changes particular in DBB valves , instrument panel handle orientation etc which resulted in late rework. A review shows following causes | Lack of vendor’s commitment in keeping confirmation made during bid evaluation Delayed submission of key information as part of bid and post order Vendor documents Lack of engineer passing the requirement as part of RFQ/Bid evaluation Lack of focused review by engineer /designer – and late comments (2nd revision) resulted in difficult and almost on all occasion we had “cut our shoe to suit to the foot” | A focused effort is required to pass on key/preferred orientation of equipment and component as part of RFQ. Bid evaluation Have critical information obtained from bidder and include them in bid evaluation Have critical information submitted on time by vendor Pass on layout comments on a single pass to vendor and follow it up with a discussion to ensure our requirement are met
28 | CHN-ECLL-PL-0028 |  | Piping & Layout | PL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | BF Laser Model | Laser model shall be validated with site survey by all disciplines. Although this was performed, the team still found some late stage surprises during execution. |  | Include this as a procedure so that no F&G system FAT ever happens without taking sample devices of each type
29 | CHN-ECLL-PL-0029 |  | Piping & Layout | PL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | BF scope rigging details modelling | Model has to be updated with the Rigging details such as (Bumpers, guides, C-Clamps locations, chain block for the transfer of the major items), hence will avoid any clashes or any other surprises during installation, resulting in more offshore time |  | CSE to model the rigging details in the 3 D Model during the details design deliverables stage
30 | CHN-ECLL-PL-0030 |  | Piping & Layout | PL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Piping Proximity issues | Close proximity (less than 50mm) between pipe/tray and structure identified at late stage of the project at certain locations. These are violating certain Aramco standards, although we interpret these standards as "onshore specific" |  | 1.) 3D model coordinator (if available) or Lead Layout designer needs to ensure proper checking was done and conduct as many as required internal model reviews to address close proximity issues. 2.) Area lead designers of respective disciplines shall be made responsible for 3D Model quality. 3.) Separate Round Table Discussion shall be conducted prior to the issuance of penetration drawings to avoid close proximity issues.
31 | CHN-ECLL-PL-0031 |  | Piping & Layout | PL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Compliance to L5 schedule (yard matrix/fabrication deliverables issuance) | In spite so many issues, delay in support standard finalization, addition/deletion of some lines and ~12% increase in support counts, the issuance of fabrication deliverables were almost on target at all the time in both design isometrics and pipe support details drawings i.e. the weekly targets were achieved |  | This model shall be implemented in all the projects i.e. realistic weekly target based on fabrication schedule, progress status of design, team size based on work fronts and DM's regular review with the team on look ahead plans. DMs to continuously educate or increase the awareness to all the resources about various levels of schedules, look ahead plans, importance of meeting yard requirements etc.
32 | CHN-ECLL-PL-0032 |  | Piping & Layout | PL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Project Handover / Take over process | Numerous issues were faced when the project was restarted after a gap of nearly 4 years. There was no proper close-out documentation when the project was mothballed. The team was forced to make assumptions and proceed with work in order to maintain the project schedule and budget but resulted in lot of rework/redesign, increase in man-hours and poor productivity etc. few notable issues are, 1.) 3D model was not updated as per the latest revision of P&IDs 2.) 3D model was not updated as per latest vendor data/drawing for equipment and inline piping and instrumentation items even for the items received at site during phase-1. 3.) Mismatch between 3D Model extracted MTO and the MTO used for procurement. 4.) Non-compliance to ARAMCO desktop standards. |  | Procedure to be developed for handover and takeover process. This procedure shall address the documentation and records keeping requirement particularly when a project is mothballed for an indefinite period. Also the team takeover the from another office as continuation from either a live or mothballed project condition, shall check the following (as a minimum) prior to the start of any activity. 1.) Status of the design and verify the progress of 3D model against the latest revision of P&IDs, specifications and datasheets. 2.) Status of requisition engineering activities including vendor data status, compare with 3D model catalogue updation status. 3.) Compliance to Client specifications and desktop standards as applicable 4.) Status of any data and or drawings extracted out of 3D model such as, MTO, equipment layouts, Isometrics etc.
33 | CHN-ECLL-PL-0033 |  | Piping & Layout | PL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Pump Skid Drain | As per scope of work and P&ID, KOD Pump skids which are welded to the Deck structure, has drain connections which needs to be routed to a bunded area or a drip pan. Drains from the bunded area will be collected through a tundish which has an in-built liquid seal and routed to the nearest drain header. During the design of this arrangement following issues are faced. 1.) The drain nozzle elevation was too close to the deck elevation and part of the flange was clashing with the deck structure. Hence it was not possible to route the line further with minimum fittings. 2.) There was no possibility to revise the nozzle elevation through VDR, since the skid was already purchased and received at site during phase-1. 3.) The skid beam height was also not sufficient enough to make any local modification and revise the nozzle elevation. 4.) The option of elevating the total skid was ruled out due to the NPSH requirements with the tank. 5.) The option of elevating both Tank and pump skid was ruled out because of the deck to deck elevation difference available between cellar deck and main deck. |  | 1.) Drainage philosophy of the Project (bund and liquid seal requirements etc.) needs to be thoroughly discussed and agreed between all stake holders at early stage (prior to 30% model review) of the project. 2.) Skid height shall be finalized as early as possible or at the early stage of the project. 3.) A round table discussion shall be conducted to discuss all the design, constructability and operability related issues such as, NPSH requirements, drain line routing feasibility up to header, deck elevations, close proximity and construction difficulties etc. before finalizing the skid height.
34 | CHN-ECLL-PL-0034 |  | Piping & Layout | PL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Bolt length | Inadequate stud bolt length. 'For few cases the bolt length was not coming correctly and was updated manually until the bolt table was fixed by PDMS admin in due course |  | PDMS Bolt length to be verified and fixed before ISO issuance, any conflict from Bolt table to be finalized with PDMS admin
35 | CHN-ECLL-PL-0035 |  | Piping & Layout | PL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Finalization of Project Pipe Support Standard | Design and extraction of pipe support detail drawings delayed because the issuance of project specific pipe support standard delayed expecting the release of Global Pipe Support Standard. Also there was insufficient time frame to develop catalogues in MDS which resulted the design and 3D modeling of supports. |  | Pipe Support design and modeling strategy shall be finalized prior to 30% model review and project specific support standard (if required) shall be issued within 4-6 weeks from the completion of 30% model review date. Also Catalogue Creation in MDS shall be completed well in advance to 60% model review since the fabrication deliverables issuance starts around this time.
36 | CHN-ECLL-PL-0036 |  | Piping & Layout | PL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Flange Material Selection | A694 F60 was initially selected as flange material and this was rejected by KJO as as A694 F60 is not available in Table I of 01-SAMMS-11. |  | It is recommeded to use A707 material when grade F60 is used
37 | CHN-ECLL-PL-0037 |  | Piping & Layout | PL | D5763 ¦ Karan offshore | Saudi Aramco |  | ECLL |  |  |  | Pipe supports in Boat landing level. | Boat landing installation volumes were not clearly captured in 3D model for TP-18 platform, Engineering designed and issued pipe supports in the vicinity of boat landing installation areas which had created hinderance to boat landing during installation campaign in offshore. This resulted in cutting of the affected pipe supports for smooth boat landing installation and re-welding the secondary pipe supports. Engineering re-validations and additional support was needed to Marine team to complete the campaign. | Proper Installation methodology/study was not performed in 3D model and Installation model reviews were not conducted with stakeholders in multiple stages of the project during detail design. | • Identify Marine installation focal point during early stage of the project and maintaining an installation methodology for each offshore installed items. • Installation methodology to be validated during detail design in all stages of project with respective engineering discipline stake holders. • Marine recommendations to be captured in 3D models and required exclusion zones/volumes to be updated in 3D model and ensure strict compliance in maintaining clash free. • Deliverables shall be issued in line with the agreed recommendations from Marine. This will ensure offshore re-work activities during marine campaigns.
38 | CHN-ECLL-PL-0038 |  | Piping & Layout | PL | D5763 ¦ Karan offshore | Saudi Aramco |  | ECLL |  |  |  | Valve design to MAOP | Bid Project valve data sheet for 38" valves specified pressure class as ASME B16.34, 1500# rating (e.g. 3329.4 psig at 120oC for Table 2-1.1 materials) and Maximum Allowable Operating Pressure (MAOP) as 2071 psig. Also these valves were specified with flanged connections. Designing the valve to ASME B16.34,1500# rating for the plant requirement of MAOP of 2071 psig is not a common industry practice, as the difference between the design pressure (3329.4 psig) and MAOP ( 2071 psig) is very large i.e.,1257.4 psig. The large factor of margin will not be utilized in the plant life. This was reviewed for alternative design for reduced rating to meet the requirement of project | By designing the valve to ASME 16.34-class 900 with Group 1.2 material and Hub connectors, 38" Valve weight was reduced by approx. 18 tones. This in turn reduced the crainage to accommodate within selected crane capacity and also the platform weight. | The design pressure of the platform was based on the maximum operating pressure, in such cases the Large bore valve design has to be reviewed to optimize the design based on platform maximum operating pressure(MOP) instead of MAOP design/ fully rated design. This will provide considerable cost and weight saving. To be included in Valve data sheet / Specification check list to review the rating in case of platform design based on MOP to utilize in future project optimization consideration.
39 | CHN-ECLL-PL-0039 |  | Piping & Layout | PL | D5763 ¦ Karan offshore | Saudi Aramco |  | ECLL |  |  |  | Compact DBB / SBB valve design from Conventional | Company had indicated on Bid P&IDs to provide conventional double block and bleed or single block bleed type isolation valves for process drains / vents depending upon application / service. | Compact design of DBB / SBB was evolved. MDR proposed as a post award optimization and it was approved to use compact design double block and bleed or single block bleed type isolation valves | Compact design DBB's or modular types can be proposed as a post award optimization based on historical application on similar configuration of platforms considering optimization on the cost, space and weight benefits. However, during the bid time since there is a significant cost difference between various types(Conventional, IDBB, slimline/monoflange) to avoid any bid miss, the Pricing MTO shall be updated with specific type verified from FEED documents such as PID's, Valve Datasheet, Process isolation philosophy etc.
40 | CHN-ECLL-PL-0040 |  | Piping & Layout | PL | D5763 ¦ Karan offshore | Saudi Aramco |  | ECLL |  |  |  | Weld overlay on flange facing | As per Piping class the flanges were to be weld overlaid till the OD of the raised face for the process services. There was a mismatch observed in the weld overlay configuration on the Choke valve vendor drawing. Weld overlay of choke valve have to be done same configuration of the mating flange in order to avoid galvanic corrosion due to dissimilar material contact. | Vendor did not comply to this requirement instead provided only up to the ring joint, for API 6A type BX flanges. | Extent of weld overlay to be clarified with vendor during the technical evaluation stage and the same has to be verified in the valve GA drawing/ Clad map drawing.
41 | CHN-ECLL-PL-0041 |  | Piping & Layout | PL | D5763 ¦ Karan offshore | Saudi Aramco |  | ECLL |  |  |  | Feed verification of Pipe wall thickness | Bid piping specification developed by FEED contractor specified pipe wall thickness schedule for 1SD0P piping class for size 2" as sch 10. ARAMCO desk top standard SAES-L-105 specifies the minimum schedule for 1SD0P piping class for sizes up to 2" as sch 40. | Conflict of wall thickness within company supplied specifications has not been verified. Although Sch 10S meets the design minimum thickness company requirement of SCH 40 is based on minimum mechanical strength to avoid fatigue due to dropped objects. | The FEED contractor provided PMS part of the ITT documents cannot be used as it is during EPC without verifying compliances against company standard PMS. The FEED verification has to be done with due diligence during bid time itself inline with MDR procedure, if not, to be done at least post award within the conflict verification period .
42 | CHN-ECLL-PL-0042 |  | Piping & Layout | PL | D5763 ¦ Karan offshore | Saudi Aramco |  | ECLL |  |  |  | Valve stem failure -Design parameters for Nozzle Check valves | Orion Nozzle Check Valves (2" Class 150) in the chemical pump discharge lines were found to be chattering continuously leading to failure of the stem/ stem guide. | Root Cause Analysis carried out by the vendor indicated that the springs were not suitable for the flow conditions and hence the valve would not open fully in the normal operating conditions leading to chatter. | The valve data sheet normally specifies only the MAOP (Maximum allowable operating pressure) and minimum & maximum operating temperature. In order to consider the appropriate cost during the bid, sizing & selection of the check valves, flow conditions such as flowrate, viscosity, density of the fluid needs to be communicated to the vendor. Vendor shall submit the Pressure drop vs Flowrate analysis for the selected valves and needs to confirm that the disc will remain in the full open, without any chattering under the normal operating conditions.
43 | CHN-ECLL-PL-0043 |  | Piping & Layout | PL | D6200 ¦ SAF 6 | Saudi Aramco |  | ECLL |  |  |  | Mismatch between issued P&ID’s and issued piping design Isometric drawings | At 2 locations valves marked on P&ID were missed out in issued piping design Isometric drawings. Spectacle blind open/close symbol shown in P&ID but issued Isometric drawings were not aligned. Branch connection details shown in P&ID but Isometric drawings were different in one location in Sfny544 Platform | Piping design team was missed to comply P&ID requirements during isometric checking process | Before releasing the Design isometric drawings, Layout design team needs to ensure whether all requirements shown in latest P&ID’s including lines sequence are captured in design isometric drawings. If there is any mismatch, prior agreement with process to be made and P&ID mark-up to be shared with process for P&ID’s update.
44 | CHN-ECLL-PL-0044 |  | Piping & Layout | PL | D5854 ¦ SAFANIYA | Saudi Aramco |  | ECLL |  |  |  | Incorrect scraper receiver nozzle orientations in 3D model | In TP-18 scraper receiver, 4" Nozzle (2nos) orientation were considered incorrectly in 3D model, subsequently nozzle connected piping design isometrics were issued to production | Vendor supplied scraper receiver drawings were not correctly modelled in 3D model, which in turn caused wrong design isometrics issuance | Nozzles in 3D models to be correctly captured based on final mechanical equipment vendor drawings received and ensure strict compliance of the isometrics before issue to production to avoid any rework.
45 | CHN-ECLL-PL-0045 |  | Piping & Layout | PL | D6376 ¦ SAF II | Saudi Aramco |  | ECLL |  |  |  | Corrosion Injection access fitting/quill retriever volume | Aramco standard drawing DA-950035-001 indicates, standard requirement of 24” diameter volume to be considered for retrieval volume for corrosion injection quill/access fitting. | The standard requirement of maintaining 24” diameter free space for retriever volume was missed out in detail design | Space requirement for online retrieval need to be double checked for CI injection access fitting during detail design of the project
46 | CHN-ECLL-PL-0046 |  | Piping & Layout | PL | D6376 ¦ SAF II | Saudi Aramco |  | ECLL |  |  |  | Corrosion Coupon and Probe installation requirements | Corrosion probes and coupons were installed in yard part of inline piping instruments, but during Proponent walkthrough it was identified and was insisted to install corrosion probe & coupon only before commissioning of the platform. | Piping design isometrics does not specify clearly that corrosion coupon and probe are required to be installed before commissioning of the platform | Recommended to add a note on Piping design isometric drawing saying that corrosion probe and coupon shall be installed before commissioning of the platform
47 | CHN-ECLL-PL-0047 |  | Piping & Layout | PL | D6847 ¦ Hasbah | Saudi Aramco |  | ECLL |  |  |  | Bolt material (Solid Inconel vs CS) | Procurement Overrun in Piping Stud Bolts was found during execution due to requirement of solid Inconel bolts in place of CS bolts. CS bolts were considered during bid, where as bid documents were specifying bolts of solid Inconel material. |  | Very careful review is recommended to check whether what bolt material is permitted or not per bid documents. If required, review from SME must be ensured prior to taking such big decisions. Attention must be paid to bolt material as there is significant cost difference between CS material and Alloy 625 material (exotic material).
48 | CHN-ECLL-PL-0048 |  | Piping & Layout | PL |  | Saudi Aramco |  | ECLL |  |  |  | Slimline DBB vs Integral DBB | Consideration of Slimline type DBB Valves in place of Integral type in bid pricing. Slimline type considered in Bid against Spec requirement of Integral type DBB, which was a bid miss. Attention was not paid to the isolation philosophy requirements during bidding. | - Inadequate review of Bid documents led to Bid miss | - Slimline design has lower cost than DBB valves but this can only be accepted if it is permitted in the design. Very careful review is recommended to check whether slimline design has been permitted or not per bid documents. If required, review from SME must be ensured prior to taking such big decisions.
49 | CHN-ECLL-PL-0049 |  | Piping & Layout | PL | D7057 ¦ MRJN TP10 | Saudi Aramco |  | ECLL |  |  |  | Incorrect Bolt Lengths causing cost overrun | There was an issue noted in TP 10 project, related to incorrect bolt lengths specified in the isometrics for the Inconel flanges 2” & 4” size Inconel Pipe class, 90NX0T, API 3000#, The length of the bolt procured, and the actual requirements were different (The procured length is lower than that of required). The number of bolts is around 4000. The Bid PMS mentions A193 bolt. During execution, a discrepancy was found between the bolt table and the PMS. PMS indicates A193 B7 with sleeve for default option, which is supposed to be for optional flange where insulating gaskets are required. However, Bolts per Contract requirement is A 193 B7, which was not followed. | Lead engineer was demobilized during critical stage of project. The coordination between the Piping engineering team and design team missing. There is no evidence that the piping requisition engineer verifying the MTO with the layout and the PMS. The bolt table used in the project belongs to LTA 2 and there is no evidence that this table is validated for the project as per the PMS. Lack of checking during isometric extraction. | 1. Strict adherence to PMS, and any subsequent revision must be made aware to all concerned. 2. Use of any go by documents from previous projects must be validated for the present project. 3. Bolt table with test isometrics shall be signed by all 3 parties and must be validated. 4. Prior to issue of final MTO and AFC isometrics, stud bolt lengths to be verified manually and certified. 5. If the bolt table is not final and the isometric drawings are to be issued to meet fabrication schedule, the stud bolt lengths to be kept under HOLD and drawings to be issued. 6. Piping requisition engineer must check and verify the MTO issued from Layout is included with all length cases as per P&ID and PMS. 7. Proper orientation must be imparted to the engineers/designers, who are new joinees to McDermott.
50 | CHN-ECLL-PL-0050 |  |  |  | D5773 ¦ ONGC | ONGC | [5 empty] | Vent Line routing and slope requirements | The layout of ONGC decks made it inconvenient to have positive slope on the vent lines as required by Process.This was identified during the Cold eye reviews conducted on 3D models. |  | Layout team should inform/highlight to Process during the early phase of engg, if any of the process requirements (specified in PID's/datasheets) could not be met due to one or the other reasons. (Example: PSV upstream & downstream slope should be properly modeled as it is an API code requirement and safety issue) Design isometrics shall be issued as IDC to process (or) model reviews to be done for all critical lines. Process should identify the critical lines, for which they want to review the isometrics. If slope requirement could not be met, adequate drain lines should be provided to prevent liquid accumulation in PSV discharge lines.
51 | CHN-ECLL-PL-0051 |  |  |  | A6019 ¦ PEMEX | Pemex | [5 empty] | Model Progress and frequent Changes | Quality of model often misconstrued due to lack of progress and changes happening very often, affecting the progress and productivity. |  | The scope for the 3D model health checks and cold eye reviews need to be defined prior to initiating them -- identifying the areas that can be reviewed in agreement with the project engineering team. The timing for such reviews to be decided at an appropriate time when the design is mature enough for the audit.
52 | CHN-ECLL-PL-0052 |  |  |  | A6019 ¦ PEMEX | Pemex | [5 empty] | Discripency between structural and piping isometrics | Mis-match of dimensions between riser isometric drawings (issued by SURF) & structural drawings Riser clamps bolts floro-ploymer coated as per drawing but galvanized (above splash zone) as per MTO |  | Better interaction between engineering disciplines (pipeline, piping and structural) to avoid conflicting dimensions / details.
53 | CHN-ECLL-PL-0053 |  |  |  | A6019 ¦ PEMEX | Pemex | [5 empty] | Piping & valves inside Vendor Packages | Piping & valves interconnectivity neither included in vendor MTO nor in MDR MTO (bid miss). Because of this the MTO's and weight estimates were grossly underestimated. |  | Valves, Piping, E&I items inside vendor packages - whether vendor scope or MDR scope to be to be clearly identified during Bid Stage to avoid cost impact during project execution. To achieve this, detailed evaluation of vendor offers need to be done during bid stage and cost adders clearly identified.
54 | CHN-ECLL-PL-0054 |  |  |  | D6071 ¦ QP Bul Hanine | Qatar Petroleum | [5 empty] | 3D Model inconsistencies | Halul facility (Onshore scope) Coordinates Laser model not matching with actual coordinates at site. This resulted in revising many drawings. | Incorrect PDMS set-up that did not consider a correct reference point (0,0) with respect to actual resulting in mismatch. | Perform a due diligence on the laser model by checking with existing drawings, appropriately liaising with the laser survey subcontractor to rule out any inconsistencies in understanding and ensuring a correct reference point. Perform a pre-engineering site visit to confirm the reliability of the laser model.
55 | CHN-ECLL-PL-0055 |  |  |  | A7697 ¦ Angelin | British Petroleum | [5 empty] | Lack of standardization | Lack of focus to minimize different type of valves and bulks, line size and spec, put a burden on procurement. Though this was mainly due to weight management – to use fit for purpose size of valves to keep weights low. – on hindsight, it looks like it was overdone. This myriad of spec and size resulted in sourcing and delayed procurement |  | A proper review of pros and cons of different size and rationalization of standard size and spec , to be reviewed early in the project.
56 | CHN-ECLL-PL-0056 |  |  |  | A6224 ¦ KJO Hout | Al Khafji Joint Operations | [5 empty] | Including PMI/UT checks for Brownfield tie-ins during Pre-engineering survey | In our pre-engineering survey, we did not perform any existing piping PMI/UT checks for verifying the suitability of all piping tie-ins. During recent pre-execution stage checks, they performed PMIU, UT checks and found surprises wherein few places the thickness was less than PMS and few places the material was CS and not SS as per our drawings |  | Pre-engineering check list to highlight these PMI and UT requirements to bring up for discussions at early stage.
57 | CHN-ECLL-PL-0057 |  |  |  | N0510 ¦ TYRA | Maersk | [5 empty] | PDMS Model Review | PDMS model review was not attended by all project stakeholders from customers, e.g. Operation team. In the past projects it caused reworks on vendor skids, valve access, instrument access etc. In addition we ended up adding additional access platform for the in accessible equipment, instruments. |  | Human Factor Engineering reviews shall take consideration of all access issues. In addition Operation from MOG will be participating in PDMS model reviews.

## Structural
Serial No | LL Number | Date | Discipline | DC | Project Name | Client | Facility category | LL category | Subject1 | Subject2 | Subject3 | Title | Background | Root cause | Corrective action | Preparer | Preparer Desn | Reviewer | Reviewer Desgn | Approver | Approver Desgn
1 | CHN-ECLL-ST-0001 |  | Structural | ST | D5773 ¦ ONGC | ONGC | Topside | ECLL | Topside | Building |  | IDC reviews of structural deliverables without 3D models | IDC reviews of a few critical structural deliverables (architectural walls, security gate etc.) were completed by disciplines without the 3D model getting updated for the same. This resulted in rework to fix the piping/ E&I clashes with these structures. | 3D model not updated in line with 2D drawings issued. | The IDC reviews of all layout related deliverables shall be done only when the 3D model of the same is made available. All disciplines to ensure that the 3D model is updated prior to issuing them for IDC reviews.
2 | CHN-ECLL-ST-0002 |  | Structural | ST | D5773 ¦ ONGC | ONGC | Topside | ECLL | Topside | Helideck |  | Overhanging of structure | Large overhang of solar array platforms on BHE deck resulted in deflection of the platform. | Structural Integrity - Deflection | Supports to be suitably designed to avoid large cantilevers.
3 | CHN-ECLL-ST-0003 |  | Structural | ST | D5773 ¦ ONGC | ONGC | Riser platform | ECLL | Riser | Jacket |  | Riser Clash | The riser arrangements in D5773 had to undergo a few revisions because of late client inputs (risers were swapped) and also because of the fact that risers were not modeled in PDMS. This led to clashes with the jacket bracings and the riser arrangements had to be changed, having a knock on effect on layouts. | Riser modelling on Jacket including riser approach to Jacket | The risers need to be modeled all the way down to the sea-bed by Layout in PDMS and clash checked
4 | CHN-ECLL-ST-0004 |  | Structural | ST | D5773 ¦ ONGC | ONGC | Jacket | ECLL | Boatlanding | Lift | Trial fit | Boat landing design | Boat landing design complex and flimsy and had to be flipped 180 twice for trail fit, which had also caused damage to shock cells. | Boat landing design to be checked for yard lifting during trial fit. | Stabbing arrangement more suitable for fabrication as well as offshore installation.
5 | CHN-ECLL-ST-0005 |  | Structural | ST | A6019 ¦ PEMEX | Pemex | Production platform | ECLL | Caisson | Installation |  | Caisson Installation Methodology | Installation methodology for Caisson not considered even in the early stages of the project | Caisson installation methodology | Caisson Installation Methodology and cost impact to be considered and documented during Bid Stage and further elaborated and finalized in early stage during Detailed Engineering.
6 | CHN-ECLL-ST-0006 |  | Structural | ST | A6019 ¦ PEMEX | Pemex | Production platform | ECLL | Pile Drivability | Geotechnical Report | Pile Driving Hammer | Pile Drivability and Hammer Selection | Pile load and hammer size for doing the pile drivability, not reviewed properly. The bid documents referred to 2 different soil reports, but only one was given during bid stage. No effort was made to obtain the missing report during bid. The missing report provided after award led to two different sets of soil data for the two adjacent platforms. Using one Soil data the pile length calculated was 65m and the other Soil Data gave a Pile length of 79m. Since both were adjacent although PEMEX confirmed to use the data that resulted in 65m Pile Length calculation - ignoring the other data which is actually more closer to our PB-Litorale A platform poses a big risk during offshore pile driving and installation. Hammer size also could go to higher size. | Geo-technical report availability | Soil reports and geotechnical information need to be obtained during bid stage; clarifications to be obtained in case of discrepancies and should be part of the bid basis. Pile driveability and hammer size selection should be based on correct information during bid.
7 | CHN-ECLL-ST-0007 |  | Structural | ST | A6019 ¦ PEMEX | Pemex | Production platform | ECLL | Structural MTO | Fabrication Team |  | Custodian of MTO structural databases | MTO databases for structural materials should be under the custody of yard CSE team so that right materials can be purchased. In this project, this responsibility was given to Engineering up to AFD stage, as yard CSE team did not have sufficient personnel to update the MTO databases from IDC stage. All MTO updates after AFD was supposed to be done by yard CSE team. However during the placement of primary steel MTO's the AFD stage MTO descriptions were used for procurement purposes and AFC drawings were attached to the vendor - which led to last minute confusion on placing firm PO's with the steel vendor Sam Kang. | Yard MTO team to maintain Structural MTO and update frequently. | MTO database for structural materials should be under the custody of yard CSE team and they should be sufficiently manned.
8 | CHN-ECLL-ST-0008 |  | Structural | ST | A6019 ¦ PEMEX | Pemex | Production platform | ECLL | Stair/Stair Tower | Constructability |  | Stair Tower Design | Not so effective stair tower design in wave zone to accommodate fab yard requirements | Constructability of Stair Tower | Design of Stair Tower to be done considering fab yard requirement and ease of fabrication and erection.
9 | CHN-ECLL-ST-0009 |  | Structural | ST | A6019 ¦ PEMEX | Pemex | Production platform | ECLL | Pipe Support | Constructability |  | Use of doubler plates | Every support on the column irrespective of the load / size were provided with doubler plates, creating too much work for the yard. Fabrication has proceeded without doubler plates, as it is against Atlantic practice. | Excessive use of Doubler plate for supports welded to Braces | Criteria to be be evaluated based on realistic approach and doubler plates applied only for critical supports. Appropriate work instruction / procedure to be developed for this.
10 | CHN-ECLL-ST-0010 |  | Structural | ST | A6019 ¦ PEMEX | Pemex | Production platform | ECLL | Equipment/Supports | Transporation | Temporary support | Rational use of stiffeners | Too many stiffeners for equipment saddle supports to take care of transportation loads were provided. | Additional stiffeners on Equipment saddle support for transportation condition. | Cost benefit analysis of strengthening permanent steel structures vs removal of transportation supports to be made prior to making changes to the design.
11 | CHN-ECLL-ST-0011 |  | Structural | ST | D5773 ¦ ONGC | ONGC | Well head platform | ECLL | Painting | Topside | Equipment/Supports | Paint Warranty for Vendor packages | As per the General Conditions of Contract, Contractor has to furnish a warranty for the painting for Jacket and Deck along with topsides facilities (inclusive of all the Decks and equipment installed) for a period of 38 months from the date of expiry of initial warranty period for the works. To cover this warranty period, Contractor has to furnish performance bank guarantees. This additional paint warranty requirement was not specified in the Purchase Requisitions issued for the various equipment and hence it was difficult to impose this requirement on the vendors, after placement of order. Alternatively it was decided to look at the methods to improve the quality of painting at the vendor works. This was done by suitably commenting on the vendor ITPs – adding Witness/ Hold point for surface preparation and painting and close monitoring and control on these activities by MDR QA/QC. | Warranty for painting of Jacket, Topsides and equipment. | It is recommended that Project Specific “General Notes” identifying such project specific requirements are prepared at the initial stages of the project and this should be part of every Purchase Requisition / PO.
12 | CHN-ECLL-ST-0012 |  | Structural | ST | A6224 ¦ KJO Hout | Al Khafji Joint Operations | Auxiliary platform | ECLL | Brownfield | Bolted connection | HUC Team | Bolted vs Welded connection for Brownfield | HUC preferred bolted connections for offshore field connections to avoid hot works & requirement of habitats. However, bolted connections for primary connections are found not generally accepted by clients for various reasons of maintenance, performance, no redundancy, lack of clarity in standards & specifications. Additionally, more than normal engineering & design man-hours is required as existing structure integrity check for section property loss due to bolt holes & bolted connection design is not possible with standard software. | Brownfield Bolted connection connection | Usage of bolted connection for primary members to be clarified & accounted accordingly at bid stage for the project. Structural Dept. should develop standard bolting scheme/details for all brownfield structural modifications in consultation with Brownfield HUC Team / CSE.
13 | CHN-ECLL-ST-0013 |  | Structural | ST | A6224 ¦ KJO Hout | Al Khafji Joint Operations | Auxiliary platform | ECLL | Geotechnical Report | Mudmat |  | Clay soil | Top layer of soil is very soft clay and generally soil consultant gives parameter only for top layer, which leads to large size mudmat. | Geo-technical report - Skirt Mudmat | While writing SOW for subcontractor ensure to add a clause, if clay soils are encountered, suitable soil parameters at suitable intervals shall be provided for skit mudmat design.
14 | CHN-ECLL-ST-0014 |  | Structural | ST | A6224 ¦ KJO Hout | Al Khafji Joint Operations | Auxiliary platform | ECLL | 3D Modelling | Structural MTO |  | Comparison of Structural MTO with PDMS | As all structural components are modelled along with grades in PDMS. This help in comparison of structural MTO ordered and also any structural steel top-up can be ordered based on PDMS MTO dump. | 3D modelling including Material Grade | Ensure all structural steel components shown on drawings are properly modelled in PDMS with grades. Plan for MTO extraction from PDMS model and adopt the same during material ordering.
15 | CHN-ECLL-ST-0015 |  | Structural | ST | A6224 ¦ KJO Hout | Al Khafji Joint Operations | Auxiliary platform | ECLL | Geotechnical Report | Mudmat |  | Geotechnical Report | As per site specific soil report supplied by COMPANY, top layer of soil was sand. Accordingly On-bottom Stability Analysis and mudmat design was performed and build as part of base scope. As part of revised scope when reviewed pipeline soil data and near by platforms, all top layer of soil was very soft clay. | Geotechnical report of near by structures | Review existing soil data and pipeline soil data for nearby platform if both are available. If only soil report is available, do the survey and raise a TQ to Company in case of a query / conflict
16 | CHN-ECLL-ST-0016 |  | Structural | ST | A6224 ¦ KJO Hout | Al Khafji Joint Operations | Auxiliary platform | ECLL | Pile / Pile Penetration | Insurance Pile |  | Insurance pile requirement and length | Insurance pile for KRG Jacket of 9m was considered and there was no comments at beginning of project, however Marine at later stage had asked for 12m which includes cutoff allowance of 3m. Insurance pile for Flare Tripod Jacket was not considered in base scope of project and same has been requested by Marine. | Late request from Marine for Insurance piles | Ensure to get clear way forward from Marine & PMT for Insurance pile requirement at beginning of project, to avoid late ordering of material.
17 | CHN-ECLL-ST-0017 |  | Structural | ST | A6224 ¦ KJO Hout | Al Khafji Joint Operations | Auxiliary platform | ECLL | Installation | Boatlanding |  | Offshore installed boat landing stub connection between jacket and boat landing | No green length was provided on offshore installed stub connection between jacket and boat landing. Marine has requested for additional green, to allow for any tolerance during installation. | Offshore installation tolerance green length on boatlanding stubs | Ensure to get marine comments in advance on all offshore installed loose pieces. Constructability to address such aspects upfront.
18 | CHN-ECLL-ST-0018 |  | Structural | ST | A6224 ¦ KJO Hout | Al Khafji Joint Operations | Auxiliary platform | ECLL | Boatlanding | Lift | Installation | Padeye for boat landing | Engineering has prepared boat landing padeyes based on Marine request as this padeye are not intended to cut at offshore. However when drawings are issued for Marine review, they told that this padeye drawings was not required as they will be using soft sling to lift boat landing. | Boatlanding Lifting Padeye | Marine need to clearly define requirement of padeye after their internal review. Constructability to address such aspects upfront.
19 | CHN-ECLL-ST-0019 |  | Structural | ST | A6224 ¦ KJO Hout | Al Khafji Joint Operations | Auxiliary platform | ECLL | Transporation | Loadout | Marine Team | Late change from Marine in loadout and Transportation | Many changes caused by Marine regarding loadout and transportation led to post-AFC changes for structural drawings (KRG deck loadout scheme / KRG deck transportation barge / Deck orientation in cargo barge etc. changed) | Frequent changes by Marine on Loadout/Transportation. | Marine to avoid such late changes and close this as part of stagewise constructability
20 | CHN-ECLL-ST-0020 |  | Structural | ST | A6224 ¦ KJO Hout | Al Khafji Joint Operations | Auxiliary platform | ECLL | Pile / Pile Penetration | CSE |  | Pile drawings | Pile makeup drawings issued both from Engineering & Marine CSE. Fabrication was done based on CSE drawings. | Pile make-up drawings issued from both Engineering?CSE. | Need to ensure only one drawings is produced and all comments from CSE need to be captured on Structural drawings
21 | CHN-ECLL-ST-0021 |  | Structural | ST | A6224 ¦ KJO Hout | Al Khafji Joint Operations | Auxiliary platform | ECLL | Air Gap | Topside |  | Sub cellar deck elevation change | Sub cellar deck elevation was in air gap as elevation was reduced to meet drain line slope requirements and pump NPSH. Deck elevation could be increased due to interconnecting bridges. | Sub-Cellar deck elevation falling within Air gap | Sub cellar deck elevation need to finalized at beginning of project with proper study from layout and process.
22 | CHN-ECLL-ST-0022 |  | Structural | ST | D6688 ¦ 9 Jackets | Saudi Aramco | Tie-in platform | ECLL | Pile / Pile Penetration | Pile Drivability | Insert Pile | Pile refusal in ARAMCO ZULF FIELD platforms | Pile refusal is expected at shallow depths due to the presence of thick Gypsum or Calcarenite layers . Shallow refusal occurred at ZULF 590/599 Jacket in 9 Jackets project and ZULF 2010/2019 Jacket in 13 Jackets project. | When the soil layer thickness is less, geotechnical reports adopt conservative (lower) capacities for pile capacities. Once the pile is driven through these layers residual capacity will be low as it losses properties. | Grouted pile capacity curves should be part of all soil reports. Insert pile design shall be carried out and approved by Aramco in advance if Gypsum layers are encountered at shallow layers. Shear keys shall be used to reduce the depth of insert pile. High strength grout to be used in order to reduce the insert pile depth. Electrical connectivity must be maintained between the insert pile and the main pile. An Optimum insert pile design will result in minimum offshore time.
23 | CHN-ECLL-ST-0023 |  | Structural | ST | D6200 ¦ SAF 6 | Saudi Aramco | Tie-in platform | ECLL | Boatlanding | Trial fit | Constructability | Boat Landing Misalignment at walkway interconnections and the ovality of the king posts | During installation campaign for SFNY-550 jacket by DB-32 vessel, Misalignment of 55mm was found between the south and east boat landings upper chords During boat landing trial fit at fabrication yard for ZULF 610, it is found the stand off member having ovality issue | Jacket will never be perfectly level after installation. When two boatlandings at two faces has to be inter connected, this will have natural alignment mismatches. All pipes will have ovality (normally within tolerance), which may increase during the fabrication / welding process. | Where ever possible Boat landing trial fit to be done before the loadout When ever two Boat landings has to be interconnected, details has to developed taking into account expected jacket level tolerances. Installation of header plate in the both end of boat landing chord may be required to accommodate the misalignment issue Ovality check should be done for the king post bottom length to ensure smooth stabbing and also on stand off pipes, if any major ovality found it shall be corrected following the approved procedures.
24 | CHN-ECLL-ST-0024 |  | Structural | ST | D7358 ¦ MRJN Upgrade | Saudi Aramco | Tie-in platform | ECLL | Brownfield | Codes and standards |  | Existing structure overstress | In brown field modification, new modules / equipment etc. are required to be added. Adding new loads to the existing platform that may exceed the allowable capacity and the design limits. | Existing platforms are designed to meet older API codes and older design basis. | Do quick checks/analysis to ensure complying With API recommendations.
25 | CHN-ECLL-ST-0025 |  | Structural | ST | D7057 ¦ MRJN TP10 | Saudi Aramco | Tie-in platform | ECLL | Building | Floor / Plating / Grating |  | Building floors | As per Aramco standard specification SAES-P-119, the floor shall be horizontal below the switch gear equipment only, However providing ramps inside the building will cause a problem during material handling as well as the access / egress. Hence, flat surface plate should be considered inside the building. | Aramco deck levels are with 1:100 slope. The building will be in this area, however this local area has to be kept flat. | During bid stage , a query has to be sent to client to confirm the specific requirements.
26 | CHN-ECLL-ST-0026 |  | Structural | ST | D7057 ¦ MRJN TP10 | Saudi Aramco | Tie-in platform | ECLL | Blast Design | Blast Wall |  | Blast analysis and impact on additional steel strengthening requirements | The IFB structural drawings/ MTO typically don’t consider blast Loads, as the Blast Risk Assessment is not part of feed documents typically. During detailed engineering the BRA study should be done in a very early stage as it may affect the members / plates integrity. | Blast analysis not performed during FEED design. | Early issue BRA study at AFC stage and consider additional contingencies during bid stage.
27 | CHN-ECLL-ST-0027 |  | Structural | ST | D7057 ¦ MRJN TP10 | Saudi Aramco | Tie-in platform | ECLL | Building | Floor / Plating / Grating | Drains | The transition from flat building floor to slopped deck area | Due client requirements to consider the switch gear building a flat surface therefore ramps were added. | The building floor area is flat and also some the area outside also will become flat due to ramp or other detailing limitations | Add additional drains those areas at early stage of the project.
28 | CHN-ECLL-ST-0028 |  | Structural | ST | D7057 ¦ MRJN TP10 | Saudi Aramco | Tie-in platform | ECLL | Brownfield | Clamps | Connection / Bolted | Use of clamp connections in brown field structures | Typically Mechanical clamps used in brown field structures is designed as a fully connected joint to the structure and the clamp design will be checked separately, the existing structure joint crushing check is not done correctly because the associated Hoop stresses from the bolt tightening is not considered in the calculations. | In adequate engineering calculations for the clamp connections | FEM analysis or a detailed check on the combined stresses should be done to simulate the actual stresses on the existing structure.
29 | CHN-ECLL-ST-0029 |  | Structural | ST | D6200 ¦ SAF 6 | Saudi Aramco | Well head platform | ECLL | Padeye | Analysis / Design / FEA | Constructability | Pad eye orientation hold removal | Orientation of the pad-eyes affect fabrication schedule for the topside as it’s preferable be fabricated as pancake while the pad-eye slotting will affect the process. | Hold on pad eye orientation due to lack of confidence with the CoG in WCR | FEM analysis or a detailed check on the combined stresses should be done to simulate the actual stresses on the Projected Pad-eye.
30 | CHN-ECLL-ST-0030 |  | Structural | ST | D6200 ¦ SAF 6 | Saudi Aramco | Electrical platform | ECLL | Mudmat | Analysis / Design / FEA | Crimp Plate | Use of crimped plate for the mud mat | In SAF6 EDP project due to the limitation of the crane capacity it was required to reduce the Mud-mat weight as much as possible. As an innovative solution we use crimped plate mud-mat with skirt arrangement. | Non availability of soil report during bid | FEM analysis should be considered to check the actual stresses in the plates.
31 | CHN-ECLL-ST-0031 |  | Structural | ST | D6200 ¦ SAF 6 | Saudi Aramco | Electrical platform | ECLL | Analysis / Design / FEA | Deflection | Equipment/Supports | Deflection limits for the GIS / GIB area required by vendor | In SAF6 EDP project GIS / GIB required deflection control due to the duct material. However, the required criteria was not identified in early stage of the project / bidding stage. | Tight deflection limitations dictated by GIS/GIB vendors. | Early identification of such items during execution / bidding stage
32 | CHN-ECLL-ST-0032 |  | Structural | ST | D7057 ¦ MRJN TP10 | Saudi Aramco | Tie-in platform | ECLL | Bidding | Analysis / Design / FEA |  | Critical bid analysis requirements | During TP-10 bidding time the provided man-hours and schedule was very limited accordingly some critical studies was not done during that stag such as transportation and float-over analysis of the topside. | Tight bidding schedules / budgets | Structural lead should identify the critical analysis and activates to be done and agreed with the bid manager.
33 | CHN-ECLL-ST-0033 |  | Structural | ST | A6019 ¦ PEMEX | Pemex | Production platform | ECLL | Flare structure | Lift | Marine Team | Frequent changes to flare stack design. | The flare bridge and tripod design (initially shelved as flare boom option was explored) was finally taken up after a prolonged discussions with Pemex in Feb'14 on the relief system capacities. Every time, the vent dispersion study had to be done to verify if the option is acceptable. Opinion was sought from marine about the lifting methods for the tripod+flarestack and it was agreed that counterweight mechanism can be used. Not enough thought was applied to see if there is a better way to do this. This came up after the marine constructability reviews conducted during Sep'14 and a better option to lift the bridge and flarestack together was proposed by CSE. The new proposal was technically feasible and was giving considerable benefit in terms of saving marine costs. | Early finalisation of Flare lift philosophy. | Various options towards cost optimization / design optimization shall be addressed well in advance during early constructablity review sessions should be used to challenge the design to identify optimizations. These issues should not be left till engineering completion stages.
34 | CHN-ECLL-ST-0034 |  | Structural | ST | D6071 ¦ QP Bul Hanine | Qatar Petroleum | Well head platform | ECLL | Brownfield | Pipe Support / Modular supp |  | Modular v/s conventional supports | Modular Support for Brownfield Scope - Modular supports were specified with the intention to reduce offshore hook-up work, post award. Bid basis was conventional supports. However, the cost of the supports are higher than conventional supports, however, this was expected to be offset with a productivity gain. A root cause analysis was initiated by PMT to assess the additional costs. Root cause showed that modular supports did provide an overall benefit. | Inadequate cost benefit analysis | Any optimization exercise should take into account a number of factors prior to be implemented and needs the concurrence of all parties and functions. There will be often conflicting factors - for instance, a productivity gain need not necessarily result in a reduced cost if it is not on critical path. A cost-benefit assessment is in order in such cases prior to decision making. Such items should go through a MOC process with appropriate sign-offs. Attention to be paid while finalizing philosophy during bid as well.
35 | CHN-ECLL-ST-0035 |  | Structural | ST | A7697 ¦ Angelin | British Petroleum | Well head platform | ECLL | Weight Control Report | Not to exceed weight |  | Weight Control | Platform Weight exceeded the bid estimate and DLV200 NTE lift weight. During pre-FEED phase, the first draft weight estimate , after initial workshop, indicated +400 MT (40%) higher factored weight to what was estimated in bid phase (which was based on OME benchmark). This almost jeopardized the project feasibility A rigorous review was conducted and found the draft weight estimated was correct and the Bid estimate was overly optimistic and did not dial in all requirement’s | Improper WCR reporting during bid stage. | This should be tied up with schedule. Adequate contingency and cross functional review to be considered while providing OME weight estimates. Rigorous weight management strategy shall be in place right from beginning of the project Close monitoring of weight : bi-Weekly review, monthly WCR Escalation of challenges to leadership team and quick decision making from leadership team helped us control the Platform weight – a major positive
36 | CHN-ECLL-ST-0036 |  | Structural | ST | N0510 ¦ TYRA | Maersk | Well head platform | ECLL | Constructability | Nodes |  | Weld defects | Weld defects at Interface of Leg Tubular and Star/End Plate. Constructability review for the project was conducted during detail engineering phase. For main leg locations the detail agreed during constructability had plate girders (PG) thru and legs were discontinued. Legs from both sides of PG were connected on star/end plate. Leg thickness at these interface locations were in the range of 70-80mm. Detail provided allows the leg tubular welding to be single V with access from outer side of tubular. Filling single V from one side required several weld passes and access to weld area was limited due to deck plating. It resulted in several weld defects. Rectifying these weld defects became a major bottleneck in fabrication progress. | Early constructability reviews | Follow leg thru connection for such joints wherein plate girder flange/star plate are welded on leg tubular. This allows two side welding access and in-case of thick flanges / star plate double V weld can be provided. Constructability rview are normally conducted in the early stage of detail engineering (i.e. much before the start of detail fabrication activities). It is understood that during initial phase full construction team is not mobilised but it is very critical to ensure right representation from discipline participates during Constructability. Issues related to welding access. risk of weld defect issues etc..need to reviewed for critical joints.

## Electrical
Serial No | LL Number | Date | Discipline | DC | Project Name | Client | Facility category | LL category | Subject1 | Subject2 | Subject3 | Title | Background | Root cause | Corrective action | Preparer | Preparer Desn | Reviewer | Reviewer Desgn | Approver | Approver Desgn
1 | CHN-ECLL-EL-0001 |  | Electrical | EL | D5773 ¦ ONGC | ONGC |  | ECLL |  |  | Electrical Loads / Load list | Solar sizing calculations | Due to frequent changes in Instrumentation loads (some optimizations, some bid miss and some vendor induced), solar sizing calculations was revised several times, which delayed the finalization of system design, sizing of solar controller, batteries, cables and solar panels. In addition to this, equipment layout and solar deck layout were modified a few times (to accommodate the required number of solar panels and as per vendor recommendations), which resulted in changes in no. of junctions boxes, cable size, cable glands, distibution board and solar modules mounting structures. |  | Solar sizing calculation needs be done only after finalizing the instrumentation loads. Solar panel deck layouts need to be finalized only after the sizing calculations are complete. The orientation of the solar panels is directly related to the location of the offshore facility, and this orientation needs to be clearly communicated by electrical engineers to the layout team without waiting for vendor inputs.
2 | CHN-ECLL-EL-0002 |  | Electrical | EL | D5773 ¦ ONGC | ONGC |  | ECLL |  |  | Electrical building | Late finalization of Architectural vendor and scope causing rework in design efforts | The selected architectural vendor came up with a Sewage treatment plant which required 240V AC power, when the requirement was for a biological STP which required no electricity. It took time and efforts from engineering to zero in on the type of Macerator, and there were further delays from the vendor in finalizing the toilet / toilet support details. |  | Proper TBE of the architectural sub-contract needs to be done and client requirements need to be clearly spelt out to the sub-contractor prior to placement of order.
3 | CHN-ECLL-EL-0003 |  | Electrical | EL | D5773 ¦ ONGC | ONGC |  | ECLL |  |  | Unique project requirement | Design tolerence not considered for cable glands | Some of the cable glands were not suitable for the actual cable sizes (manufactured to ± 2mm tolerances) Some of the cable glands of the same model were received with different internals. |  | Attention to detail during engineering and procurement stages is required.
4 | CHN-ECLL-EL-0004 |  | Electrical | EL | D5773 ¦ ONGC | ONGC |  | ECLL |  |  | Electrical Loads / Load list | Illumination requirements for Level Gauge | Illumination requirements for Level Gauges were missed during the bid engineering. As ONGC platforms are solar powered, the electrical load list had to be updated during deatiled engineering to include the power consumption for level gauge illuminators, which led to the increase in number of solar panels and related electrical accessories. |  | Wherever Level Gauges require illumination, Instrumentation discipline to communicate the load requirements of the same to Electrical for inclusion in the Electrical Load list. This must be rigorously implemented on all Solar powered structures.
5 | CHN-ECLL-EL-0005 |  | Electrical | EL | D5773 ¦ ONGC | ONGC |  | ECLL |  |  |  | Control Cards | Some Control cards were not working for solar packages. |  | Spare control cards should be considered for solar packages (or Electrical/Instrumentation packages). FAT to be carried out for control panel.
6 | CHN-ECLL-EL-0006 |  | Electrical | EL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Electrical Load Growth | During bid stage total platform load was 1114kW with two numbers of 2500kVA transformers, during engineering platform load has grown upto 2790kW which results in one more 1500kVA additional transformer and increase in MCC feeders & Cables, etc., The load has increased by 1676kW , which more than twice the estimated load. |  | Caution to be exercised while estimating load during bid stage. All loads as per vendor bid information shall be included in the list. There shall not be any “miss out “. Checklist for determining system-wise electrical loads needs to be prepared for bids / detail engineering phase.
7 | CHN-ECLL-EL-0007 |  | Electrical | EL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Electrical Feeders for HVAC System | HVAC Panel vendor input still not finalized (18 months from project award). This will have an impact on building internal volume blocking and lot of cable tray adjustment and finalization of MCC feeders. |  | HVAC shall be finalized earlier (at least at 50% of engineering completion).
8 | CHN-ECLL-EL-0008 |  | Electrical | EL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Electrical Feeders for Mechanical packages. | Due to delay in Mechanical package input, Electrical load changed many times. This has affected electrical deliverables such as sizing of equipment, revision of documents, After placing MCC PO, lot of changes in mechanical Packages load. It has impact change order. |  | MCC PO to be placed after 75% completion of the mechanical load.
9 | CHN-ECLL-EL-0009 |  | Electrical | EL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Cable Tray fixing holes | Tray fixing holes were finalized based on the identified vendor (Crouse hinds), however this vendor was changed to SEASAFE at a very last stage. The fixing holes arrangement of Crouse hinds tray details did not match for SEASAFE tray details. This resulted in re-works in modeling and fabrication at the yard. |  | This could be avoided by finalizing the cable tray vendor at the early stage.
10 | CHN-ECLL-EL-0010 |  | Electrical | EL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Late finalization fo cable vendors | Cable vendor was finalized very late stage of the project. It has affected cable OD finalization and cable tray sizing. |  | This could be avoided by finalizing the cable vendor at the early stage of engineering.
11 | CHN-ECLL-EL-0011 |  | Electrical | EL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Change orders from MCC vendor Schneider | During TQ stage MCC vendor confirmed all open points. After PO placement they came with changes with commercial impact. |  | Typical control circuit diagram shall be included as part of the RFQ.
12 | CHN-ECLL-EL-0012 |  | Electrical | EL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Optimization of Cable Tray Supports | Cable tray support typical drawings should cover maximum types of special supports, so that separate drawing for special support can be avoided. |  | By covering the special supports in the typical drawing we can avoid making separate drawings for special supports, which would result in lot of time saving.
13 | CHN-ECLL-EL-0013 |  | Electrical | EL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Mounting details of Light fixtures. | As per PEMEX typical installation, column mounted fixtures are to be installed using trunnion arm for mounting Normal and Emergency lighting Fixtures. WE could not use the trunninon arrangement for emergency lighting fixtures. For emergency lighting fixtures mounting arrangement (bracket type mounting with angled Dome) was adopted as per the advice by the vendor. This resulted in rework for lighting calculation. |  | Type of lighting fixtures and installation details shall be finalized before finalizing typical lighting installation details. It is better to float an inquiry before the 1st pass lighting study to find out what is available in the market.
14 | CHN-ECLL-EL-0014 |  | Electrical | EL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Change in MTO formats. | MTO format is not finalized at the initial stage, later the requirement came with system wise MTO, which resulted in additional work to generate MTO as per system wise requirements. A separate MTO in a different format had to be issued to procurement. |  | MTO format has to be finalized during initial stage. Multi formats to be avoided.
15 | CHN-ECLL-EL-0015 |  | Electrical | EL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Clarity on scope split for vendor packages | In Air cooler package access platform initially was under the scope of MDR, Later the access platform transferred to vendor’s scope. Lighting and cable tray supports model were done based on MDR access platform by welding arrangement. After the change of scope to vendor, platform is made by galvanized steel and welding is not allowed on the platform. This results in rework for bolt & nut fixing model for all the supports. |  | Scope of access platform shall be finalized before finalizing the supports.
16 | CHN-ECLL-EL-0016 |  | Electrical | EL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | 24DC Cables for mechanical packages | For Crude Oil pumping system, 24VDC supply is used for control and DC motor, due the distance and voltage resulted in big size cables and new junctions were added to accommodate the cables. |  | For other mechanical packages use of 24V DC for control and drive to be evaluated. 110V DC shall be used in place of 24V DC to avoid bigger size of cables.
17 | CHN-ECLL-EL-0017 |  | Electrical | EL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Solar sizing calculations | Due to frequent changes in Instrumentation loads (some optimizations, some bid miss and some vendor induced), solar sizing calculations was revised several times, which delayed the finalization of system design, sizing of solar controller, batteries, cables and solar panels. In addition to this, equipment layout and solar deck layout were modified a few times (to accommodate the required number of solar panels and as per vendor recommendations), which resulted in changes in no. of junctions boxes, cable size, cable glands, distibution board and solar modules mounting structures. |  | Solar sizing calculation needs be done only after finalizing the instrumentation loads. Solar panel deck layouts need to be finalized only after the sizing calculations are complete. The orientation of the solar panels is directly related to the location of the offshore facility, and this orientation needs to be clearly communicated by electrical engineers to the layout team without waiting for vendor inputs
18 | CHN-ECLL-EL-0018 |  | Electrical | EL | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Late finalization of Architectural vendor and scope causing rework in design efforts | The selected architectural vendor came up with a Sewage treatment plant which required 240V AC power, when the requirement was for a biological STP which required no electricity. It took time and efforts from engineering to zero in on the type of Macerator, and there were further delays from the vendor in finalizing the toilet / toilet support details. |  | Proper TBE of the architectural sub-contract needs to be done and client requirements need to be clearly spelt out to the sub-contractor prior to placement of order.
19 | CHN-ECLL-EL-0019 |  | Electrical | EL | D6071 ¦ QP Bul Hanine | Qatar Petroleum |  | ECLL |  |  |  | Design of IT earthing system | This project had a unique power distribution with IT system earthing for offshore. This system though used in offshore for small load like lighting, but not used for power supply system exceeding 230 Volts. This IT Earthing system was implemented to increase the availability of the plant power. Such system do not trip under first fault and hence rectification can wait till the second fault thus providing ample time for trouble shooting and rectification. However, this system has large limitation for system having large charging current in the network due to subsea cable. This system needs special consideration while bidding. Even though IT earthing system was recommended as per FEED, there was no detail design done of the same. Feasibility study regarding the IT system design and associated constraints were addressed in TQ but withdrawn during face to face meeting with client. The equipment referred during FEED for IT system were mostly obsolete and not compatible for the Project scope. FEED endorsement missed to evaluate the same due to limited offers form vendor and limited bid budget. | - Lack of proper FEED documents. - Withdrawal of qualification (with COMPANY), without technical or commercial assessment. - Missed during FEED endorsement | It is recommended to evaluate / qualify such critical design aspects during FEED endorsement stage so that these could be pursued further as variations to COMPANY during detail engineering.
20 | CHN-ECLL-EL-0020 |  | Electrical | EL | D6071 ¦ QP Bul Hanine | Qatar Petroleum |  | ECLL |  |  |  | Addition of Emergency Light fixtures in Escape Route. | QP Bulhanine project wellheads were conceptualized with minimum topside facilities and minimum lights. The project had 4 well heads and one manifold tower. Aspect of escape route Lighting was ignored in Feed . ITT scope of work did not mention any requirement of outdoor Emergency light fixtures. However, this turned out to be violation of QP Safety Philosophy. Engineering Safety did not highlight this requirement in feed verification. During project execution (during SAFOP workshop), it was recommended to install Emergency light fixtures on escape routes. | - Poor FEED design from FEED CONTRACTOR - Lack of engineering evaluation on aspect of emergency lighting for wellheads and manifold tower. | It is recommended to raise such discrepancies during bid clarifications or include in PROM register as potential variation during execution.
21 | CHN-ECLL-EL-0021 |  | Electrical | EL | D6071 ¦ QP Bul Hanine | Qatar Petroleum |  | ECLL |  |  |  | Utilization of Modular supports | For Bulhanine project, the brownfield strategy was to use existing support based on ITT drawings to the extent possible. During execution, per Hook-up requirements for flexibility of installation), modular supports were utilized. There was a change in strategy during execution, which lead to increase in cost and engineering man-hours. | Inappropriate assessment of Brownfield work and lack of strategy discussion with hook-up team. | It is essential during bid to evaluate such requirements. Coordination shall be done with Hook-up team during bid to ensure proper estimation of installation requirements.
22 | CHN-ECLL-EL-0022 |  | Electrical | EL | D6071 ¦ QP Bul Hanine | Qatar Petroleum |  | ECLL |  |  |  | Estimation of Power System Study scope | For Electrical Power system study, COMPANY initially accepted inhouse study. However, subsequently, client in the TQ clarified that a third party study must be considered for Electrical power system study work. Due to time constraint, It was not possible to obtain quotation due to time constraints from third party specifically when client required third party study. During bid it is a general practice to estimate the cost for Power System Study with reference from previous projects with some cost adjustment factors. Engineering inputs were furnished to Subcontracts team, However, these references were not interpreted aptly. So, the cost estimated for Electrical Power system study work was not adequate. | Lack of time due to changing requirement from COMPANY and inability to get firm vendor quote. Communication gap between engineering team and subcontracts team resulted in to inadequate cost estimation for this work. | During bidding, It is advisable to obtain vendor quote for Electrical power system study work in case COMPANY mandates to have this performed from third party. COMPANY approval also to be sought on approved vendors for this study work. If it is estimated based on in-house data, it is recommended to highlight project risk to Bid manager, P&E team and appropriately cover this aspect in PROM register.
23 | CHN-ECLL-EL-0023 |  | Electrical | EL | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | Modification of PMS scope | Modification scope for PMS was not evaluated properly during Bid under the assumption that COMPANY shall upgrade PMS (on NFB complex) considering future facilities such as PRQ1 and other facilities for NFPS I1P1 scope. This assumption was made because COMPANY was upgrading PMS during NFPS I1P1 FEED, and this was captured as a part of site survey. Hence, the MR was also not issued to vendor for PMS integration work during bid. The above assumption was not having enough basis to exclude the cost of PMS integration work. | - Assumption was made that PMS integration work would have been carried out by COMPANY for future facilities and projects. - No clarification was raised to COMPANY during FEED or Bid to validate this assumption. - Non-issuance of MR to vendor for pricing. - No PROM strategy during bid on PMS integration. | - Brownfield integration work is always tricky and any miss may turn in to very expensive affair during execution. Hence, all assumptions on Brownfield integration must be agreed with COMPANY during bid. - It is always possible that single source vendor may increase price during execution under any pretext, hence appropriate PROM strategy must be in place or Pre-bid agreements must be in place during bid to deal with this risk. - BEM must ensure that Single source packages (also including packages requiring Brownfield Integration) are dealt during PROM reviews and Cost reviews.
24 | CHN-ECLL-EL-0024 |  | Electrical | EL | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | Costing of Navaids | During bidding, Permanent Navaid MR was issued and TBE was performed. However, during internal engineering review, it was noticed that 6 numbers of temporary Navaid Lanterns were missed for 5 numbers of jackets. Hence, 10 numbers of temporary lanterns were added as a part of DELTA MTO report. DELTA MTO report was issued to capture impact in MTO due to receipt of last minute tender bulletins from COMPANY. Temporary Navaids were given a price reference based on execution ARAMCO project. However, during EPCI, it was found that there was a cost escalation in the range of 350 K US$ for this package. | - SCM did not pick the correct PO reference given by engineering. Only half price was considered by SCM than suggested by engineering (based on PO reference given by engineering). - Unit rate for Permanent navaids were also neglected by SCM while pricing. - During cost reviews, this item was not discussed as temporary navaids were considered as small cost item package and the cost escalation was not expected in the range of 350 K US$. - Vendor escalated the cost of Permanent Navaids during execution, under the pretext of increased efforts to integrate Navaids systems of new platforms with existing platforms. | - For future bids, Considering NAVAIDs are safety critical item, it is highly recommended to issue MR for temporary NAVAIDs as well and price them based on vendor quotations. - Do not miss temporary lanterns on Jackets. - Ensure correct pricing of all Navaid items during bidding. Particularly, on Brownfield Platforms, cost escalation from existing vendor is expected as Navaid package may need an integration of new systems with existing systems. Hence, this aspect also must not be missed during future bids.
25 | CHN-ECLL-EL-0025 |  | Electrical | EL | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | Cyber Security Requirements for ECMS | Bid estimation was not done based on the latest ECMS architecture diagram. The ECMS MR was not lacking any item regarding to CYBERSECURITY requirements as latest drawing and spec was already included as a part of ECMS MR. Vendor did not raise any deviation during Bid. But Vendor came back with additional cost stating that they missed pricing on CYBERSECURITY requirements. | - Vendor did not raise any deviation on CYBERSECURITY requirements. | - CYBERSECURITY is a specialized subject nowadays and very critically reviewed by clients due CYBERSECURITY related threats. This aspect must be dealt specifically during Bid review to check whether CYBERSECURITY requirements have been dealt or not. Specific confirmations must be obtained from vendor during bidding. - It is always possible that single source vendor may increase price during execution under any pretext, hence appropriate PROM strategy must be in place or Pre-bid agreements must be in place during bid to deal with this risk. - BEM must ensure that Single source packages (also including packages requiring Brownfield Integration) are dealt during PROM reviews and Cost reviews.
26 | CHN-ECLL-EL-0026 |  | Electrical | EL | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | Missing quantity of Electrical Cable Trays | It was noticed during project execution that Tray quantities estimated during bid, were less and inadequate to execute project scope. Electrical Bulk MTO (Rev A) was issued to SCM for pricing during bid, which was predominantly based on FEED executed by McDermott. However, Electrical MTO (Rev B) was received very late (due to tender bulletins and other developments), and it was not possible to issue this MTO to SCM again so that they can go to vendors for pricing of entire MTO again due to deadline pressure. Hence, it was agreed with SCM, P&E team that engineering will furnish DELTA MTO to estimation team (not to SCM as there was no time to go to vendors for pricing). Rev B of Electrical MTO was having much higher quantity for Electrical Trays than Rev A of Electrical MTO. While issuing DELTA MTO, this additional quantity was missed by bidding engineers | - Bidding Engineers overlooked the quantity of trays, while preparing DELTA MTO. | - BEM must ensure that all DMs verify the MTO quantity and owns the MTOs. Record notes must be retained for the same. - BEM must ensure that review and benchmarking work from DMs are in schedule and man-hours are allocated for the same. - FEED MTO can be utilized to get vendor quotes but final MTO must be thoroughly checked by Lead engineers prior to issuance to other functions. - BEM to ensure that final MTOs are issued to Other functions such as HUC, Fabrication, QA/QC , SCM, P&E etc..
27 | CHN-ECLL-EL-0027 |  | Electrical | EL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Gaps in Lighting study | Lux test done revealed that certain shadow areas had less than acceptable illumination; hence, this led to late stage addition of three numbers lighting fixtures / with supports, cabling etc. |  | Awareness to engineers on the limitations of lighting software / check list to add extra lights to address this issue at design stage itself. TQA to address such issues
28 | CHN-ECLL-EL-0028 |  | Electrical | EL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Junction boxes design without adequate breather / drains | During VDR of electrical JB, we have missed out the requirement of breather / drain in certain cases |  | Have better awareness / check list to address these aspects
29 | CHN-ECLL-EL-0029 |  | Electrical | EL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Battery Drain Drum requirement for Alkaline Batteries | Battery drain drum with Neutralizing Tank was not considered in the design |  | If Nickel Cadmium Batteries are used in the project, raise a TQ on battery drain drum / neutralizing tank requirement to Company during early stages of the project to have clarity on Company's requirements.
30 | CHN-ECLL-EL-0030 |  | Electrical | EL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Deliverable Schedule | AFC deliverables such as Load List, Cable sizing, Support drawings, Ladder Lyouts & Cable routing were all scheduled to be issued before vendor data receival/ 60% design review. |  | Proper planning of deliverable dates against project milestones
31 | CHN-ECLL-EL-0031 |  | Electrical | EL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Design Review & Model review man hours | the CTR for model/design reviews was only 33 hours. 30/60/90% reviews turned out to be 5 days each. |  | appropriate manhours to be considered in future projects
32 | CHN-ECLL-EL-0032 |  | Electrical | EL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | More offhsore survey time to be considered | The lack of existing drawings resulted in the need for additional site surveys to gather information. |  | Complex brownfield projects with limited existing drawings should allow for more site survey man hours.
33 | CHN-ECLL-EL-0033 |  | Electrical | EL | D6847 ¦ Hasbah | Saudi Aramco |  | ECLL |  |  |  | Increased Number of Lighting Fixtures per PDM | Basis for PDM design was considering the same as unmanned. The Feed contractor estimated platform lighting considering open platform area without obstruction factored in. Lighting Calculation re-verification was not carried out during the bid stage. Only quantity was calculated from FEED Lighting layout for cost estimation. Number of lighting fixtures in the IFC package was insufficient to meet Lux requirements as per Aramco standards (SAES-P-123) | Additional lights were procured to meet SEAS requirements (increase from approx. 70 light fixtures to 160 light fixtures per PDM). | Recommendation is to re-validate the lighting calculation during Bid stage. It is worthful to consider benchmarking of the number of Light fixture for SS standard SSS design. Instead of relying on ITT /FEED documents, Number of light fixtures can be benchmarked with different type of PDMs.
34 | CHN-ECLL-EL-0034 |  | Electrical | EL | D6847 ¦ Hasbah | Saudi Aramco |  | ECLL |  |  |  | Classification of SMART Drawings | Drawings Directly extracted from model (like structural support drawings and isometrics) have been classified historically as Smart Drawings as per MDR. However SAPMT pointed out that as per SAES-A-202 and SAEP-334 smart drawings are only SPI, SPPID and SPEL. Structural drawings and isometrics should not be categorized as smart. | Lack of awareness on EKRD procedures and SA standards on documentation (SAEP-334 and SAES-A-202). | MDR to emphasize and make sure all Engineers are aware and is updated on latest iplant requirements and are familiar with all applicable SA standards
35 | CHN-ECLL-EL-0035 |  | Electrical | EL | D7018 ¦ SAF Phase8 | Saudi Aramco |  | ECLL |  |  |  | Subsea cable size optimisation | ITT/FEED package requires 4 different cable sizes with 1 km spare cable for each size. Bid basis was considered only two sizes (higher ones) to avoid 2 km of spare cable. However, cost analysis was not done if increase in cable sizes cost can offset the saving due to 2 km spare cable. Furthermore, nothing was included in PROM to alert the EPC execution team of this approach. During EPC execution, 4 cable sizes were provided as above approach didn't bring any cost benefit and also not accepted by Company. | Deviation to contract requirement was not included in PROM. Economic analysis was not done to asses if this approach will bring cost benefit. | Any deviation to project scope/strategy, must be suitably included in PROM with appropriate cost allocation against it as there are very high possibility of rejection from COMPANY.
36 | CHN-ECLL-EL-0036 |  | Electrical | EL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | E&I supports | Excessive Vibration in E&I supports This issue keeps happening in many projects leading to late stage mods at site |  | Explore and fine tune MDR support standards to mitigate this recurring issue
37 | CHN-ECLL-EL-0037 |  | Electrical | EL | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | E&I design deliverables accuracy | Late changes seen in certain E&I design deliverables with regards to consistency with vendor data / package vendor scope; this led to some late stage cabling and yard rework |  | Better quality of checking and also checklist to ensure 100% consistency check attained Final AFC drawings

## Instrumentation
Serial No | LL Number | Date | Discipline | DC | Project Name | Client | Facility category | LL category | Subject1 | Subject2 | Subject3 | Title | Background | Root cause | Corrective action | Preparer | Preparer Desn | Reviewer | Reviewer Desgn | Approver | Approver Desgn
1 | CHN-ECLL-IN-0001 |  | Instrumentation | IN | D5773 ¦ ONGC | ONGC |  | ECLL |  |  | Interfaces / Battery limits | Transmitter height | Slope requirements were not met in the drawings in many areas on the impulse tubing between transmitters and piping tapping points. Instrument stand heights had to be increased. |  | Sufficient allowance (approx. 100mm) in the sintrument handle may be considered while finalizing the transmitter height in order to cater for slope requirements.
2 | CHN-ECLL-IN-0002 |  | Instrumentation | IN | D5773 ¦ ONGC | ONGC |  | ECLL |  |  |  | Path lose calculation for the radio signals | Path loose calcualtion for the radio was perfomed without considering roll,. Pitch and heave fo the FPSO & also it was perfomed by the vendor towars the end of the Project. Hene the mounting height requirement for radio was changed Additional power requirement was notified by the venodor which resulted in change in solar system sizing and also changes in Layout. |  | The radio dispression study needs to be perfomed condifering all the movment of the FPSO and also this needs to be done at a early stage of the project.
3 | CHN-ECLL-IN-0003 |  | Instrumentation | IN | D5773 ¦ ONGC | ONGC |  | ECLL |  |  |  | Entry points for the cables and tubes of the shutdown panles | Entry points for the cables and tubes of the shutdown panles The area should have been frozen until the panel entry was not finalised. |  | The area should have been frozen until the panel entry was not finalised and this needs to be confimed during early Engineering phase.
4 | CHN-ECLL-IN-0004 |  | Instrumentation | IN | D5773 ¦ ONGC | ONGC |  | ECLL |  |  |  | Control Valve | Control valve postioner , spare cable entry are pluged with certified plugs |  | This needs to captured in the specification
5 | CHN-ECLL-IN-0005 |  | Instrumentation | IN | D5773 ¦ ONGC | ONGC |  | ECLL |  |  | Codes and standards | Control system | Duct sizing , segeration , spacing , earthing of signal sheild etc was - vendor not following standards Engineering pratices |  | This needs to be confirmed during the early stage of Engineering
6 | CHN-ECLL-IN-0006 |  | Instrumentation | IN | D5773 ¦ ONGC | ONGC |  | ECLL |  |  |  | Entry points for cables in RTU. | Insufficuent space between the wire duct and wire terminals |  | This needs to be taken care during design stage of the panels .
7 | CHN-ECLL-IN-0007 |  | Instrumentation | IN | D5773 ¦ ONGC | ONGC |  | ECLL |  |  |  | Flame Arrestor and Sight Glass. | Flame Arrestor and Sight Glass covered neither by Piping nor by Instrumentation during bid estimates |  | Which discipline needs to do the procurement engineering for these items is to be decided by engineering management.
8 | CHN-ECLL-IN-0008 |  | Instrumentation | IN | D5773 ¦ ONGC | ONGC |  | ECLL |  |  |  | X- ray requirment for relief valves & senior orifice assembly | X -ray requirement of clinet was not followed by Vendor . |  | This requiremnt needs to be captured in the ITR.
9 | CHN-ECLL-IN-0009 |  | Instrumentation | IN | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | DCS requirements specified by PEMEX | Lack of understanding on DCS Control requirements in the bid, could have major impact (Ambiguities were not cleared in the bid engineering). |  | Specification / Clear scope for Control Systems to be finalized and clarified with client during Bid stage. Especially I/O counts and interface with other platforms / facilities to be identified. In case of not sufficient information being made available by client, appropriate qualifications to be done during bid submission.
10 | CHN-ECLL-IN-0010 |  | Instrumentation | IN | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Cable and Cable Tray Vs Conduits and Wires | Usage of cables against conduits – concerns on Productivity and Cost. Review took place in the later stages of the project. |  | Cost Benefit Analysis to be performed in early stage in Engineering considering all aspects l;ike Material cost, Fab Man-Hours, etc and decide on philosophy for Cable Tray or Conduits with wire.
11 | CHN-ECLL-IN-0011 |  | Instrumentation | IN | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Junction Box | Lack of inputs & clarity on PVC coating on Junction boxes from PEMEX. |  | Specification / requirements for JB to be finalized and clarified with client during Bid stage. For all Pemex projects, PVC coating should be considered default.
12 | CHN-ECLL-IN-0012 |  | Instrumentation | IN | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Instrumentation Definition | Less Definition on Instrumentation requirements from PEMEX like Hook-up etc. |  | Specification / Hook-up details to be finalized and clarified with client during Bid stage.
13 | CHN-ECLL-IN-0013 |  | Instrumentation | IN | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Conduits & Wires | Mexican Vendors are not well verse with Cables & tray. Interfacing was an issue with packages. Their design is based on Conduits & wires |  | More clarity is required in KOM and design issues related to Cable & glands to be communicated to Vendor at early stages
14 | CHN-ECLL-IN-0014 |  | Instrumentation | IN | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Multiple contractors for Building/HVAC scope | In spite of repeated requests from Engineering to have a EPC type subcontract for buildings, decision was taken to split the building scope into multiple subcontracts with building related engineering being a separate contract. This led to a lot of confusion for the production engineers/ document controllers and review engineers as 1. Engineering contractor was not willing to incorporate the vendor data in their design as it came too late because of late placement of vendor PO's. 2. We had multiple sets of drawings for the same scope from Engineering contractor and from the installation contractor (with same drawing numbers in some cases). Strategy for HVAC design & modeling was included in the Engineering contractor who was not well versed with HVAC modelling and had been using third party resources to do this. This led to a lot of delays and engineering was forced to model the ducts in 3D model to provide a clash free design of cable trays and tray supports to the yard. |  | Follow EPC type of subcontract for buildings and release the subcontract early on in the project for engineering to be able to obtain the necessary vendor data / comprehensive 3D model(s) from the EPC contractor. Identify the subcontract manager for this scope (preferably from the production engineering side), come out with a single scope split matrix and execute the subcontract as per the scope split matrix and avoid dealing with multiple agencies.
15 | CHN-ECLL-IN-0015 |  | Instrumentation | IN | D6071 ¦ QP Bul Hanine | Qatar Petroleum |  | ECLL |  |  |  | Corrosion Probes and Transmitter issues | 1. Late change of Corrosion Probe locations due to failed criteria of Wave frequency calculations led to delays in Fabrication. 2. Missed Hollow Plugs in Piping PR, though highlighted in Instrument PO that these will be purchased part of Piping. 3.Mismatch in Corrosion Probe and Access Fittings | 1. Corrosion Probe and Transmitter MR's delayed due to delays in finalizing the communication type and also they were categorized as Non-critical. 2. Instrumentation PO indicated that Hollow Plugs will be purchased by Piping, however this requirement was not communicated explicitly with Piping. 3. Piping team followed the access fitting design as per GA document provided by Vendor; However, vendor changed the access fitting requirement when submitted the GA drawing for Probes. Access fitting GA by Piping shows direct installation of access fitting on Tee; however vendor drawing submitted part of Probes shown access fitting installation on Weldolet (SNAP C). Vendor did not follow the tee arrangement, which was basis for pipe fabrication. Due to this issue, the probe insertion length became higher then required. | 1. Corrosion probes shall be prioritized considering the interface with other disciplines. 2. Instrumentation need to take confirmation from Piping that required material is not missed and purchased inline with design requirement. 3. Interdisciplinary coordination shall be maintained for packages where multiple disciplines involved. Instrumentation shall forward the access fitting information to Piping for their review. 4. Recommend Instrumentation to take control of the total package including access fittings, Probes and Transmitters
16 | CHN-ECLL-IN-0016 |  | Instrumentation | IN | D6071 ¦ QP Bul Hanine | Qatar Petroleum |  | ECLL |  |  |  | Redundant Communication between RTU (Yokogawa) and MPFM (Schlumberger) | Schlumberger MPFM has Simplex Ethernet Port, however Project required to have redundancy in communication with Yokogawa RTU. | Redundant communication requirements were missed during TBE. Even though Vendor agreed to add MOXA switch after the PO placement, Simplex Ethernet port in MPFM allows only Single IP address. | If Redundant port is not available then it shall be highlighted during TBE stage and required approval shall be taken from Company.
17 | CHN-ECLL-IN-0017 |  | Instrumentation | IN | D6071 ¦ QP Bul Hanine | Qatar Petroleum |  | ECLL |  |  |  | Foundation Fieldbus based Local Controller Limitations | FF based Local Controller was used for controlling the Hydraulic Choke Valve including the SOVs and Position Transmitters. However the FF based Local Controller provided only 2 function blocks ( AI and AO signals) and not able to provide diagnostic information for its sub components like SOVs, Position transmitter etc. | Product limitations and unable to provide diagnostic information to the control system. | Foundation Fieldbus based Local Controllers shall be avoided by shifting the choke valve Logic to DCS/RTU and there by eliminating additional failure point.
18 | CHN-ECLL-IN-0018 |  | Instrumentation | IN | D6071 ¦ QP Bul Hanine | Qatar Petroleum |  | ECLL |  |  |  | SIL Assessment & Verification issues of Final Control Elements | FEED SIL report identified SIL-2 rated Loops with one imitator and multiple Final Control Elements, however during EPC phase the same configuration could not achieve the SIL-2 requirement. SIL-2 requirement for Actuated Valves & its Actuators specified in the Datasheet, Vendor provided PFD data, which met SIL-2 for the Actuators, however the overall loop could not achieve SIL-2. | Lack of Verification / Validation during the FEED. Vendors were unable to provide better PFD data for Actuators with single SOV. | Review the Feed SIL study recommendations specifically for Loops >= SIL-2 and ensure PFD / RRF data obtained from the Vendors. In case if no data available from FEED / ITT, PROM shall be included for cost increase during EPC stage.
19 | CHN-ECLL-IN-0019 |  | Instrumentation | IN | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | I/O segregation | Based on FEED documents, It was required to have I/O segregation in control systems. Based on site survey during execution, vendor proposed for combining the I/O's, and same was accepted by us after seeking approval from ADMA site engineer. PO was placed based on agreement reached during site survey. This was a change in I/O assignment philosophy, and the was not accepted by ADMA DED/PMT later on. This had a significant impact on overall engineering schedule and overall vendor cost as this led to change order from vendor during execution. | Engineering placed PO without considering I/O segregation requirements, which as a contract requirement from COMPANY. This was considered based on site survey agreement reached with ADMA site engineer. However, this agreement was not regularized with ADMA DED or ADMA PMT through a deviation request. | Client site representatives are not the correct guys to seek approval on major philosophy related deviations. Site surveys are intended to register site findings, and Approval of critical decisions (change in overall philosophy) must be regularized with COMPANY PMT team through technical deviation request or by other means. In case of any kind of schedule urgency, decision must be taken after conducting risk assessment with Project PMT and Engineering PMT.
20 | CHN-ECLL-IN-0020 |  | Instrumentation | IN | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | Customized protocols limiting Soft I/O's - Brownfield engineering | As a part of project scope, communication through soft link was envisaged from RTU to SCADA. It was assumed by engineering team that standard DNP3 protocol shall be utilized for communication between inter system communications such as RTU and SCADA. However, during execution (before FAT), Vendor (Weatherford) informed CONTRACTOR that COMPANY is not using standard DNP3 protocol (which allows 2048 I/O points to be communicated between RTU and SCADA) but COMPANY utilized customized DNP3 protocol which has limitation on number of soft I/Os (Approximately 646 points only) to be communicated between systems. Engineering design was based on standard DNP3 protocol, which was required to be changed to meet customized DNP3 protocol requirements. There was no communication received on COMPANY customized DNP3 protocol requirement during bid or during EPCI execution. This led to re-work on soft I/Os with vendor and re-work of engineering deliverables at CONTRACTOR end. | Client had customized the standard DNP3 protocol that was neither mentioned in the ITT nor informed to CONTRACTOR post award. Even during execution, vendor was not asked for any kind of limitations with respect to Protocol or communication with third party devices. This aspect was missed during engineering. | Integration issues between third party systems have been observed as a recurring issue in executed projects. It is advised to raise a clarification during the bidding stage to know the , the customizations by COMPANY or limitations of existing networks / protocols / Software tag limitations / software expiry dates etc.. More attention to be paid to software limitations or communication limitations considering interface among third party devices. During the FEED verification stage, the above mentioned aspect must be thoroughly reviewed and must be clarified with vendors if required. During technical evaluation, enough attention must be given to ensure trouble free integration of 3rd party equipment. During execution, intersystem issues can have detrimental impact on project cost (it can run in to 0.5 M US$ to 1M US$) and overall project schedule
21 | CHN-ECLL-IN-0021 |  | Instrumentation | IN | D6221 ¦ ADMA | ADMA |  | ECLL |  |  |  | Brownfield Site surveys | Project requirements were kept changing post Site survey (Stick built ITT design to Modular design) on ZK-300 and ZK-GIP platforms. These changes were not verified with site data as there were no site surveys planned by Engineering. Late arrival of cladding and fire proofing information resulted in to redesign of the cable trays / supports. During construction campaign at ZK-GIP, Existing cable trays found with enough spare loading space, that was not identified during Site surveys. | Change of HUC Managers lead to considerable re-work as decisions made on Instrument tie-ins by the earlier HUC Manager were changed from Site-run to Engineering design. Pre-engineering site surveys were carried out at early stages based on the ITT design. Also, due to VISA limitations, designer who is not familiar with complete scope was used for site survey and the time duration required on each platform was not studied fully and there no preparedness. cable tray spare loading capacity was not verified and Site survey reports were not prepared immediately after the survey. | Multiple Site surveys recommended for any conceptual changes done post pre-engineering survey in complex brownfield scopes, In this particular instance, Stick-built ITT design was changed to Modular post award and after pre-engineering surveys on ZK-300 and ZK-GIP platforms. Site survey reports to be prepared immediately after the survey capturing the images, redline mark-ups and other necessary details. Readiness meeting shall be conducted to discuss the duration required, extent of scope, checklists availability, etc. as this may vary from discipline to discipline.
22 | CHN-ECLL-IN-0022 |  | Instrumentation | IN | D6803 ¦ RasGas FAXP | Qatar Gas |  | ECLL |  |  |  | Schedule impact due to delays in Reservation Change Requests to COMPANY | Reservation change requests were planned at a later stage of the project and thus delayed firming up the control system scope. PO's were issued without RCR approvals and Design deliverables were prepared based on vendor data received. Site surveys were conducted in Oct-Nov'15, however RCR's were planned in March 2016. Client made few changes during the RCR approval's and that lead to change in SOW for Control system vendors. Considerable delays (6-8 weeks) in issuing the design deliverables including re-work and PO amendments . | Instrumentation deliverable dates and the predecessor, successor linkages were not assessed / reviewed in the Schedule. | Schedule for Reservation Change Requests shall be reviewed during schedule review exercise. RCR shall be issued immediately after site survey so that approved RCRs are available prior to PO Placement. This will ensure schedule certainty and reduce the risk of change orders from vendors. In case POs must be placed prior to RCR approval, it is strongly recommended to conduct risk assessment with engineering PMT and project PMT prior to PO Placement. All decisions must be recorded for future use.
23 | CHN-ECLL-IN-0023 |  | Instrumentation | IN | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | Execution phasing of Instrumented Systems Package | ICSS package vendor came up with additional costs during EPC to account for additional testing/staging as delivery of the packages was split into two phases (2 brownfield and one Greenfield scope). The additional costs had to be agreed as the vendor was COMPANY nominated with little room for hard negotiations. The need for separate FAT was covered in MR documents, but vendor advised that this was not considered for costing. | Single source vendor assessments during bid | 1. Be extra cautious with nominated/single source vendors as room for negotiations will be limited. 2. Cost escalation during EPC is generally observed from single source vendors. Hence, it is highly recommended to include PROM on single source vendors by BEM. Practically, vendors can give any arbitrary reasons to increase price. For example, they had not considered price escalation due to depreciation of currency or their price was only valid for the year of bidding etc. 3. BEM must agree strategy with SCM , Bid PM to effectively handle single source vendors and must document for future records.
24 | CHN-ECLL-IN-0024 |  | Instrumentation | IN | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | Cost of Magnetic Level Gauges & Transmitters | During Bidding, Magnetic Level Gauge & transmitter were priced based on PO reference from one of the executed projects. Per Engineering PO reference, Magnetic LG and LTs were having unit cost of 21.5 K US$, but SCM considered pricing close to 6K US$ . | - Engineering PO references were not considered by SCM during pricing. | - Big ticket packages, which are priced based on PO references, must be reviewed critically during cost reviews. BEM and Procurement coordinator must ensure that engineering price references have been priced correctly. - Engineering must ask for priced POs in case cost inputs are required from SCM. SCM shall furnish priced POs based on revised procedure agreed with SCM.
25 | CHN-ECLL-IN-0025 |  | Instrumentation | IN | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | Cost of Flow Nozzles and Venturis | During Bidding, MR was raised to SCM to obtain vendor offers for Alloy 625 cladded Flow Nozzles and Venturis. SCM failed to give any vendor offer during Bid. Engineering was requested by SCM to help in pricing based on recent bids / execution projects. Since the bid deadline was approaching, Engineering gave a pricing inputs with technical adjustment factors, based on ARAMCO HASBAH bid for Alloy 625 cladded Venturi. SCM did not validate this price and simply priced based on engineering inputs. During execution, cost escalation was found in the range of 200K - 250 K for Flow nozzles & venturis | - Engineering suggested cost inputs in the absence of firm vendor offers based on SCM's request. - Cost escalation was observed after bidding for Alloy 625 pricing. - No PROM was considered specifically for this package, only general PROM was considered for material growth. | - Engineering should refrain from giving cost inputs in the absence of vendor offers. SCM must price these items. Alloy 625 is an exotic material and price varies a lot every year, hence, Engineering must not give pricing inputs to SCM for such big ticket cost items. - If Bid manager advises bid team to give price reference, then PROM inputs to address risk of cost increase during execution must be considered during bidding for the same. BEM to endure appropriate package specific PROM strategy. - Use the pricing reference from executed projects, not from Bids. Pricing from other bids, may be erroneous and can lead to cost escalation during execution.
26 | CHN-ECLL-IN-0026 |  | Instrumentation | IN | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | E&I Brownfield design modification to reduce offshore work. | Further optimisation activities were done on the FEED design to reduce offshore hook-up work. |  | For brownfield, early during detail engineering, an optimisation exercise must be done to identify all possibilities where count of offshore cables & equipment installation can be reduced. This activity must be completed before start of deliverables issue & MTO activity.
27 | CHN-ECLL-IN-0027 |  | Instrumentation | IN | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Base scope Deviation list | During the base scope deviation/exception list with remarks were accepted and attached in the Purchase requisition. As per the amended scope instruction, NO DEVIATION LIST has to be enclosed in the PR. Any deviation/exception stated even with MACL remark is not accepted. For retagging of the base scope supplied instruments, PR was issued to all base scope vendor. However, few vendors (CCTV- TRIZAC, Pressure regulator - Emerson) are not agreed to provide NO DEVIATION list . |  | For all similar brown field projects, it is recommended to obtain the blanket NO DEVIATION LIST from vendor to avoid Client rejection in later stage.
28 | CHN-ECLL-IN-0028 |  | Instrumentation | IN | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Frequent revisions of block diagram | During the brownfield scope execution, the cable block diagrams were revised many times due to the following activities: a. Addition of telecom cabinet to reduce offshore work (optimisation) b. Addition of brownfield JBs to reduce offshore hook-up activities (optimisation) c. Addition of brownfield F & G detectors d. Change in cable size after receipt of vendor data. e. Fieldbus segment sizing This caused frequent revisions in MTO & all other brownfield & greenfield deliverables. |  | Very close & frequent co-ordination needs to be maintained to ensure that the many revisions were properly captured across all affected deliverables and that the correct MTO was ordered.
29 | CHN-ECLL-IN-0029 |  | Instrumentation | IN | D6255 ¦ LTA II | Saudi Aramco |  | ECLL |  |  |  | Interface issues between valve, actuator, control panels and ESD | SSIVs: Interface issues were found among valve, actuator, control panels and ESD hydraulic panel for the SSIVs. During SAT, there were many issues related to interface found, which should have been dealt with during detailed engineering phase. | - Lack of plan to manage interfaces among different supplier during detailed engineering. - Lack of coordination with vendors - Lack of in-depth vendor drawing review | Site Acceptance Test(SAT) to be included in the PO from the initial stage as a part actuator vendor scope. Develop a clear interface matrix for the subsea valve package and identify the interdependencies. Review it throughout the VDR/ FAT /SAT process.
30 | CHN-ECLL-IN-0030 |  | Instrumentation | IN | D6255 ¦ LTA II | Saudi Aramco |  | ECLL |  |  |  | Instrument Tubing Design | During Pre-commissioning of TP-23 Platform of LTA-II, 30” Actuated Valve (ZV-1001) closing time was found 66 sec where as the Aramco standard (SAES-B-058, Clause 10.2) & Project Data sheet (RE-576266) mentioned 30sec. During factory acceptance test, valve closing time was recorded as 30.6 sec at factory test conditions (i.e. hydraulic power pack next to the valve), as against the site conditions of 69m away from the ESD Panel. | The additional delay of 36 seconds was found due to the reducers used inside the Partial Stroking Panel, Bends and turns in the long run of 69m Instrument Tube Routing and high swept volume of the ZV-1001- 30" Size. | Tube length, Tube size details shall be commented on the Vendor submitted drawings & FAT procedure. Port sizes and tubing component sizes along the complete hydraulic path shall be reviewed for free flow of the Hydraulic fluid. Tubing ID shall be kept uniform across the lines and restrictions/ reduced port sizes shall be eliminated. Vendor shall be requested to conduct the FAT replicating the site conditions (Not Factory conditions). Else, vendor shall recommend suitable testing set-up to replicate the closing/ opening time in installed conditions for higher size Valves. Vendor shall be requested to provide the closing time and pressure profile at the inlet/outlet of Actuators as part of sizing calculations, considering the tubing lengths and sizes.
31 | CHN-ECLL-IN-0031 |  | Instrumentation | IN | D6255 ¦ LTA II | Saudi Aramco |  | ECLL |  |  |  | MPFM Skid | For the MPFM skid, following were the major issues. 1. Schedule delays, Non-conformance of Skid material sourced from sub-vendors 2. Split PO's issued (one for meter, one for Skid) - which made more challenging to handle vendor interface issues. | Initially PO was placed on Schlumberger, Singapore for the MPFM Skid, however Schlumberger placed order for Skid to KSA Vendor "Abdullah Ak Shuwayer Sons Company, It was found at a late stage, that KSA Vendor didn't purchased Flanges and FBE coated Pipes, McDermott arranged Flanges, FBE lining Pipes and free-issued to KSA Vendor to meet Project schedule. | During TBE, Engineering shall ensure the compliance of Sub-vendor supplied equipment and request SCM to get the required back-up documentation.
32 | CHN-ECLL-IN-0032 |  | Instrumentation | IN | D6200 ¦ SAF 6 | Saudi Aramco |  | ECLL |  |  |  | Incorrect Wiring drawings of Corrosion Transmitters | During Offshore commissioning, Corrosion Transmitters were unable to Power on at PDMs SAF#34, SFNY#77, SFNY#544 and not communicating with RTU Terminal server or Service Engineer's Laptop. | The fault wiring caused the Voltage supply to the wrong terminals and damaged the Transmitters. | Designers shall ensure the correct terminals by referring to Manufacturers Installation manuals while preparing the Interconnection drawings. Onshore hook-up team shall verify the terminals and also test the communications in the Yard.
33 | CHN-ECLL-IN-0033 |  | Instrumentation | IN | D7057 ¦ MRJN TP10 | Saudi Aramco |  | ECLL |  |  |  | SPI Set-up | Delays in SPI set-up / Data sheets issue as the complete SPI database set-up has to be done during detail engineering. No SPI DB development done during the FEED and hence only the ISS formats given as input. This called for development of DB right from scratch and consumed additional manhours. | No SPI Seed files provided by Client, though ITT Bid Clarifications mentioned that the SPI seed files for instrumentation shall be given to successful CONTRACTOR.
34 | CHN-ECLL-IN-0034 |  | Instrumentation | IN | D7057 ¦ MRJN TP10 | Saudi Aramco |  | ECLL |  |  |  | Power Supply for Hydraulic Emergency shutdown System (HESD) | Power Supply for Hydraulic Emergency shutdown System (HESD) motors were specified as 24V DC powered with battery charger backup with an autonomy period of cold charging time of 65 minutes and re-charging time of 14 minutes. During EPC execution, the vendors were unable to meet the charging and re-charging design limits. | Vendors were unable to provide suitable 24VDC motors complying with required cold charging and re-charging design limits for Accumulators. | Hydraulic sizing calculations shall be verified and analyzed during the bid stage and also during the 90/120 days verification.
35 | CHN-ECLL-IN-0035 |  | Instrumentation | IN | D7057 ¦ MRJN TP10 | Saudi Aramco |  | ECLL |  |  |  | Instrument Cables Routing into Zone-1 areas | Instrument cables purchased in the Project were not in compliance with Zone-1 requirements as per SAES-J-902 Table-2B and NEC clause 501.10.d, where it specifies “corrugated steel tape” type Armor for zone-1 areas. | Instrument cables purchased are of PLTC type where as ITC type required for Zone-1 areas. | Designers shall verify the Zone-1 areas and select suitable cables of "Metal cladded" or conduits if cannot be avoided. Recurrence of this issue may prove costly for future projects.
36 | CHN-ECLL-IN-0036 |  | Instrumentation | IN | D7018 ¦ SAF Phase8 | Saudi Aramco |  | ECLL |  |  |  | Cost escalation for ESD system package | On Saf-8 PLC based ESD is required as per ITT instead of hydraulic type used in previous ARAMCO projects, during BID a provision of 30K for each ESD was added on top of reference price of the hydraulic type (SAF-6 based) without getting a quote from market. Also technical / commercial implications on other associated packages were not considered. In first round only one vendor provided technically acceptable quotation with amount 1.4M higher than the budget. This has impacted the cost of battery charger (+20K) (size increase) and Pressure transmitters (quantity increase) (+85K @ bid rate). | Reference pricing of package with non identical specifications. | Validate the ITT specifications for all Packages (Engg.) and based on that select appropriate projects or reference pricing ( Proc). If reference priced is to be considered, then PROM items should be appropriately added
37 | CHN-ECLL-IN-0037 |  | Instrumentation | IN | D6200 ¦ SAF 6 | Saudi Aramco |  | ECLL |  |  |  | Leak at offshore platform | In SAF-6 Project, It was noticed during offshore campaign that the hydraulic tubing connecting to x-tree valves (SSSV, SSV and WV) got unplugged because of x-tree vibration and lead into huge leak at the offshore. HUC team suggested to consider 250 mm well growth allowance in the engineering design. | - Excessive vibrations and inadequate design growth | - Apply 250 mm well growth allowance for future projects to avoid repetition of such issue. - During Bid, clarification to be obtained in case no clarity is available in ITT documents.
38 | CHN-ECLL-IN-0038 |  | Instrumentation | IN | D5773 ¦ ONGC | ONGC |  | ECLL |  |  |  | Flame Arrestor and Sight Glass. | Flame Arrestor and Sight Glass covered neither by Piping nor by Instrumentation during bid estimates |  | Which discipline needs to do the procurement engineering for these items is to be decided by engineering management.
39 | CHN-ECLL-IN-0039 |  | Instrumentation | IN | D7244 ¦ Belbazem FEED | Al Yasat Petroleum |  | ECLL |  |  |  | SIL workshop and impact of open points on engineering design | SIL Workshop was completed with certain basis agreed by all stakeholders including COMPANY representative, PMC, McDermott Process, HSE, Instrumentation and SIL Chairperson. However, Company has commented on SIL Workshop Report (through email, not on official report comment), for different data/basis/cases to be considered for SIL assessment at WHT e.g. occupancy factor, SIMOPS consideration, pig stuck scenario etc. This had impact on design and ended up in re-work and delay. | Few commented points were already highlighted by McDermott (Process team) during SIL Workshop, however all workshop participants agreed for Not to consider those points during assessment. These agreed points were not recorded in SIL Report, hence no written back of these discussions is available in report. | - Any basis or point discussed and agreed during workshop which may impact design later date shall be clearly registered in report for regularization. Appropriated reporting is highly recommended. Specially if any stringent case exempted from consideration, shall be clearly mentioned with reason to avoid any future comments or debate from any party including COMPANY.
40 | CHN-ECLL-IN-0040 |  | Instrumentation | IN | D7369 ¦ NASR 100 MBD | ADNOC |  | ECLL |  |  |  | Lack of clarity on scope of adequacy checks | Scope of work, received from COMPANY was vague on scope of adequacy studies during Pre-FEED (SELECT phase), with respect to level of detailing. For example, During execution ADNOC forced McDermott to perform adequacy checks on following items, which were not envisaged during bid. Detailed adequacy assessments (sizing checks) to control valves, relief valve, MPFM level were not envisaged to be performed during Pre-FEED. However, CONTRACTOR had to perform this as COMPANY wanted to assess instrument level adequacy checks. Adequacy checks for inline instruments were conducted for Onshore and offshore facilities as well. | - Lack of clarify on quantum of work with respect to adequacy checks during pre-FEED. - No qualification in bid regarding scope limit for adequacy checks | It is very important to add qualifications on aspects of adequacy checks as it can lead to significant increase in work. For example, it is very important to list down adequacy checks will be performed at equipment level or at instrument level as well. This aspect must be dealt with clarity with COMPANY during bidding to avoid misalignment. Be prepared to consider defining clear red lines (equipment level, not control valve level e.g.) but to reconsider in execution where justified.

## QAQC
Serial No | LL Number | Date | Discipline | DC | Project Name | Client | Facility category | LL category | Subject1 | Subject2 | Subject3 | Title | Background | Root cause | Corrective action | Preparer | Preparer Desn | Reviewer | Reviewer Desgn | Approver | Approver Desgn
1 | CHN-ECLL-QA-0001 |  | QA/QC | QA | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Hydrotest requirements | Actual Operating pressure was not considered while preparing the PMS & Line list which lead to pressure testing of open drain lines, however later the Operating pressure was revised and the hydro test requirements was revised to leak test since this was inline with SAES-L-150 para 5.9. |  | Suggested to consider the hydro test requirement while preparing PMS
2 | CHN-ECLL-QA-0002 |  | QA/QC | QA | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | NDE requirements not addressed fully in PMS | Consideration of service category w.r.t Radiographic requirement as specified in SAES-W-011 were not done as this leads to 100% RT for drain lines. Later the Piping class summary was revised in consideration to SAES-W-011 clause 17.5.2.2 & revised the MDMT and RT requirements were revised to 10% in line list. |  | Suggested to consider the NDE requirements while preparing PMS
3 | CHN-ECLL-QA-0003 |  | QA/QC | QA | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Non-AVL / Vendor location / Vendor name changes | SCM work practice not adequately addressing KJO AVL compliance / AVL location and also AVL vendor name change and this leads to delays in KJO approval of TBE, PR and PO. And wasted engineering efforts. |  | SCM to include this in their LL f0r KJO projects. KJO compliance of AVL much stringent than Aramco.
4 | CHN-ECLL-QA-0004 |  | QA/QC | QA | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Piping Top Color Coat | As per Base scope order the Piping Top coat color was finalized as yellow, however later after change order scope, there was an agreement with KJO to paint SS piping & tanks (exclude. Valves) and additional services like fresh water line & propane line got revised, hence the TOP coat color was not uniform(i.e. yellow) and as per TQ-020 with KJO, MACL contractually need to follow top coat color as per service fluid. This leads to change in color which got already painted in Base scope like Flare lines and also base scope procedure valves (which got painted in Yellow) were to be repainted with top coat color suitable to service fluid. |  | Suggested to document thru TQ or Waiver and to have detailed study (Cascading effect on other activities/disciplines) prior to agreement with COMPANY for any additional works.

## Subsea Pipeline
Serial No | LL Number | Date | Discipline | DC | Project Name | Client | Facility category | LL category | Subject1 | Subject2 | Subject3 | Title | Background | Root cause | Corrective action | Preparer | Preparer Desn | Reviewer | Reviewer Desgn | Approver | Approver Desgn
1 | CHN-ECLL-SP-0001 |  | Subsea / Pipeline | SP | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Re-inforcement Design of Crossing Sleepers | The crossing sleepers order was placed to ICC, Saudi Arabia. The re-inforcement design took much longer time than expected. |  | It is recommended to conduct the re-inforcement design in house by MACL to save time when selecting ICC, Saudi Arabia.
2 | CHN-ECLL-SP-0002 |  | Subsea / Pipeline | SP | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Requirement of ROV survey at the crossing locations | The initial crossing design was based on the exposed heights of the existing crossings obtained from geophysical survey and ROV survey could not be performed as part of the initial geophysical survey. ROV survey was performed at a later date which showed different results to geophysical survey results and re-design of crossings was required due to this. |  | ROV survey is recommended to be performed for all crossings as part of the geophysical survey to accurately design crossings.
3 | CHN-ECLL-SP-0003 |  | Subsea / Pipeline | SP | D6255 ¦ LTA II | Saudi Aramco |  | ECLL |  |  |  | The unstable seabed condition (marker pole) | For marker pole, ARAMCO ITT project scope specified for pile driven shallow water markers. However, during execution, project team decided to go for conventional gravity anchor based marker poles. While offshore installation, one off the marker pole fell down, which resulted in to extra marine efforts. | - Decision taken to utilize gravity based anchors without performing any engineering study by Project PMT. | 1) In case of deviation of ITT requirements or alternatives solutions, reasonable engineering should have been carried out accounting for location specific soil data and met ocean data, instead of following go-by or typical drawings. 2) Future engineering design of the marker pole must also finalized after performing stability analysis as to the prevailing soil conditions. The aspects like feasibility of provision of a mud mat or wider mud line base or the concrete base for additional stability must be explored during engineering.
4 | CHN-ECLL-SP-0004 |  | Subsea / Pipeline | SP | D6255 ¦ LTA II | Saudi Aramco |  | ECLL |  |  |  | The Piping Hook Up Riser clashing with bracing | The 24” Piping Hook Up Riser has to add pup piece to avoid clash with bracing due to actual jacket elevation is less than theoretical elevation | - Lack of constructability review - Lack of enough allowance to take care in variation in As-built jacket elevation. | The allowance of Hook Up piping has to suffice range of possible actual jacket elevation (range between the jacket is on maximum elevation case to minimum elevation case). Sufficient green shall be provided in hook up spools to take care of variation in As Built Jacket elevation. 3D model to have both riser and the topside piping fully modelled to scale. Review this as part of Constructability reviews, add this to the constructability checklist.
5 | CHN-ECLL-SP-0005 |  | Subsea / Pipeline | SP | D6255 ¦ LTA II | Saudi Aramco |  | ECLL |  |  |  | Concrete Sleeper Mix Design | In LTA-II & TP-10 projects, approval of concrete mix design was excessively delayed and hence made the pipeline lay activity on critical path. QC & COMPANY took a lot of time in verifying the concrete mix design, and vendors were not able to commence the production of sleepers, which resulted the same on on critical path for pipelay campaign. Few times, it was also noticed that vendor's poor track record in meeting COMPANY quality requirements is also a potential reason for delay in approval of design. | Unreasonable delay in approval / verification of concrete mix design and inappropriate vendor selection. | 1) Package Manager must be on top getting COMPANY approval (with interfacing with QC engineering) for concrete mix design. 2) Vendor's track records for past approval should be thoroughly verified prior as a part of TBE process and prior to PO Placement. Since this is a recurring issue in all projects, attention to be paid on delivery of concrete sleepers considering criticality of the need of sleepers on time for marine campaigns.
6 | CHN-ECLL-SP-0006 |  | Subsea / Pipeline | SP | D6463 ¦ SAF 5 | Saudi Aramco |  | ECLL |  |  |  | Incomplete datasheets for Sub-sea ball and check valves | During bid - In the technical datasheet of Sub-sea ball and check valves, key technical details were missing such as materials, design standards etc. Pricing of SSIVs were performed based on key missing technical details , which resulted in inaccurate pricing. No technical clarifications were raised to COMPANY during bid on missing technical details for SSIVs, which resulted in inaccurate pricing of SSIVs. During project execution, Engineering team was under pressure to meet the budget for sub-sea valves. However, due to innovations and negotiations, the overall budget was met. | Inadequate review of key technical parameters in datasheet of Sub-sea ball and check valves | During bidding stage, it must be ensured that key technical details for critical sub-sea valves are available in datasheets. If these details are not available, technical clarifications must be raised to obtain appropriate response from COMPANY. Appropriate PROM inputs to be availed in PROM register.
7 | CHN-ECLL-SP-0007 |  | Subsea / Pipeline | SP | D6463 ¦ SAF 5 | Saudi Aramco |  | ECLL |  |  |  | Fluid Compatibility with Umbilical | Project scope involved the topside connection of existing umbilical (Umbilical were installed as a part of SAF-2 project). After SAF-2 project, Umbilical specification was updated as a part of SAF-5 project, which also replaced the specification of fluid (water based environment friendly fluid) to be filled in Umbilical. However, no attention was paid to the revised requirements of fluid during bid. Old specifications were followed during bid. During execution, revised requirements led to change order from vendor as old specifications were used while placing order as these requirements were noticed later during project. | Paid no attention to revised spec of Umbilical during bid | Engineer has to ensure that such aspect has been taken care in TBE process during bid as well as EPCI execution. During EPCI execution, it must be very clearly mentioned in Purchase Requisition as well.
8 | CHN-ECLL-SP-0008 |  | Subsea / Pipeline | SP | D6200 ¦ SAF 6 | Saudi Aramco |  | ECLL |  |  |  | Umbilical wiring diagram vis-à-vis a interface with actuator and HPU supplier | In SAF-6 project, Umbilical end and subsea valve actuator end connections were found incompatible. In-consistencies were found in connection details and its sequencing on vendor drawing and McDermott interface drawing. | - Lack of plan to manage interfaces among different supplier during detailed engineering. - Lack of coordination with vendors - Lack of in-depth vendor drawing review | Interface schematic and wiring diagram has to developed at start of the project and compliance needs to be ensured throughout the project while reviewing the VDR and preparing the IFC drawing.
9 | CHN-ECLL-SP-0009 |  | Subsea / Pipeline | SP | D7072 ¦ MRJN PKG-4 | Saudi Aramco |  | ECLL |  |  |  | DOP scope to be confirmed for subsea or third party right from the bidding stage.. | Conventionally, the DOP study for subsea spool is done in-house by subsea engineering. However on MRJN PKG-1/4, this scope was included in third party consultant scope. In case of such scenario, the subsea engineering shall be thoroughly involved to ensure that study is in compliance to applicable subsea guidelines as well as any additional recommendation are properly taken care in-line with provision of contract. | NA | During bid and EPCI, subsea engineering must be thoroughly involved to ensure that study is in compliance to applicable subsea guidelines as well as any additional recommendation are properly taken care in-line with provision of contract.
10 | CHN-ECLL-SP-0010 |  | Subsea / Pipeline | SP | D6200 ¦ SAF 6 | Saudi Aramco |  | ECLL |  |  |  | ECA based qualification requirements for pipes | FTM data base has to be looked into for items which can be substituted at the start of every project. However due consideration needs to be given to ECA aspect in case FTMed pipe is meant for pipelay. A FTM has been initiated by PMT from LTA-2 to save cost in terms of material and external coating cost , the initiative could have saved 300K$ in project cost whereas ECA based acceptance criteria was totally ignored while considering this proposal . PMT was planning to transfer 38 pipes from LTA-2 to save cost whereas ECA was not qualified for these pipes. PMT and Engineering was informed about the ECA qualification requirements and later PMT decided to avoid FTM pipe to SAF-6 Pipe lay | If ECA based acceptance criteria is used as an alternative to API 1104 workmanship , Marine, MT and Engineering should be aware of ECA requirements related to material qualification. It is recommended that welding engineering to give a presentation on ECA qualification and requirement to all involved to create awareness .
11 | CHN-ECLL-SP-0011 |  |  |  | D6463 ¦ SAF 5 | [6 empty] | Scope of supply of bend mother pipe and its details. . | There was instance on previous projects that bend mother pipe doesn't meet the post bending required properties. This depends upon many aspect including bending parameters selected by bend vendor. Also on MRJN TP-10 project, the mother pipe offered by bend vendor was marginally not passing the ID criteria set on the project and project specific approval was obtained from Aramco. | To avoid any issue on a quality and properties of mother pipe raised during bending, the scope of bend mother pipe preferably needs to be kept in scope of bend vendor. Further the details of mother pipe from vendor has to be thoroughly reviewed prior to placing the PO to ensure that minimum ID requirement. ID table should be part of requisition. | For future projects, the scope of bend mother pipe preferably needs to be kept in scope of bend vendor. Further the details of mother pipe from vendor has to be thoroughly reviewed prior to placing the PO to ensure that minimum ID requirement. ID table should be part of requisition.
12 | CHN-ECLL-SP-0012 |  | Subsea / Pipeline | SP | D7018 ¦ SAF Phase8 | Saudi Aramco |  | ECLL |  |  |  | Missing Umbilical accessories | The Bid budget basis of using existing accessories on 3 nos. of umbilical was not aligned with ITT requirement which advises to price all accessories. Additionally, engineering missed to considered accessories of other 2 umbilicals in MTO. | The subsea accessories MTO BID differ from Execution MTO. 2 nos. umbilical’s accessories were missed. Failed assumed optimization during the bid for reutilization of accessories associated with existing 3 Umbilical. | 1) Provide detailed specifications to SCM for adequate pricing on all engineered items in future bids and also have this event included in lesson learnt database. 2) All engineered package should be evaluated at high level as a minimum on all future bids. 3) Possibility of rejection of optimization to be incorporated in RISK, Or Price the bid according to ITT, and input possibility optimization in OPPORTUNITY
13 | CHN-ECLL-SP-0013 |  | Subsea / Pipeline | SP | D7018 ¦ SAF Phase8 | Saudi Aramco |  | ECLL |  |  |  | Sub-sea cable accessories | Associated spare cable length and accessories budgeted only for 2/4 cable sizes. As per client requirement, 1km of spare cable and associated repair kits were to be handed over at the end of every project per cable size. This was needed to be priced into the bid. | Possible size optimization was assumed in the bid. This was unsuccessful after award. This was unsuccessful after site and dive survey | 1) A cost benefit analysis with wholistic approach to be done for all non compliant optimizations before considering into estimates. 2 )Possibility of rejection of optimization to be incorporated in RISK, Or Price the bid according to ITT, and input possibility optimization in OPPORTUNITY
14 | CHN-ECLL-SP-0014 |  | Subsea / Pipeline | SP | D7018 ¦ SAF Phase8 | Saudi Aramco |  | ECLL |  |  |  | Flexible Carcass Material | Although, project scope prohibited use of DSS as Flexible Carcass material, during bidding DSS was considered as a base case considering previous project experience. It was also rightly highlighted in PROM that this deviation of using DSS in place of 6Mo to be taken up for Company approval during EPC stage. However, no cost provision was considered in PROM for this item. During execution, COMPANY categorically rejected the use of DSS. 6Mo was then procured to comply with project specification requirements. | Cost provision shall have been considered in PROM | For any risk included in PROM, which is a deviation to project scope, suitable cost provisions must be included. Ensure review of PROM from respective Engineering Area Management prior to submission to P&E team.

## CSE
Serial No | LL Number | Date | Discipline | DC | Project Name | Client | Facility category | LL category | Subject1 | Subject2 | Subject3 | Title | Background | Root cause | Corrective action | Preparer | Preparer Desn | Reviewer | Reviewer Desgn | Approver | Approver Desgn
1 | CHN-ECLL-CS-0001 |  | CSE | CS | D6255 ¦ LTA II | Saudi Aramco |  | ECLL |  |  |  | DMA (Dead Man Anchor) wire parting | This issue was observed during during the START-UP of Pipelay campaign of the project. Anchored barge was used for the Pipelay and one of the anchor was very close to the existing subsea asset. This asset was protected by concrete mattresses. Pipeline Lay was initiated using chain &SUPERMAX rope. During pipe lay, DMA wire parted before starting of normal lay due to abrasion of SUPERMAX rope against existing concrete mattress. | Abrasion of supermax rope against subsea concrete mattress. SUPERMAX ropes are fibre ropes and may not be an ideal choice considering less abrasion withstanding capacity. | After careful review with Marine team, recommendation was that use SUPERMAX rope for DMA start-up must be avoided for future projects, considering the fact that SUPERMAX ropes are fibre ropes, and have less abrasion withstanding capability. Another recommendation was that CSE team shall indicate the size of wire rope in Field data book / Pipeline Installation Manual prepared by CSE.
2 | CHN-ECLL-CS-0002 |  | CSE | CS | D7057 ¦ MRJN TP10 | Saudi Aramco |  | ECLL |  |  |  | Deck panel Stacking - temporary steel and analysis | For TP10 project, it was found that there is no available crane in region, which can have enough reach and capacity to lift deck panels from its legs. Hence, it was recommended to lift the deck panels from the edges. Due to requirement of lifting from the edges, deck panels required extra amount of temporary strengthening. It was observed that enough efforts were not made during bid to check whether stacking shall be possible with available cranes or not. Assumption during bid was that standard stacking like PDM decks would be sufficient, which was a wrong assumption during bid. | No detailed stacking checks requested by Fab at bid stage and temporary steel requirements were estimated based on normal stacking checks. | For the largest decks like ARAMCO TPs, Compression platforms, it is highly recommended to perform detailed stacking analysis during bid stage. Quantity of temporary steel requirements must be considered based on outcome of stacking analysis.
3 | CHN-ECLL-CS-0003 |  | CSE | CS | D7057 ¦ MRJN TP10 | Saudi Aramco |  | ECLL |  |  |  | Deck Support Frame (DSF) steel quantity | Steel quantity for fabrication of DSF increased due to inclusion of loadout beams. Loadout beams intended to be supplied by ALE were found to be unusable and incorrectly priced with regards to duration needed. | Installation plan change from DB50 to use of float over barge for boat landing during EPCI execution. | Loadout plans & methods recommended by CSE, Marine & Fab. Structural analysis of float over decks should include the DSF.

## Projects
Serial No | LL Number | Date | Discipline | DC | Project Name | Client | Facility category | LL category | Subject1 | Subject2 | Subject3 | Title | Background | Root cause | Corrective action | Preparer | Preparer Desn | Reviewer | Reviewer Desgn | Approver | Approver Desgn
1 | CHN-ECLL-PJ-0001 |  | Projects | PJ | D6255 ¦ LTA II | Saudi Aramco |  | ECLL |  |  |  | DMA (Dead Man Anchor) wire parting | This issue was observed during during the START-UP of Pipelay campaign of the project. Anchored barge was used for the Pipelay and one of the anchor was very close to the existing subsea asset. This asset was protected by concrete mattresses. Pipeline Lay was initiated using chain &SUPERMAX rope. During pipe lay, DMA wire parted before starting of normal lay due to abrasion of SUPERMAX rope against existing concrete mattress. | Abrasion of supermax rope against subsea concrete mattress. SUPERMAX ropes are fibre ropes and may not be an ideal choice considering less abrasion withstanding capacity. | After careful review with Marine team, recommendation was that use SUPERMAX rope for DMA start-up must be avoided for future projects, considering the fact that SUPERMAX ropes are fibre ropes, and have less abrasion withstanding capability. Another recommendation was that CSE team shall indicate the size of wire rope in Field data book / Pipeline Installation Manual prepared by CSE.
2 | CHN-ECLL-PJ-0002 |  | Projects | PJ | D7057 ¦ MRJN TP10 | Saudi Aramco |  | ECLL |  |  |  | Deck panel Stacking - temporary steel and analysis | For TP10 project, it was found that there is no available crane in region, which can have enough reach and capacity to lift deck panels from its legs. Hence, it was recommended to lift the deck panels from the edges. Due to requirement of lifting from the edges, deck panels required extra amount of temporary strengthening. It was observed that enough efforts were not made during bid to check whether stacking shall be possible with available cranes or not. Assumption during bid was that standard stacking like PDM decks would be sufficient, which was a wrong assumption during bid. | No detailed stacking checks requested by Fab at bid stage and temporary steel requirements were estimated based on normal stacking checks. | For the largest decks like ARAMCO TPs, Compression platforms, it is highly recommended to perform detailed stacking analysis during bid stage. Quantity of temporary steel requirements must be considered based on outcome of stacking analysis.
3 | CHN-ECLL-PJ-0003 |  | Projects | PJ | D7057 ¦ MRJN TP10 | Saudi Aramco |  | ECLL |  |  |  | Deck Support Frame (DSF) steel quantity | Steel quantity for fabrication of DSF increased due to inclusion of loadout beams. Loadout beams intended to be supplied by ALE were found to be unusable and incorrectly priced with regards to duration needed. | Installation plan change from DB50 to use of float over barge for boat landing during EPCI execution. | Loadout plans & methods recommended by CSE, Marine & Fab. Structural analysis of float over decks should include the DSF.
4 | CHN-ECLL-PJ-0004 |  | Projects | PJ | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Document Numbering Schema | PEMEX requirement on Document numbers are based on the System numbers. Intially the delvierable register distributed and numbered based on the inputs received from our Engineers. Based on the inputs the documents got numbered and subsequently loaded al ldocuments into CWX. Later a month When the deliverable register was submitted to PEMEX, we received hunderes of comments on the change in the system number which affects the entire numbering schema, results in changing of document number from CWX which consumes more time and rework |  | Deliverable register to be submitted to client before enter into CWX.
5 | CHN-ECLL-PJ-0005 |  | Projects | PJ | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | PEMEX Standards in English | Non-availability of Pemex standards in English - cost was not considered in the bid. |  | Availability of all Standards, Project specifications etc in English and cost for obtaining the same to be considered during Bid.
6 | CHN-ECLL-PJ-0006 |  | Projects | PJ | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Spanish to English Translation and dealing with PEMEX | No strategy for deliverables translation and how to manage Pemex with English deliverables were not clear and ambiguous |  | Spanish / English versions of the Deliverables and dealing with PEMEX on this issue to be strategized during Bid stage. All functional / discipline leads involved in the project execution should be trained in Spanish language
7 | CHN-ECLL-PJ-0007 |  | Projects | PJ | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Non Availability of Critical Documents NRF, NOM EPI | Many critical documents (NOM, NRF) referenced in bid documents were not available till execution. This could lead to bid miss and not meeting requirements. To be thoroughly reviewed during the bid stage |  | List of all documents like NRF, NOM, EPI which are PEMEX specific to be identified and obtained during bid Stage. Considering the future bids for Pemex, a complete set of Mexican standards/ PEMEX standards and specifications need to be translated to English and preferably maintained in Intelex (or) IHS.
8 | CHN-ECLL-PJ-0008 |  | Projects | PJ | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | ICC review Cycle | Introducing an intermittent review cycle ICC was an afterthought and not a result of strategy. While the compliance reviews were helpful during the initial stages of the project in the absence of client reviews - in later stages this became a bottleneck as Compliance team started providing directions assuming the role of client and not taking issues to client. |  | Such additional reviews (basic deviations from the procedure) should be identified during bid stage as part of project execution strategy. The scope and time limit of any such reviews need to be part of the execution strategy.
9 | CHN-ECLL-PJ-0009 |  | Projects | PJ | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Change Management | All changes were logged and a change log was maintained diligently during the basic engineering phase of the project. Change coordinator was identified immediately afterwards to compile/ quantify all the changes for estimation of change orders. Change order quantification took longer than estimated time. The DTCMS usage by the engineering team was mainly limited to man hours and not on material / procurement costs. Review of DTCMS raised by Project controls team was not effective to capture the changes. |  | Change coordinator should be identified within the engineering team in all projects to look out for changes and record them diligently. DTCMS usage by engineers should not be limited to man hours, but also highlight the changes that can potentially impact the project. Project Controls Manager should be mobilized early on in the job and regular review of DTCMS should be done.
10 | CHN-ECLL-PJ-0010 |  | Projects | PJ | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Documenting of Constructability Review | Review for major packages / skids for constructability / fab review at Altamira Yard not documented during bid leading to change in strategy after award of work. |  | Constructability review and philosophy for major packages and skids to be done during Bid Stage and clearly documented. This should be part of the bid strategy document.
11 | CHN-ECLL-PJ-0011 |  | Projects | PJ | A6019 ¦ PEMEX | Pemex |  | ECLL |  |  |  | Bid Engineering | Non-availability of bid-engineering efforts/ deliverables and lack of basis & assumption of the bid – left no benchmark to compare whenever a change is identified. |  | All Bid Engineering efforts / deliverables, basis, assumptions if any to be clearly documented and available for Project Execution team post award
12 | CHN-ECLL-PJ-0012 |  | Projects | PJ | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | Stringency of project specifications beyond codes/standards/practices | Project specifications developed during FEED were primarily ExxonMobil specifications adjusted for QG practices and regional requirements. This was received during the ITT. This was floated to the vendors who provided quotes and the pricing was considered by SCM. However, during execution, it became evident on a majority of the packages that the vendors were unable to comply to the specifications and raised deviations. In a number of cases, it turned out that the vendors had not read all the specifications thoroughly during the bid Some deviations pertained to QA aspects such as inspection and testing, NDT etc. In some instances, vendors provided their standard packages. This led to two issues a) Delay in issuing TBE and Purchase Requisitions as the deviations had to be addressed through "Specification Deviation Requests" with COMPANY. B) Cost over-runs to comply where COMPANY did not accept the deviations. This was the case with major packages such as GTG, Fuel Gas Package, Structural Steel, Clad Piping, Safety items, Crane etc. Procurement delays at EPC due to vendors inability to supply in line with project specifications. Deviations which require approval from Company. | Inadequate assessment of the stringency of specifications w.r.t codes and standards and typical McDermott historical practices | 1. Get a confirmation from the vendor in writing that they have read all the specifications and has provided the quote. Vendor to be asked to provide a price with deviations and also for full compliance, if it is determined that this will be beneficial from a competitiveness point of view. 2. In cases where the above cannot be obtained due to bid timelines etc. ensure this is communicated to the bid team (bid PM, Estimation and SCM) in the TBE/CBE meetings. Whilst the setting up of the meetings is by Estimation, bid PEM to push for the same and actively participate along with the respective discipline engineer. Also, QA engineer participation will be required during bid. 3. MR issued to vendors, vendor offers and TBEs during bid should be reviewed by QA to ensure that QA related points are adequately captured. 4. Providing cost adders should be structured, bid PEM to ensure that the ownership is collective. 5. If cost adders have unknowns, risks or uncertainties, include a specific PROM item. PROM inputs must cover all uncertainty with respect to vendors and must be discussed with Bid PM and P&E team. This aspect is very important to be addressed in future bids. BEM must review the procurement risks due to open deviations / cost adders and suitably address in PROM especially for CATEGORY A packages. 6. Bid PEM to seek a list of non-AVL vendors if used as pricing basis and seek discipline alignment whether this approach is appropriate. Awareness that location change can also result in an AVL vendor being classified as non-AVL.
13 | CHN-ECLL-PJ-0013 |  | Projects | PJ | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | Schedule development (bid and EPC) | A typical standard schedule was adopted as the basis during the bid to develop the EPC schedule for execution. Post award, it was recognized that QG has specific requirements (e.g. issue of MRs to vendors only after COMPANY approval of MR, need for layouts to be AFC prior to approval of structural drawings etc.) which resulted in protracted discussions with COMPANY on achieving a practical middle ground. | Reliance on standard schedules | a) During the bid stage, review ITT requirements thoroughly to address any deviations to standard schedule and provide this input to bid planning. B) Build the base schedule upon the above input and where overall project schedule cannot be met, raise upfront for alignment with COMPANY (through bid PMT). c) If a deviation is the basis of schedule, a high impact PROM entry to be considered. d) During execution, pursue with COMPANY to optimize the schedule and bring in floats that will de-risk the project.
14 | CHN-ECLL-PJ-0014 |  | Projects | PJ | D6978 ¦ NFPS I1P1 | Qatar Gas |  | ECLL |  |  |  | 3.2 certification requirements for material for hydrocarbon service | it was noticed during EPCI execution that 3.2 certification requirements were missed on many packages during bidding for example, Flow Nozzle / Venturis, Level Gauges, Level transmitters, Fuel gas treatment package etc.. For hydrocarbon services, it is very essential to consider such requirements in line with COMPANY specs. | - Oversight during bidding by engineers | Bidding engineers (in addition to QA engineer) must pay attention to QA/QC related requirements during bidding. These requirements can have detrimental impact on project schedule and cost. During bidding, engineers must consult QA engineer to ensure that requirements related to QA/QC are addressed. BEM to ensure that QA engineer is assigned to bid, and inputs are ensured from QA engineer to disciplines.
15 | CHN-ECLL-PJ-0015 |  | Projects | PJ | D7202 ¦ NFE FEED | Qatar Gas |  | ECLL |  |  |  | Extensive Subcontractor Support for SmartPlant Software due to system / software limitations | SmartPlant (SP) Tools Inbuilt utility was not enough to meet the SP integration as per project requirement - Refer to the following examples: 1. System configuration for SP Foundation Integration 2. Implementation of Data exchange Workflows (e.g. Electrical cable schedule) 3. Failing of Macro expansion 4. Few of Line Tasks -not running 5. Manual efforts for renaming loops 6. Inability to print multi tag spec in Citrix Environment 7. Prefix given in copy from window is not applied to LINE, PID and Equipment number 8. Limitations of importing data and copying data due to character limitations. Hence, to address the system limitation issues faced during execution, extensive Vendor (HEXAGON) support was required full time to develop systems during bid and a lot of efforts were required to address these limitations. | Vendor Software built in utility was not enough to meet the specific project requirements and these were identified at the early stages. Extensive support from Vendor was required during execution to address system limitations | 1) It is very essential that system limitations and required additional efforts are discussed with third party subcontractor (HEXAGON) during bid and they are budgeted. 2) During project execution, it is very essential to address the issue of system limitations. Third party Support (from HEXAGON) should be ensured during execution. Software / system limitations and its impact must be gauged with Project system team & COMPANY. 3) Vendor shall be encouraged to spell out the limitations, and any additional support module/licences, at the initial stage of Project presentation in which System Engineers and Project Coordinators should participate.
16 | CHN-ECLL-PJ-0016 |  | Projects | PJ | D7233 ¦ Umm Shaif | ADNOC |  | ECLL |  |  |  | MOPEX office alignment | In Umm Shaif project, for engineering execution, London was the lead office for process platforms, LQ and Onshore, while Dubai was the lead office for WHTs, Subsea and overall bid estimation. Additionally, Chennai and Gurgaon were support offices for the offshore and onshore scopes, respectively. Different offices were familiar with different standards and methods, which led to inconsistencies and rework. Few examples are below: a) London & Gurgaon offices used CMS standards while Dubai and Chennai offices used IMS standards (Note: IMS-CMS were not completely unified at that point) b) London & Dubai used different 3D coordinate systems, i.e. Dubai used (0,0) for each platform, while London used a COA datum point. c) Calculation spreadsheets were different across offices. d) Detailed MTOs based on legacy McDermott's Standard MTO templates were required by MENA Estimation since beginning. However London office was not familiar with the same and they were used to providing high-level MTOs only. Hence, above issues led to misalignment among various offices. | - Gaps in MOPEX alignment; - Incomplete unification of McDermott operating methods (for e.g., standards, spreadsheets) - Lead offices like London were not used to prepare detailed MTO which is required by MENA estimation team. | a) Conduct multiple alignment sessions with all the MOPEX offices to ensure correct requirements/responsibilities are identified to avoid project delays. All team members shall be included in such alignment meetings and not just be limited to PMT and location leads only. This should be followed by regular/weekly meetings to ensure enough awareness so that executed work will have desired quality at the first time. b) Use a common reference point for 3D models across all MOPEX offices. This will prevent overlap/clash when the models are merged. c) All Templates (spreadsheets, deliverable, MR, TBE, MTO, etc) shall be aligned at the beginning of the project. Conduct trainings, where necessary. d) For MOPEX based projects, the cost of alignment sessions, team buildings, travel and trainings to be included in bid estimate. e) Ensure focus on delivering desired quality for MTOs / MRs / TBEs to be issued for bid estimate.
17 | CHN-ECLL-PJ-0017 |  | Projects | PJ | D7233 ¦ Umm Shaif | ADNOC |  | ECLL |  |  |  | Preparation of MTOs | Legacy McDermott and Legacy CB&I have different mechanisms for creating bid MTOs. At the beginning of project, all offices were notified regarding the Estimating Plan and the mandatory use of McDermott Standard MTO templates. However, the MTOs prepared in Chennai and London had errors, which required rework. For example, Ident Codes, Insulation, Line numbers, Train 2 items etc were missing. Furthermore, few disciplines did not follow the procedure of issuing MTOs to Estimation Dept via iDocs, which led to Estimation Dept using earlier revisions. | - Lack of training and understanding of McDermott Standard MTO templates - Lack of trained resources | a) Arrange refresher trainings for bidding team on the Standard MTO Templates. This is recommended irrespective of previous training sessions. b) Prepare MTO Basis along with the MTOs. c) Issue Engineering discipline 'rule book' for norms and allowances added to similar items i.e. supports per pipe, tons of electrical supports per m of cable tray etc. d) Assign a project engineer at the start of the proposal phase to coordinate MTO production (potentially with Estimating background) to ensure MTOs are of the correct quality so no rework is required and MTOs are entered into the estimate on time.
18 | CHN-ECLL-PJ-0018 |  | Projects | PJ | D7244 ¦ Belbazem FEED | Al Yasat Petroleum |  | ECLL |  |  |  | Site surveys and availability of right personnel for survey | Availability of McDermott engineering personnel to undertake surveys at ADNOC facilities during multi project execution in Dubai office. | There is severe lack of personnel that meet current ADNOC eligibility requirements to undertake site surveys. This is primarily due to the requirement of personnel being issued a residential visa from Abu Dhabi as opposed to Dubai. | Ensure survey dates are know in advance for all parallel projects to ensure availability of personnel. HR to review visa policies in line with ADNOC requirements for new applications as well as renewals.
19 | CHN-ECLL-PJ-0019 |  | Projects | PJ | D7244 ¦ Belbazem FEED | Al Yasat Petroleum |  | ECLL |  |  |  | BOQ preparation work (in additional to MTO generation work) | Provision of BOQ to Construction sub-contractor to allow preparation of third party project costs. | Estimation team necessitated to prepare BOQs (not MTOs) for onshore scope, which will enable them to compare prices for the following purposes. 1. Onshore benchmarking 2. Effective comparison of quantities with other executed projects. 3. Negotiation of rates with Construction Contractors. This requirement was never stated in the beginning but this was communicated to engineering later on, which was not accounted during FEED bidding. | - For onshore scope, BOQs will help Estimation team for many ways as listed here. However, engineering team need to allow man-hours during bidding for this work. - Additional man-hours shall also be required to be considered for effective coordination with Construction Contractor during bid. - BOQ templates to be agreed and frozen with Estimation team and Construction Contractor.
20 | CHN-ECLL-PJ-0020 |  | Projects | PJ | D7369 ¦ NASR 100 MBD | ADNOC |  | ECLL |  |  |  | Late receipt of revised ADNOC standards, and its impact on project | ADNOC continued updating standards as a part of updating their existing standards. In the middle of project, ADNOC enforced new and updated standards as basis for our adequacy checks which were not applied at the time of beginning of study. This led to re-checking or verifying the adequacy checks already performed by disciplines like Process, I&C. | - Lack of qualification in bid or no agreement with ADNOC that McDermott will only follow standards which are applicable on the date of award. Any changes to it, can attract for change order. - No push-back from PMT team to ADNOC on this issue. | Qualify in bid proposal that CONTRACTOR will only follow standards which are applicable on the date of award. Any changes made after award date, shall be handled through change management process.. Drive a discussion at study outset on approach to be taken for use of design standards and application of normal design practices / margins / design criteria in brownfield assessments. Agree on set of standards at the outset prior to commencement of engineering work.
21 | CHN-ECLL-PJ-0021 |  | Projects | PJ | A7697 ¦ Angelin | British Petroleum |  | ECLL |  |  |  | Update on code requirements. | Lack of update on latest code requirements. While team’s knowledge of Code requirement was never a shortcoming , there were incidences (as identified below) where team’s lack of awareness in latest code requirement led to bottleneck in the project API 526 - Updates on Overpressure protection for jet fire scenario Industrial practice of Thick Plate orifice as per RW miller ASME Wake frequency calculation as per Latest updated code |  | Constant awareness of changes in design practice in updated code and standards shall be mandatory and must be implemented in all project to mitigate potential CONQ
22 | CHN-ECLL-PJ-0022 |  | Projects | PJ | A7697 ¦ Angelin | British Petroleum |  | ECLL |  |  |  | Awareness of Special project requirements. | Lack of awareness of Special project requirements. Every project comes with special requirement , Angelin had its share. – painting of SS material , Spl requirement for welding of DSS, Spl coating requirement for splash zone area, additional testing requirement of HC piping While engineering correctly captured the requirement in the various applicable document, gaps were found during fabrication and some of the above was not strictly adhered to. |  | We could have mitigated this problem had we run an awareness campaign for spl requirement across discipline and function – through toolbox talks , review workshops etc. Maintain a register of such spl requirement Include this construability review and other workshop
23 | CHN-ECLL-PJ-0023 |  | Projects | PJ | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Tagging Philosophy | KJO Proponent comment on Tag sequence after 60% design review created delays and multiple revision of design and engineering deliverables on all discipline. |  | Tagging philosophy shall be discussed and approved by Company before first issuance of P&ID and instrument index.
24 | CHN-ECLL-PJ-0024 |  | Projects | PJ | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Constructability review | Certain Constructability Review ideas/solutions (for eg, stairtower design) were added at late stage (after IFC of drawings), which resulted in considerable rework and additional manhours. |  | a) Constructabilty reviews to be scheduled at early stage of the project & ensure attendance of all applicable parties. b) Compare cost/ schedule of ideas arising from Constr. Review before implenting.
25 | CHN-ECLL-PJ-0025 |  | Projects | PJ | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Dimensional survey for brownfield | late dimensional survey resulted in issuing the drawings with numerous HOLDS & delay for final IFC. |  | dimensional survey results from DC to be made available before IFC stage for prompt issue of the design deliverables without HOLDS & to avoid reworks.
26 | CHN-ECLL-PJ-0026 |  | Projects | PJ | A6224 ¦ KJO Hout | Al Khafji Joint Operations |  | ECLL |  |  |  | Delayed Constructability reviews | Constructability reviews were held at very latter stage of the project (Post 60%) , which resulted in many reworks for all the desciplines |  | Costructability review programs are suggested to be conducted from the 30% stageof the project with the same people who will be involved in the project from FAB/HUC/ Marine/CSE.

## Procurement
Serial No | LL Number | Date | Discipline | DC | Project Name | Client | Facility category | LL category | Subject1 | Subject2 | Subject3 | Title | Background | Root cause | Corrective action | Preparer | Preparer Desn | Reviewer | Reviewer Desgn | Approver | Approver Desgn
1 | CHN-ECLL-PE-0001 |  | Procurement engineering | PE | A6019 ¦ PEMEX | Pemex | [5 empty] | Vendor document Reviews by Client | It was proposed to send only FAT procedure of all packages to client for review, later was debated that FAT Procedures for the systems that were listed in Annexure B1 shall only be sent to PEMEX. Subsequenlty there was a mail from AFY QA , that FAT proceudres will be handled separately by AFY QA and not through CWX. |  | Discussions to be initiated with client in the initial stages to agree upon what vendor documentation need to be submitted to the client engineers for a. Review / Approval b. Information c. Not required to be sent and documented in the Document control procedure
2 | CHN-ECLL-PE-0002 |  | Procurement engineering | PE | A6019 ¦ PEMEX | Pemex | [5 empty] | Vendor documents submitted for Engineer review | In the absence of experienced vendor data / package expeditors, package engineers, lead engineers, QA/QC engineers and even Quality Director were forced to perform the role of expeditors to obtain vendor documentation. This led to a situation where the VDCS portal was not efficiently utilized to route the vendor data. It was left to the individuals to obtain necessary information in whatever means and then regularize it through the VDCS portal, thereby putting the Document Controllers to do a lot of additional work / rework which was not envisaged. |  | Qualified expediting team to be in place prior to placement of PO's to obtain information and upload the information through VDCS, so that Document controllers can distribute them to the reviewers in a orderly manner.
3 | CHN-ECLL-PE-0003 |  | Procurement engineering | PE | A6019 ¦ PEMEX | Pemex | [5 empty] | Technical Integrity | TI team was identified to review the procurement engineering documents and assist in vendor inspection/ audits. Without clear scope definition and without clear project background and involvement during bid stage coupled with overlap of responsibilities with QA/QC, this led to a lot of confusion and duplicity of comments. Some of the observations by the TI team made had cost implications. |  | TI team need to be made part of the bid team to review the bid documents and raise their concerns as bid clarifications which will help in 1. bringing awareness to client and to all bidders. 2. bringing awareness to the TI team about contract scope
4 | CHN-ECLL-PE-0004 |  | Procurement engineering | PE | A6019 ¦ PEMEX | Pemex | [5 empty] | Incomplete TBEs. | Incomplete TBE issued for progressing purposes. TBE’s issued had many open points, because of various reasons including: - Late vendor offers - Slow vendor responses - Change in Procurement strategy from Single vendor to Multi vendor evaluation. |  | TBE should be issued only after all major Technical issues are resolved and confirmation obtained from Vendor. Clear procurement strategy and proper procurement support in expediting vendor offers / responses essential in providing quality TBE's.
5 | CHN-ECLL-PE-0005 |  | Procurement engineering | PE | A6019 ¦ PEMEX | Pemex | [5 empty] | Bid Stage TBE | Vendor offers during bid stage not evaluated for compliance to Pemex requirements |  | Proper TBE with TQs to vendors and vendor obtaining responses and confirmations wherever required to be done during Bid Stage to avoid cost impact and delivery impact during Project execution
6 | CHN-ECLL-PE-0006 |  | Procurement engineering | PE | D6978 ¦ NFPS I1P1 | Qatar Gas | [5 empty] | Improper Technical adjustment factors for tagged items / vendor packages (during bidding) leading to cost escalations during Execution | It was noticed during NFPS I1P1 EPCI execution that pricing of tagged items were observed with significant cost escalations. There were many instances where cost increase very significantly, and one of the reason was improper technical adjustment factor or PO reference given for a particular tagged item. | - Paying less attention to check whether respective tagged item is technically comparable or not.. - Unavailability of Priced PO from SCM (it was not allowed during bid to have priced PO details from SCM) | - Based on latest agreement, engineering is allowed to have priced PO from SCM. Before giving PO reference to SCM, Priced PO must be obtained to ensure that sensible pricing shall be performed after giving PO reference. - BEM to ensure that engineering cost reviews are schedules prior to Local area review. - If not sure about pricing, this issue must be bring to the notice of P&E, SCM and Bid manager and appropriate strategy to be considered to mitigate this risk. It is advisable to update PROM if required. - Engineering must participate in cost reviews and ask SCM team to share pricing details prior to Local area review.
7 | CHN-ECLL-PE-0007 |  | Procurement engineering | PE | D6978 ¦ NFPS I1P1 | Qatar Gas | [5 empty] | Procurement strategy for handling single source vendors | - During EPCI execution of NFPS I1P1 EPCI, significant cost escalation were observed from single source vendors due to many reasons. For example, reasons are given below. - Vendors did not review the specifications during bid, and cost escalation is required to meet the COMPANY requirements. - Vendor's pricing based on old rates. - Vendor missed many requirements such as string test for GTG, cyber security, IFAT requirement etc.. and they did not price them in their quotation In the absence of robust engineering and procurement strategy during bid, significant cost escalation was observed mainly on single source vendor packages. It was not thought during bid that how vendors can be stopped to escalate cost during EPCI execution. | - Lack of robust E&P strategy for handling single source vendors. - Lack of pre-bid agreements with single source vendors. - Lack of receipt of signed deviation list. - Lack of PROM inputs on single source packages | - Ensure robust E&P strategy in place for bid. BEM must ensure this in consultation with SCM manager during bid. - Ensure risk mitigations are in place and well documented that how single source vendors shall be limited from rising their price during execution. - Check whether pre-bid agreements can be reached with vendors. - Must endure that signed deviation list (stamped) is available from vendor. - All cost adders must be priced and jointly agreed with SCM and the same are well documented for future use. - All communications must be marked to P&E, SCM and Bid Manager for future references. - Ensure PROM inputs are updated in case of risks associated with single source suppliers.
8 | CHN-ECLL-PE-0008 |  | Procurement engineering | PE | D6978 ¦ NFPS I1P1 | Qatar Gas | [5 empty] | Bid v/s Order Quantity | Bid v/s Order quantity for bulks : Towards completion of TBE and before issue, for each package prepare a bid v/s buy (order) v/s EAC quantity noting any changes – This will be handy to explain any growth or optimization. This was prepared on an “as-needed” basis for I1P1 to discuss internally with project controls and the vendors, where necessary. It is worthwhile to make this as a norm. A standard template is to be used. | Process improvement | Lead/Discipline engineer to provide a summary level quantity and key deviations from bid to buy such that timely action can be taken if any over-run is foreseen or there is an optimization opportunity. This will help support such efforts in a timely manner by the PEM/PE
9 | CHN-ECLL-PE-0009 |  | Procurement engineering | PE | D6978 ¦ NFPS I1P1 | Qatar Gas | [5 empty] | Brownfield materials and materials procured by other functions | For the shutdown work, a material required v/s ordered gap analysis was performed to ensure no surprises. This was done just at the right time and few additional materials ordered as an outcome of the exercise. This was also the case with jacket miscellaneous materials. This exercise is very important to identify inadvertent misses and also address any inter-disciplinary alignment issues (between engineering disciplines and also with fabrication, marine etc. as some materials are ordered by these functions). It is noted that missing minor materials can cause major issues (e.g. missing nuts and bolts). In a shutdown scenario, material control is very critical and should be co-related to engineering MTOs. | Process improvement | Sign off sheets from each discipline to be maintained by EMT to address the same and shared with offshore hook-up team and the offshore coordinator/project engineer. This should be tracked soon after award and into the issue of IFC drawings. A shutdown materials alignment workshop should be conducted with all stakeholders internally to ensure no items are missed (Note - Awareness that minor items if not ordered can cause major problems should be emphasized to the team).
10 | CHN-ECLL-PE-0010 |  | Procurement engineering | PE | A7697 ¦ Angelin | British Petroleum | [5 empty] | Vendor Document Reviews | Vendor document review - Compared to similar projects , we had improvement in close out of vendor document approval, however we were constantly lagging behind the plan progress– excepting few packages Delay on vendor documents review had profound impact on tight schedule of fab deliverables and resulted in revision and ARN during follow on engineering At the same time we can say for sure that the Vendor document review process ensured compliance of vendor to project requirement and minimized smooth FAT and surprised at yard. The following areas which contributed in delay in VDR and needs improvement Lack of reporting ability in Coreworks - PMT did not have a proper tool to monitor progress Lack of email notification in Coreworks – engineers were not having a clue if the new document has been submitted by vendor Though Coreworks had a feature for commenting in single document, they did not function well and was abandoned. Inter discipline comments were handled by email and it was left to individual organizing ability to keep track Multiple software used for receiving vendor document’s, uploading on Coreworks. Delay by vendor – there was no support for expediting vendor – which resulted in engineers and VPM to take this additional responsibility There was no penalty on vendor if they delayed a document/ incentive for completion of time. Engineer did not follow up their comments with vendor – thru telecon, meeting , which many times resulted in document returned without comments incorporated There was no CRS provided by vendor / proper revision marking on revised documents by vendor Excessive comments by engineers , many of which could have been avoided if we had a discussion with vendor prior to issue of comment Inter-discipline comments were more of CYA type and many times were irrelevant and contributed to delay due to internal resolution Frequent changes in VPM in Houston caused confusion and delay in close out of vendor documents Delay in QA comments on vendor document resulted in delay in returning vendor on time on several occasion – it became a constant problem and engineers were made to expedite internal customers Late communication to vendor for aligning their P&ID as per project legend resulted in several rounds of review and revision – Variation claim by vendor |  | Following hard lessons learnt can be tired out on other projects Have a proper team to configure Coreworks to ensure the gaps /lesson learnt are not repeated Have a good tool to monitor the progress Have notification facility along with workflow to enable faster response Monitor vendor progress with equal importance of our deliverables Have strong and adequate Desktop expediting team Have regular tool box on “how not to comment” and the “right way of commenting” Plan and budget shall include visit to vendor works to facilitate across the table review - atleast for critical and LLI Have toolbox on “how to pass on requirement /observation during VDR IDC” to improve overall time cycle Insist on revision marking and CRS from vendor Have a clear plan on resource allocation from engineering and SCM for Vendor package management – and avoid changes as far as possible Have dedicated QA team for review Vendor document Ensure we pass on requirements such “project legends to be followed for P&ID” etc. as part of RFQ , so that we do not end up with VO at later stage.
11 | CHN-ECLL-PE-0011 |  | Procurement engineering | PE | A7697 ¦ Angelin | British Petroleum | [5 empty] | Vendor Expediting | Inadequate expediting team There was no desktop expediting/field team for the project which resulted in engineer expediting vendor response. This was an unplanned work and resulted in poor productivity in VDR – across discipline. |  | Have a strong Desktop and filed expediting team
12 | CHN-ECLL-PE-0012 |  | Procurement engineering | PE | A7697 ¦ Angelin | British Petroleum | [5 empty] | Comments Resolution Sheet (CRS). | Delay in Close out of customer comments on Vendor and the “failed strategy of no CRS” Considering the fast track nature of the project, a decision was taken not to provide CRS for close out of company’s comments on vendor document. This was made considering BP assurance that BP review of vendor document will be light and it was MDR responsibly in ensuring compliances to project requirement Later during actual VDR , we found BP active participation on VDR and their were comments that need to be resolved. Engineering had to prepare CRS late in the project for resolution and till date there were several of these comments still open and unresolved – (customer approval still in code B) Further BP has resent consolidated letter pointing out gaps in vendor documentation , which has resulted unexpected remob of engineers back to ensure close out. |  | Irrespective what is agreed and promised , if we had passed a response to customer comments (a CRS), while approving VDR , we could have averted this situation. Budget adequate hours for engineering for close out of customer comments to avoid bad productivity and potential CONQ.

## Droplist
Discipline |  | Process | Loss Prevention | Electrical | Instrumentation | Mechanical | Piping & Layout | Structural | Subsea / Pipeline | CSE | QAQC | Projects | Procurement | Project name | Facility category | LL Category | Client name
Process | PR | Chemical Injection | Building design | Battery limits | Codes and standards | Coating System | 3rd Part Studies | Barge Bumper | Codes and standards | Rigging | xx | Schedule | TBE | D7068 ¦ Marjan Package1 | Well head platform | ECLL | Saudi Aramco
Loss Prevention | LP | Codes and standards | Codes and standards | Codes and standards | Fire and gas | Codes and Standards | AIV / FIV Study | Bathymetry | Material of construction | Sea fastening | xx | Manhours | MR | D6978 ¦ NFPS I1P1 | Auxiliary platform | EHLL | Total
Electrical | EL | Equipment Layout | Corrosion protection | Electrical building | HPU | Crane | Chemical Cleaning requirement | Blast Design | Pipeline protection | Bumper and guides | xx | Qualifications | VDR | D5763 ¦ Karan offshore | Tie-in platform |  | Maersk
Instrumentation | IN | Equipment Sizing | Emergency system | Electrical database | Interfaces / Battery limits | Environment conditions | Codes and Standards | Blast Wall | Pipeline Risk Assessment | Installation aids | xx | PROM | SDRL | D5773 ¦ ONGC | Riser platform |  | Qatar Gas
Mechanical | ME | HAZOP | Escape / Egress | Electrical Loads / Load list | IRCD design philosophy | Package Management | Critical lines | Boat Impact | Rely-upon data | Naval architecture | xx | Bid basis | AVL | A6019 ¦ PEMEX | SURF |  | Qatar Petroleum
Piping & Layout | PL | Hydraulic Calculations | Explosion overpressure | Emergency power philosophy | Material selection | Free issue items interface | Fabrication requirements | Boatlanding | Tie-in details | Fab Engineering | xx | Change management | FAT | D6071 ¦ QP Bul Hanine | Accommodation platform |  | British Petroleum
Structural | ST | Instrumentation | Fire and gas | Hazardous area classification | MPFM | Capital spare | Flare location | Bridge |  | Hookup engineering | xx | Doument control | MTO | D6167 ¦ RasGas | Production platform |  | Pemex
Subsea / Pipeline | SP | Isolation Philosophy | Firewater system | Heat tracing scope | Permanent Downhole Gauging System | Material handling requirements | Fluid Service Conditions | Bridge Crane |  | Load out | xx |  |  | D6221 ¦ ADMA | Electrical platform |  | ONGC
CSE | CS | Line Sizing | Helideck safety | ICCP scope | Project schedule | Mechanical datasheets | Heat Tracing | Building | [5 empty] | D6803 ¦ RasGas FAXP | Topside |  | ADMA
QA/QC | QA | Material Selection | Human factors | Lighting design | SIL assessment/verification | MOPEX requirements | Insulation | Cathodic Protection | [5 empty] | D7202 ¦ NFE FEED | Jacket |  | ADNOC
Projects | PJ | Process design basis | Layout safety | Material of Construction | Statutory requirements | MR / PR / TBE | Interfaces / Battery limits | Codes and standards | [5 empty] | D7233 ¦ Umm Shaif | Compression platform |  | Al Yasat Petroleum
Procurement engineering | PE | Process Simulation | Life saving equipment | Novated items |  | Noise | JV requirements | COG Envelope | [5 empty] | D7244 ¦ Belbazem FEED |  |  | Al Khafji Joint Operations
|  | Project schedule | Passive Fire Protection | Power system studies |  | Project schedule | Line counts | Conductors | [5 empty] | D7369 ¦ NASR 100 MBD
|  | PSV's and Flares | Project schedule | Project schedule |  | Sparing Philosophy | Line sizes | Diaphragm Closure | [5 empty] | P6068 ¦ NFPS I1P2 Bid
|  | Pumps & Compressors | Safety and Firefighting equipment | Statutory requirements |  | Statutory requirements | Material Selection | Dropped object protection | [5 empty] | A7697 ¦ Angelin
|  | Rely-upon data | Safety Studies | Unique project requirement |  | Unique design requirements | MOPEX requirements | Fatigue | [5 empty] | A6224 ¦ KJO Hout
|  | Sparing | Sour gas safety requirement |  |  | FAT / SAT | Package interfaces | Firewall | [5 empty] | N0510 ¦ TYRA
|  | Temperature & Pressure |  |  |  |  | Painting requirement | Flare structure | [5 empty] | D6255 ¦ LTA II
|  | Valves |  |  |  |  | Piping Stress Analysis | Geotechnical Report | [5 empty] | D6688 ¦ 9 Jackets
|  | Vents and Drains |  |  |  |  | Project schedule | Helideck | [5 empty] | D6200 ¦ SAF 6
[7 empty] | Seismic requirements | J-Tube | [5 empty] | D7358 ¦ MRJN Upgrade
[7 empty] | Software Tools | Lift | [5 empty] | D7057 ¦ MRJN TP10
[7 empty] | Speciality items | Loadout | [5 empty] | LTA Guaranteed Scope
[7 empty] | Transportation requirements | Monel Sheathing | [5 empty] | D6875 ¦ Header 9 & 3CRPO
[7 empty] | Valves | Mudmat | [5 empty] | D7072 ¦ MRJN PKG-4
[7 empty] | WCR and Limitations | Not to exceed weight | [5 empty] | D6847 ¦ Hasbah
[8 empty] | Passive Fire Protection | [5 empty] | D5854 ¦ SAFANIYA
[8 empty] | Pile Drivability | [5 empty] | D6376 ¦ SAF II
[8 empty] | Pile / Pile Penetration | [5 empty] | D7068 ¦ MRJN PKG 1
[8 empty] | Rely-upon data | [5 empty] | D6463 ¦ SAF 5
[8 empty] | Riser | [5 empty] | D7018 ¦ SAF Phase8
[8 empty] | Riser Protector | [5 empty] | D6758 ¦Umblical replacement
Sea-fastening
Shock Cells
Subsea Bridge
Transportation
Weight Control Report
Topside
Jacket
Trial fit
Caisson
Pile Driving Hammer
Fabrication Team
Pipe Support / Modular supp
Stair / Stair Tower
Equipment / Supports
Transporation
Painting
Brownfield
Connection / Bolted
3D Modelling
Insurance Pile
Insert Pile
Marine Team
CSE
Air Gap
HUC Team
Floor / Plating / Grating
Analysis / Design / FEA
Crimp Plate
Deflection
Bidding
Drains
Clamps
Padeye
Nodes
Temporary support
Constructability
Structural MTO
Installation